## Emergency Response
Plans Submitted for Review and Approval
Emergency Response and Health and Safety Plan_Rev02
Compiled comments from: Worker's Safety and Compensation Board, Health and Social Services, Community Services, and Mineral Resources
Emergency Response Plan
Document Reference | Comment | Required Action | Company Response | Final Action Required/Term & Condition
Forward | A concordance table is missing from the plan | BMC is to provide a concordance table that demonstrates how all applicable decision document terms and conditions and proponent commitments have been addressed. This concordance table should also indicate where revisions have been made based upon the information requests outlined in this table.
Glossary and throughout document | As of July 1, 2022, Workers’ Safety and Compensation Board has changed their name. Updated names include: Workers’ Safety and Compensation Board Workplace Health and Safety Workers’ Safety and Compensation Act Workplace Safety Regulations | BMC to update the glossary and all references within the plan.
Glossary | Definition of Serious Accident and Serious Injury has changed with new Workers' Safety and Compensation Act. | BMC to review Part 3, Section 57 of new Workers’ Safety and Compensation Act for updated list, and make required changes in revised plan
Section 2.4.5 - Mine Rescue Team | Will BMC have any agreements with other mine operators in the area? | BMC to acknowledge the comment with revised wording in the next plan submission
Section 2.4.6 -Medical Personnel | It is unclear what range of medical services will be provided on site and how they related to the level of medical professional available. | BMC to provide further delineation on medical services provided on site in accordance with the medical professionals available and their legislated and regulated authorities versus what services will be required of the community nursing stations, hospitals, etc.
Section 2.4.6 -Medical Personnel | More clarification required on the qualifications of full time medical personnel on site, ratio of medical personnel on shift per number of workers through different mine phases including construction, operations and closure. It was noted in the Phase 4 workshop that a Nurse, paramedic and OHS level 3 will be on for each shift, plus an additional OHS level 3 will be on call. Reminder that any health professionals being used (nurses, doctors or pharmacists) should all be licensed in the Yukon. | BMC to acknowledge the comment with revised wording in the next plan submission
Section 2.4.6 -Medical Personnel | More clarification required on the storage of medical supplies on site (e.g., perscription drug storage and administration) | BMC to acknowledge the comment with revised wording in the next plan submission
Section 2.9 - Mine Rescue Resources | BMC to ensure facilities, gear and training required for the project meet the Yukon Mine Rescue Guidelines and workers are trained to the Western Canada Mine Rescue Manual. | BMC to update information and references to represent all requirements
Section 2.9 - Mine Rescue Resources | It is not clear if BMC has done a risk assessment of the workplace as required by Section 18.02 of the WHS regulations. This will support the determination of equipment, supplies, facilities, attendents and service, etc required on site along with section 18 of the regulations. | BMC to edit plan to present required facilities, gear, training required for the project based on section 18 requirements and risk assessment process.
Section 2.9 - Mine Rescue Resources | Workers’ Safety and Compensation Board must be notified if the Emergency Response Team is activated for any reason. Notification must be provided to the appointed WHS Duty Officer at 867-667-5450 or 800-661-0443. | BMC to acknowledge the comment with revised wording in the next plan submission and include notification in any procedural documents provided at site.
Section 2.9 - Mine Rescue Resources | There is no mention in the plan that Workers’ Safety and Compensation board can provide resources for emergency rescues if needed. | BMC to contact WHS Mine Rescue Coordinator for additional information on the services/resources that can provided in the event of a mine emergency. This should be reflected in the plan.
Section 2.13 - Emergency Response Proceedures | The plan does not consider the potential case of a fatality | BMC to include procedure to follow in the case of a fatality
Section 2.13.8 - Underground Emergency Action Plan | The plan lacks any details on underground works, and should at least include high level procedures if underground work is mentioned in other plans. | BMC should include emergency procedures for underground work in the plan at this stage, or submit a separate Undergound Emergency Response Plan for review.
Section 3.1 - Non-urgent Medical Evacuation | Should reference section 2.4.6 medical professionals on site and the level of service available from them to provide more context as to what services may be required of the neighbouring communities (particularly Ross River and Faro, as they already have limited capacity). | BMC to update section with additional context on medical services provided on site and when a non-urgent medical evacuation would be necessary and what services would be asked of the neighbouring communities.
Section 3.1 and 3.2 - Medical Evacuations | EMS does not provide dispatch services for mine sites. There are a number of inaccuracies in section 3.2. | BMC is encouraged to reach out to EMS to ensure their services are appropriately referenced in this plan.
Section 3.3 - Serious Accidents and Serious Injuries | This section is inconsistent with the new Workers' Safety and Compensation Act. See Part 3 Section 57. | Update section according to new Act.
Section 3.6 - JOHSC | This section is inconsistent with the new Workers' Safety and Compensation Act. See Part 3 Sections 36-43. | Update section according to new Act.
NOTE to BMC | If the mine site will be providing access to medical care (outside of an emergency situation) this will need to be done in accordance with health professional legislation and regulations. BMC should connect with Professional Licensing and Regulatory Affairs, Community Services, Yukon government.
Links: | Yukon Mine Rescue Guidelines
Workers' Safety and Compensation Act

## Road Construction
Plans Submitted for Review and Approval
Road Construction Plan_Rev02
Comments from Mineral Resources Branch
Road Construction Plan
Document Reference | Comment | Required Action | Company Response | Final Action Required/Term & Condition
Throughout plan | It would help in the review if BMC replaced all general terms with more specific information. For example: i. Replace “reducing water velocity across the ground” with how BMC intends to do that. ii. Replace “speed limit” with specific speed limit. iii. Replace “dust suppressant” with specific suppressant such as water, calcium, or other. | BMC to acknowledge the comment with revised wording in the next plan submission
Forward | A concordance table is missing from the plan | BMC is to provide a concordance table that demonstrates how all applicable decision document terms and conditions and proponent commitments have been addressed. This concordance table should also indicate where revisions have been made based upon the information requests outlined in this table.
Section 1 - introduction | Mention of the Tote Road upgrades. It is the understanding of Mineral Resources that 5 km of the Tote Road will fall within the QML. See comment on appendices for required submissions. | Correct language to say that the Tote Road upgrades will impact the QML. BMC to include additional section in plan regarding Tote Road upgrades, etc., and include reference to associated and required analyses and reports appended to this plan.
Section 2.2 - Fundation Preparation | The plan is missing reference to the Heritage Resources Protection plan or any procedures to follow when initially excavating for road construction. HRPP states "Prior to the start of construction, Site Management and the Environmental Department will review previous heritage impact assessment to ensure construction activities do not have the potential to affect any know heritage resource." | BMC to acknowledge the comment with revised wording in the next plan submission
Section 2.2 - Fundation Preparation | The plan is missing details around frozen materials management. See General comments for Open Pit MDOP. | BMC to include a section on frozen materials management within the next plan revision.
Section 3 - Road design and Specifications | The plan is missing descriptions of any planned road maintenance activities. Snow clearing may require adjustment of berms etc, and should be noted in the plans. | BMC to include a section on road maintenance within the next plan revision
Section 3 - Road Design and Specifications | The plan only includes 2 different road designs - haul roads and service roads, which seems like an oversimplification for all roads and trails planned fo rthe site. | BMC to confirm if they plan on having different classifications of service roads, or will they all be the same as the Tote road design? Will all haul roads be the same design? Will there be a separate trail design? Will there be any consideration of different in-situ material types for backslope grades etc.? Will there be any consideration of slope length and the addition of benches etc.?
Section 3 - Road Design and Specifications | The plan only references YWS regulations as design standards for all roads. The plan should include references to all standards used during the designs including standards from other jurisdictions. | BMC to include all design standards used for the road design within the next plan revision
Section 3 - Road Design and Specifications | The plan does not include any design criteria such as design vehicle, design speed, minimum radius, number of lanes, sight distances etc. | BMC to include all design criteria used for the road design within the next plan revision.
Section 3 - Road Design and Specifications | The plan is missing specifications for material types etc. | BMC to include specifications for each material type intended to be used in road construction within the next plan revision.
Section 3 - Road Design and Specifications | The road design drawings are annotated as "Feasibility Level Designs". This leaves room for significant design changes after licensing, which could affect material quantities and therefore borrow sources etc. required. | The drawings should be advanced to a minimum 60% design level. A reminder that design drawings need to be stamped by a Yukon Professional Engineer.
Section 3 - Road Design and Specifications | The plan is missing detail on signage types and locations on site. | The revised designs should include a site signage plan that includes types and locations of signage on site.
Section 3 - Road design and Specifications | The plan is missing standard operating protocols such as details regarding specific radio calling procedures, right of way procedures | BMC to include a section on intended operating protocols within the next plan revision
Section 3.2 - Design basis | More detailed rationale is required for the design and should directly reconcile with indicated guidance and standards used. Roadway structure, drainage requirements for expected site run-off, truck size on each road classification, turning radiuses, safety requirements such as runaway lanes, etc., should all be covered. Note that road construction drawings will need to be signed off by a Yukon PEng. | Provide additional detail on the design basis for each road classification.
Section 3.3 - Construction | The plan is missing any mention of best management practices for road construction such as lift thicknesses, compaction, process for dealing with high moisture content soils or silty soils, | BMC to include a section on best management practices within the next plan revision
Section 3.3 - Construction | What does the closure of roadways and temporary trails look like? Will BMC leave them until the end of the mine life, or close them as they go? | BMC to include a section within 3.3 that discusses the plan for road closure and de-activiation, including temporary trails.
Section 3.3.1 -Bulk Earthworks | Need more information on borrow sources used for road construction. | Clarify which borrow pits are referenced and what authorization they fall within.
Section 3.5 - Staging areas | The plans for the construction laydown area are unclear, location, size, future use or reclamation, etc. | Provide additional detail on the staging areas planned for road construction use.
Section 4 - Borrow Sources | The plan does not include enough detail on the borrow pits intended for use under the QML. | BMC to review YG Plan Requirement Guidance and include all required information in next plan submission.
Appendicies | The plan is missing appendicies for geotechnical and geochemical evaluations completed for the site as required by the YG Plan Requirement Guildeine. | BMC to include any applicable geotechnical assessments or evaluations (such as those listed in section 6 of the plan) as appendicies. Any engineered reports or assessments need to be stamped by a Yukon PEng.

## Open Pit MDOP
Plans Submitted for Review and Approval
Open Pit Mine Development and Operations Plan_Rev02
Compiled comments from: Workers' Safety and Compensation Board, Mineral Resources Branch
Open Pit Mine Development and Operations Plan
Document Reference | Comment | Required Action | Company Response | Final Action Required/Term & Condition
General | This plan focuses on open pit development and operations. There is very little detailed information on general mine construction nor the planned underground mining. Generally, QMLs contain a "Mine Development and Operations Plan" that includes mine construction, and all mining development and operations (open pit and underground in the case of KZK). This more detailed and delineated information is required. It is up to BMC how this information will be presented under the QML. | Options for BMC: a) Include separate sections within this plan to cover both construction and underground mining development and operations, changing the name of the plan to represent the broader information. B) provide separate plans for the mine construction, development and operations as well as the underground mine development and operations. Each plan to be named appropriately.
General | There are a number or requests related to further delineation of mined material as per the mining phase, classification of material, etc. More data are required to support this information. | Provide the most recent and accurate open pit block model.
General | The geotechnical assessment completed by Dempers and Seymour (2019) is used as a basis for the open pit design. | Provide the Dempers & Seymour, 2019, geotechnical assessment report.
General | During our phase 4 workshop, BMC mentioned they have a hazard assessment report similar to what was suggested by WHS contractor (Geotechnical hazards report - floods, landslides, etc.). | BMC to provide hazards report to Mineral Resources Branch.
General | Frozen material management is unclear throughout the application although there is potential to come across permafrost during mine construction. BMC may consider developing a separate frozen material management plan or including it in the waste rock and overburden plan. Either way, frozen material management strategies should be presented in the mine development and operations plan as it directly impacts mine construction and development. | BMC to reference frozen material management strategies in applicable sections of plan (e.g. Section 3.1 - site preparation).
All drawings / designs in the plan | The Plan Requirement Guidance for Quartz Mining Projects states "This plan must be accompanied by issued-for-use construction drawings stamped by an engineer licensed to practice in Yukon." Currently all drawings are at a feasibility level. | The drawings should be advanced to a minimum 60% design level. A reminder that design drawings need to be stamped by a Yukon Professional Engineer.
Forward | A concordance table is missing from the plan | BMC is to provide a concordance table that demonstrates how all applicable decision document terms and conditions and proponent commitments have been addressed. This concordance table should also indicate where revisions have been made based upon the information requests outlined in this table.
Introduction | This section in the plan does not provide enough detail, and is vague. The introduction should provide a full overview/summary of mine development and operations. | BMC to include a section on the general overview of the mine through it's various life cycles. This should include at a minimum: mine facilities overview, description of pits, rate of mining, general timeline of extraction, processing to closure, ore vs waste/tailings tonnage, crushing size prior to processing, etc.
Throughout and Section 2.1 - Geology | The language in this plan needs to be consistent and provide clarity on zone vs pit. Figure 2-1 shows one large pit called the ABM Pit, but table 2-1 breaks it into the ABM Pit and the Krakatoa Pit. It is assumed that the ABM and Krakatoa zones make up the extent of the ABM pit, but this needs to be clarified and consistent in the plan. | BMC to clarify throughout the plan ABM zone, Krakatoa zone, ABM open pit, Krakatoa open pit terms used and how they relate to one another.
Section 2.2.1 - Mine Plan | This section does not provide enough detail, and is vague. A gantt chart was provided in the BMC presentation at the May 24th meeting that provided the scheduling details needed for the plan. This section should generally be expanded upon to provide a more complete picture of the mine plan. | BMC to provide more detail, for example: stages of development and production schedule, size of pit (depth, width), design of haul roads, daily and monthly mining rates with diluted averages, pre-production material use/placement, and should acknowledge end placement (e.g., X tonnes in Class C facility), etc.
Section 2.3 - Geotechnical Assessment | There are no clear seismic design considerations. | BMC to include a section discussing the seismic design considerations for the open pit and underground design in the next plan submission
Section 2.3 - Geotechnical Assessment | The plan mentions that the pit slope design is based on dewatered slopes, but does not provide detail on how this is acheived. | BMC to provide reference to other plans where this is addressed, and update this plan accordingly to ensure consistency.
Section 2.3 - Geotechnical Assessment | The plan mentions that the pit slope design is based on a minimum factor of safety of 1.2 but does not provide a reference to the guidelines used. | BMC to provide rationale for a factor of safety of 1.2, and which standard/guidance this follows.
Section 2.3 and Table 2-3 | Lithologies described are generalized in comparison and difficult to reconcile with the Site Characterization Plan. Lithologies must be consistently referenced and reconciled across plans. | BMC to reconcile lithology categories and descriptions, particularly with the Site Characterization Plan and appended ARD/ML report.
Section 2.3 and Tables 2-4 and 2-5 | Sampling for both UCS and stregth parameters from direct shear tests are heavily weighted in favour of the felsic volcanic lothology. It is unclear how these tests can be considered representative of the mine deposit. Figure 2-2 of the Site Characterization Plan indicates that the felsic volcanic lithology is minor in comparison to rhyolite when it comes to pit make-up volumes. | Clarify how samples taken for the UCS and strength parameters from direct shear tests are geotechnically representative of the planned mine deposit.
Section 3.1 - Site Preparation | More information is required for site preparation. This section may be better presented if it was split into 1. vegetation and clearing; 2. foundation prep and construction; 3. overburden frozen material management; etc. | BMC to expand on site preparation to give further details vegetation and clearing, foundation prep and construction, material management (including frozen material).
Section 3.1 - Site Preparation | The plan is missing reference to the Heritage Resources Protection plan or any procedures to follow when initially clearing and excavating for construction. HRPP states "Prior to the start of construction, Site Management and the Environmental Department will review previous heritage impact assessment to ensure construction activities do not have the potential to affect any know heritage resource." | BMC to acknowledge the comment with revised wording in the next plan submission
Section 3.1 - Site Preparation | It is indicated that "cleared vegetation may be mixed in with topsoil stockpiles" for future use. Are there expected timber quantities and an intended use for timber? | Clarify what type of vegetation is referred to in this section and if there is an intended use (e.g., reclamation pilot programs, seed collection, etc.).
Section 3.4.1 - Pre-Construction | The plan mentions that "pre-construction activities may commence during final licensing or post final licensing". The wording should be changed to "pre-construction activities will commence as authorizations for activities are granted/issued". | BMC to acknowledge the comment with revised wording in the next plan submission
Section 3.6 - Ore handling | Ore handling requires clarity and additional information (e.g., how ROM pad will be divided, reference to QA/QC processes, etc.). This section may be better presented by dividing up into ore handling, transport and storage, crushing of ore and waste rock, mining rate to crusher, reference to process plant plan. | BMC to acknowledge the comment with revised wording in the next plan submission
Section 3.6 - Ore handling | The plan states that The ROM pad will hold both ore for short term processing and low grade ore that may not be processed until later. | BMC to clarify that the ROM pad may hold multiple stockpiles of different ore grades or metallurgical domain, and to elaborate on the expected classifications.
Section 3.6 - Ore handling | BMC to review Workplace Health and Safety Regulations, Section 8.26 - Dust Collection. Personal Protective Equipment (PPE) is a last resort and does not replace requirements in 8.26 in the: - Crushing facilities, - Process conveyor(s) and - other dust production sources (haul roads, etc.) BMC to review Workplace Health and Safety Regulations Section 9 - Thermal Environment for the heating of buildings. | BMC to acknowledge the comment with revised wording in the next plan submission
Section 4 - Associated Mine Services and Infrastructure | This section describes anciliary infrasturcture directly associated with the mine, but does not include mention of the camp, or any laydown areas. | BMC to ensure this lists is exhaustive and accurate
Section 4.1.1 - Mining Offices and Mine Dry | Ensure facilities, gear and training required for the project meet the Yukon Mine Rescue Guidelines and workers are trained to the Western Canada Mine Rescue Manual. Ensure facilities, gear and first aid training required for the project meet Section 18 of the WHS regulations based on the risk assessment required in section 18.02. Ensure the mine dry facilities considers the Code of Practice 2022-01 Workplace Sanitary AmenitiesCode of Practice. Mine dry must have separate clean and dirty sides. | BMC to acknowledge the comment with revised wording in the next plan submission
Section 4.1.3 - Explosives and Magazine Storage Facilities | The plan states that The Project will implement operational policies and procedures that meet or exceed the required acts and regulations. | BMC to include reference to permits associated with activities and produce SOPS if not included in other authorizations.
Section 4.1.3 - Explosives and Magazine Storage Facilities | Reminder that the magazines require permits from the Workplace Health and Safety branch of the board. Applications can be found on the WHS website (see links below). | BMC to acknowledge the comment with revised wording in the next plan submission
Section 4.3 - Fuel Storage | This section should reference the Emergency Response Plan and Spill Contingency Plan in the case of a spill of diesel or LNG. | BMC to acknowledge the comment with revised wording in the next plan submission
Figures 5-1 to 5-5 | The northern-most phase shown on figure 5-1 seems to disappear in the following figures (5-2 to 5-5) | BMC to refine dawings to clarify planned stages of pit development.
Stion 5.1.2 - Ground Movement Monitoring | This section needs more elaboration such as: number, type, and location of prisms; survey methodology; definition of "regular basis" for visual inspections and survey monitoring (e.g., will engineering staff be involved in the monitoring program? Is there a threshold of movement established that would trigger some type of action? Is there pit evacuation criteria established?). If this is further delineated in the EMSRAMP, a reference should be provided. The plan requirement guide states that Stability and settlement analysis reports should be included as appendices. | BMC to acknowledge the comment with revised wording in the next plan submission
Section 5.2 - Haul Roads | BMC to ensure that information presented in this section is consistent with the Road Construction Plan | BMC to acknowledge the comment with revised wording in the next plan submission
Links: | Yukon Mine Rescue Guidelines
Western Canada Mine Rescue Manual
Code of Practice 2022-01
Application for explosives magazine stroage and use permit

## Process Plant DOP
Plans Submitted for Review and Approval
Process Plant Development and Operation Plan_Rev02
Comments from Mineral Resources Branch
Process Plant Development and Operation Plan
Document Reference | Comment | Required Action | Company Response | Final Action Required/Term & Condition
General | This plan has many procedural and processing requirements associated with the safe operation of the process plant and auxillary facilities, each of which will require an SOP. All associated SOPs are required to be appended to this plan. | Append associated SOPs to the plan
Forward | A concordance table is missing from the plan | BMC is to provide a concordance table that demonstrates how all applicable decision document terms and conditions and proponent commitments have been addressed. This concordance table should also indicate where revisions have been made based upon the information requests outlined in this table.
Section 2 - Site Preparation | This section is generally vague and needs additional information such as extent of footprint, clearing and vegetation, foundation prep and containment measures/features, frozen material management, etc.) | BMC to acknowledge the comment with revised wording in the next plan submission
Section 2 - Site Preparation | The plan states Overburden that is assessed as being suitable for construction purposes. Suitable material has not been defined in the QML application. The best place for this information is likely in the Mine Development and Operations Plan, but should be referenced where construction material is mentioned. | BMC to provide reference to where suitable construction material is classified and defined. BMC to indicate what is suitable and produce specifications for construction materials within broader QML application/ more applicable plans.
Section 2 - Site Preparation | It is unclear what is meant by or the reason for "all heavy equipment will be located directly over bedrock". | Clarify statement and it's reasoning.
Table 2-1 - Estimated Volumes of Material for Process Plant Site Preparation | The plan states "Estimated volumes of materials that will be excavated and placed to construct the surface for the Process Plant and associated infrastructure are summarized in Table 2-1." Table 2-1 indicates volumes for diferent material types, but does not specify if it is a removed, placed or a combination of both. | Clarify the estimated volumes of each material that will be removed or placed for site preparation. For material being removed, indicate where that material will be stored. For material being placed, confirm the placement meets the necessary specifications for foundation and sire preparation.
Figure 3-1 | This figure is specific to the process plant and excludes auxillary facilities. | Provide additional figure that is a blown out version as to include auxillary buildings (reagent mixing areas, reagent storage, ROM stockpile, etc.) and their general arrangement in reltaion to the process plant.
Section 3.2 - Ore Stockpiles | This section needs to be further delineated. This should include metallurgical domains and ore classifications reconcilled with Site Characterization Plan (including ARD/ML report), QA/QC for classification process, foundation prep, containment measures, segregation methods, etc. | This was partially discussed at the phase 4 workshop and further details must be provided in the updated plan.
Section 3.3 - Tailings Facilities | Note that this section may require amendment as a result of the Phase 1 IR. | BCM to make amendments as necessary
Section 3.4 - Water Management System | this section indicates that make-up water will be preferrentially drawn from a number of sources but it is unclear how the preference will be determined (e.g., water quality, quantites, proximity, etc.). | Clarify prioritization of preferrentially drawn make-up water for the Process Plant.
Section 3.4 - Water Management System | The plan states that the water treatment plant will treat mine drainage water. | BMC to confirm if this statement applies to all contact water from the whole mine site and provide reference to where this information is located.
Section 4.5 - Tailings Disposal | Note that this section may require amendment as a result of the Phase 1 IR. | Ensure information is consistent with Tailings and Waste Rock plans
Section 4.5 - Tailings Disposal | More clarity is needed on the dewatering of tailings: -what defines "high" on the filter feed tanks. -is there a cut-off of when a certain amount of off-spec tailings are produced that would trigger a mill maintenance/shut down period? | Provide additonal and more detailed information on the dewatering of tailings.
Section 4.5 - Tailings Disposal | Acknowldeging that BMC mentioned the use of a QA/QC program for tailings at our Phase 4 workshop, it is unclear in this section what the QA/QC process is prior to transport and disposal of tailings. This should be outlined here. | Outline QA/QC process for tailings transport and disposal.
Section 4.5 - Tailings Disposal | More information is required around paste fill for the underground operations. As discussed at the Phase 4 worskhop, 200,000 m3 tailings are expected to be used as paste fill. What impact will this have on the operation and closure of the Class A facility, what if a larger percentage of tailings report underground? | BMC to acknowledge the comment with revised wording in the next plan submission and ensure it is consistent with the Tailings and Waste Rock management plans.
Section 4.6 - Reagent Handilng and Preparation | The plan states Each reagent will be prepared within its own area to contain spillage. Additional information is needed and should be consistent with details required under the site preparation section. | BMC to provide clarity on how each reagent and the general storage and mixing areas will be contained within their area. Including any primary, secondary and additional containment measures.
Section 6 - Concentrate Storage and Haulage | The plan states Before leaving the concentrate storage shed, all trucks will pass through a seasonal wheel wash facility to ensure that any concentrate spillage is removed from the truck and trailers. Will there be a different type of wash facility dependent on the season, or will it only operate seasonally? If only available seasonally, provide reasoning. | BMC to acknowledge the comment with revised wording in the next plan submission
Concentrate Transportation Route to Stewart BC Figure | The figure has Junction 37 annotated as Jakes Corner. | BMC to revise annotation.
Section 7 - Power Plant | The full life cycle of power supply requirements, sources, and power plant development should be outlined more clearly in this section. In the Phase 4 workshop BMC indicated that it would start with deisel generators during construction, then move to the power plant under deisel with the potential to switch to LNG. | BMC to provide more clarity on the stages of power generation and power plant installation, and which types of fuels will be utilized during each phase. Include any plans for renewable energy source investigations or projects.