## Revisions
Original | File Name | Appendix E_20200910_BMCM1_ClosureCostEst
Update 1 | File Name | Closure Cost Model_Rev01
Revision No | Tab | Column | Row | Change
1-1 | T1-Summary | I | 6 | Added 'Select Equipment Costing Method' drop box | Depending on selections made, Rev 1-1 through 1-4 substantially change the values
1-2 | T1-Summary | I | 8 | Added 'Select Reclamation Cost Timeframe' drop box | Depending on selections made, Rev 1-1 through 1-4 substantially change the values
1-3 | T1-Summary | I | 12 | Added 'Select Cost Method for Progressive Reclamation' drop box | Depending on selections made, Rev 1-1 through 1-4 substantially change the values
1-4 | T1-Summary | I | 16 | Added 'Select Contingency Level' drop box | Depending on selections made, Rev 1-1 through 1-4 substantially change the values
1-5 | Quantities | F |  | Inserted column F to include quantities for Life of Mine (LOM)
1-6 | Quantities |  | 43 | Inserted row 43 'Class A SF - Progressively Reclaimed' to show progressive rehabilitation
1-7 | Quantities |  | 57 | Inserted row 57 "Class B SF - Progressively Reclaimed' to show progressive rehabilitation
1-8 | Quantities |  | 70 | Inserted row 70 'Class C SF - Progressively Reclaimed' to show progressive rehabilitation
1-9 | Quantities | G | 39 - 82 | Updated areas and volumes
1-10 | Quantities |  | 84 - 85 | Added rows 84 & 85, additional information only
1-11 | Quantities |  | 87 - 88 | Added rows 87 & 88, Class C claim fraction information only
1-12 | EquipProd |  |  | Reviewed and updated most productivity calculations
1-13 | LHD |  | 6 - 28 | Updated equipment selection and productivity calculations
1-14 | LHD |  | 15 | Inserted row 15 to include calculation of progessive Class C material to the Class A SF
1-15 | LHD |  | 22 | Inserted row 22 to include calculation of progessive Class C material to the Class B SF
1-16 | LHD |  | 39 - 61 | Updated full placement cost calculations
1-17 | LHD |  | 48 - 50 | Inserted rows 48-50 for allow multiple pricing methodologies for Class A SF
1-18 | LHD |  | 55 - 57 | Inserted rows 55-57 for allow multiple pricing methodologies for Class B SF
1-19 | Labour & Equip Hrs | C & E | 18 | Added estimated number of seasons for active reclamation works
1-20 | T2-Unit Rates | C | 57 - 63 | Updated Labour rates for YG-FWS effective April 1, 2020
1-21 | T2-Unit Rates | J | 7 - 54 | Updated Owner Rates based on Caterpillar and Komatsu information
1-22 | T2-Unit Rates |  | 33 - 34 | Inserted rows 33 & 34 with additional trucks
1-23 | T2-Unit Rates |  | 42 | Inserted row 42 with additional loader
1-24 | T2-Unit Rates | E | 71 | Updated Zone F costs
1-25 | T2-Unit Rates | E | 72 | Updated Zone S costs
1-26 | T3 - G&A | J | 9-28 | Updated to calculate directly from info on tab 'Labour & Equip Hrs'
1-27 | T3 - G&A | L | 9-28 | Updated to calculate directly from info on tab 'Labour & Equip Hrs'
1-28 | T10 - Infrastructure |  | 10 | Added cost of demobing camp buildings
1-29 | T10 - Infrastructure | R | 8 & 15 | Updated building breakdown labour hours
1-30 | T14 - MobDemob |  |  | Adjusted number of items for various scenarios
1-31 | T14 - MobDemob |  | 38 | Added additional truck type
1-32 | T14 - MobDemob |  | 46 | Added additional FEL type
1-33 | T14 - MobDemob | K |  | Adjustedcolumn K values to reflect ICMM mobdemob for Year 2
1-34 | T15-ICMM | K | 8 - 61 | Included ICMM costs for Year 2 based on EMR request
1-35 | T15-ICMM | N | 8 - 61 | Reviewed and updated estimates
1-36 | T15-ICMM |  | 33 - 41 | Updated rows 33-41, Site Maintenance section to be similar to 'T16-PCMM' section
1-37 | T16-PCMM | I | 70 | Updated PCMM annual MobDemob to include both ways
Update 2 | File Name | Closure Cost Model_Rev02
Revision No | Tab | Column | Row | Change
2-1 | T1-Summary |  |  | Unused rows for Tailings, Quarries and Borrow Pits, Sediment and Erosion Control removed
2-2 | T1-Summary |  |  | Roads and Trails costs moved to PCMM to accurately capture timing of activity
2-3 | T1-Summary | E | 17 | Formula edited to account for 3 years of active closure
2-4 | T1-Summary | G-I |  | Tables for activity specific Contingency and Indirect costs added
2-5 | T1-Summary | B-E | 49-58 | Table 2 added to provide sensitivity analysis of NPV rates as per IR2-45
2-6 | Quantities | F | 14 | Formula corrected to show LOM quantity
2-7 | Quantities | F | 15 | Formula corrected to show LOM quantity
2-8 | Quantities | F | 18 | Formula corrected to show LOM quantity
2-9 | Quantities | F | 20 | Formula corrected to show LOM quantity
2-10 | Quantities | F | 31 | Formula corrected to show LOM quantity
2-11 | Quantities | E-G | 76 | Formulas corrected
2-12 | Quantities | G | 78 | Formula corrected
2-13 | Quantities | G | 81 | Formula corrected
2-14 | LHD | C | 6-28 | 'Nearby Stockpilec' replaced with specific stockpile names
2-15 | T2-Unit Rates | G-J | 5-54 | Cells showing BC Blue Book and Owner equipment rates blacked out
2-16 | T2-Unit Rates | E | 72 | Unit rate for Zone S material updated based on revised quote
2-17 | T7-WSF | C | 25 | Corrected cell to read Class B 'Liner Protection' volume instead of 'Frost Protection', IR2-34
2-18 | T8-Facilities | C | 14-20 | Included estimate for cleanup, transport and disposal of any residual hazardous materials
2-19 | T14-MobDemob | L |  | Updated to match ICMM requirements
2-20 | T15-ICMM | K | 49-50 | Sampling frequency reduced due to limited disturbance for initial Year 2 period
2-21 | T15-ICMM | C | 54-56 | Monitoring section updated due to limited disturbance for initial Year 2 period
2-22 | T15-ICMM | C | 58 | Section changed to Road Closure and Reclamation, part of Rev 2-2
2-23 | T16-PCMM | C | 13 | Irrelevant commit deleted as per IR2-51
2-24 | T16-PCMM | C | 36-44 | Sections updated to separate Project Management costs from other site costs
2-25 | T16-PCMM | P | 74 | Formula corrected
2-26 | T16-PCMM | S | 74 | Formula corrected
2-27 | T16-PCMM | C | 77-79 | Surface and Groundwater costs moved to 'Monitoring' rows below for consistency
2-28 | T16-PCMM | C | 82-90 | All ongoing environmental monitoring costs placed in one section for simplicity
2-29 | T16-PCMM | I | 83-90 | Lump sum rates updated following review as per IR2-50
2-30 | T16-PCMM | C-D | 83-90 | Monitoring requirements updated to match descriptions in RCP
2-31 | T16-PCMM | D | 100-103 | Section changed to Road Closure and Reclamation, part of Rev 2-2
2-32 | T17-NPV-YR0 | B | 24 | Changed to Road Closure and Reclamation, part of Rev 2-2, flows to following sections
2-33 | T17-NPV-YR0 | B | 14-24 | Location of names shifted as a result of changes made to T16-PCMM
2-34 | T18-NPV-YR2 | B | 24 | Changed to Road Closure and Reclamation, part of Rev 2-2, flows to following sections
2-35 | T18-NPV-YR2 | B | 14-24 | Location of names shifted as a result of changes made to T16-PCMM
2-36 | T19-NPV-EOM | B | 24 | Changed to Road Closure and Reclamation, part of Rev 2-2, flows to following sections
2-37 | T19-NPV-EOM | B | 14-24 | Location of names shifted as a result of changes made to T16-PCMM
2-38 | T19-NPV-EOM | C | 52-76 | Formulas corrected
2-39 | T19-NPV-EOM | C | 81-105 | Formulas corrected
2-40 | T19-NPV-EOM | D | 79 | Commencement year for NPV calculation changed to Year 1 as per IR2-46
Update 3 | File Name | Closure Cost Model_Rev03
Revision No | Tab | Column | Row | Change
3-1 | T1-Summary | H | 27 | Indirect cost for Engineering and Survey changed
3-2 | Quantities | J | 37 | Deleted obsolete comment
3-3 | T16-PCMM | I | 83-90 | Updated costs after reducing average helicopter travel speed
Update 4 | File Name | Closure Cost Model_Rev04
Revision No | Tab | Column | Row | Change
4-1 | Quantities | E |  | Review and update Year 2 quantities
4-2 | T2-Unit Rates | E-J | 7-54 | Updated hourly equipment costs to 2023 rates
4-3 | T2-Unit Rates | C | 57-68 | Updated base wage rates to 2023 rates
4-4 | T2-Unit Rates | E | 71-82 | Reviewed and updated materials costs
4-5 | T2-Unit Rates | E | 85-94 | Reviewed and updated miscellaneous costs
4-6 | T6-Pits | I | 33 | Update pit lake treatment costs following pilot plant work
4-7 | T9-Ponds |  | 55-61 | Added disposal of HDPE liners for WRSF ponds
4-8 | T10-Infrastructure |  | 46-65 | Added reclamation of temporary construction areas
4-9 | T13 - Water | I | 57 | Revised passive treatment capital cost
4-10 | T16-PCMM | I | 83-90 | Revised monitoring costs
4-11 | T1-Summary | D | 45 | Updated 5 year average inflation rate
4-12 | T1-Summary | C-E | 52-58 | Updated sensitivity table
Update 5 | File Name | Closure Cost Model_Rev05
Revision No | Tab | Column | Row | Change
5-1 | Quantities | D-G |  | Review and update all quantities
5-2 | T1-Summary | D | 45 | Updated 5 year average inflation rate
5-3 | T7-WSF |  |  | Review and add reclamation of collection ponds and ROM pad
Update 6 | File Name | Closure Cost Model_Rev06
Revision No | Tab | Column | Row | Change
6-1 | T2-Unit Rates | E-J | 7-54 | Updated hourly equipment costs for BC Blue Book 2025/2026 rates
6-2 | T2-Unit Rates | C | 57-63 | Updated base wage rates to 2026 rates
6-3 | Quantities | D |  | Update current disturbance quantities
6-4 | T2-Unit Rates |  | 83-86, 100 | Add cost data for insitu pit lake treatment
6-5 | Quantities |  | 92-94 | Added reagent consumption quantities for insitu pit lake treatment
6-6 | T6-Pits |  | 34-36 | Increased cost detail for insitu pit late treatment
6-7 | All Sheets |  |  | Added Year 5 Scenario

## T1-Summary
[9 empty] | calcs |  | Hide and lock section
Table 1
Summary Table of Estimated Closure Costs | [9 empty] | Calculation Options
Description of Cost | Current | 2 Year | 5 Year | EOM | Implementation Contingency Cost Factors
Closure Implementation |  |  |  |  | Current | 2 Year | 5 Year | EOM |  | BC Blue Book | Select Equipment Costing Method
General & Administration | 0 | 985776 | 1966552 | 2947328 | 0% | 20% | 20% | 20%
Exploration | 100000 | 100000 | 100000 | 100000 | n/a | n/a | n/a | n/a |  | EOM | Select Reclamation Cost Timeframe
Closure Planning | 0 | 160000 | 1120000 | 2240000 | 0% | 10% | 10% | 10% |  |  |  | Total LOM = Total Costs of Reclamation
Mine Working - UG & OP | 0 | 0 | 968819.5707 | 4339481.4292 | 0% | 15% | 20% | 20% |  |  |  | EOM = Costs of Reclamation Remaining At End of Operations, Removes Progressively Completed Reclamation
Waste Rock and Tailings Storage Facilities | 0 | 83605.814 | 21268342.2118 | 30561817.15 | 0% | 15% | 20% | 20%
Surface Facilities | 0 | 674247.7684 | 4613369.7706 | 4613369.7706 | 0% | 15% | 20% | 20% |  | YG | Select Cost Method for Progressive Reclamation
Water Storage Ponds | 0 | 0 | 783161.958 | 783161.958 | 0% | 15% | 15% | 15% |  |  |  | YG = Progressive Reclamation is Costed at YG 3rd Party Rates & Equipment Sizes
Infrastructure | 230064.3214 | 708798.6689 | 743398.0485 | 743398.0485 | 0% | 20% | 20% | 20% |  |  |  | Mining = Progressive Reclamatin is Costed as per the Open Pit Mining Contract
Waste Disposal / Remediation | 0 | 19636.568 | 19636.568 | 19636.568 | 0% | 15% | 15% | 15%
Water Management | 0 | 224565.4964 | 4415405.5187 | 4598682.987 | 0% | 15% | 25% | 25% |  | Medium | Select Contingency Level
Mob/Demob | 0 | 258095.25 | 366632 | 366632 | 0% | 10% | 10% | 10%
Interim Care, Maintenance, and Monitoring Costs | 0 | 389293.1 | 2709272.1 | 3336272.1 | 0% | 15% | 15% | 15%
Sub-total Implementation Costs | 330064.3214 | 3604018.6657 | 39074589.7464 | 54649780.0114
Contingency Costs | 0 | 589426.7708 | 7691421.4939 | 10672273.4203 | Average Contingency | 16.35% | 19.68% | 19.53%
Indirect Costs | 0 | 720803.7331 | 7814917.9493 | 10929956.0023
Cost Inflation 1 | 0 | 325957.5394 | 9340669.8703 | 35838193.6805 | Implementation Indirect Cost Factors
Total Implementation Costs | 330064.3214 | 4650779.9382 | 56230177.566 | 101417929.6942 | Contractors | 5%
[5 empty] | Insurance | 0%
Post Closure Costs |  |  |  |  | Bonding | 3%
Capital Costs |  |  |  |  | Taxes | 0%
Pre-Closure Site Environmental Assessment | 0 | 60000 | 120000 | 120000 | Agency administration | 0%
Post-Closure Site Environmental Assessment | 0 | 35000 | 70000 | 70000 | Engineering and Surveying | 7%
Instrumentation | 0 | 0 | 25000 | 25000 | Project Management | 5%
Recurring Costs (NPV) |  |  |  |  | Total | 20%
Water Treatment | 0 | 0 | 23426.4104 | 16702.7069
Staff/Equipment | 0 | 436635.1577 | 906654.2169 | 1064199.0619
Maintenance | 0 | 123116.8129 | 337582.902 | 616162.0361
Transportation | 0 | 88329.2244 | 252167.2103 | 285027.8996 | Post Closure Cost Factors
Monitoring | 64593.0718 | 2992920.7491 | 4460678.0775 | 6127936.4229 | Contingency | Indirects
Sub-total Post Closure Costs | 64593.0718 | 3736001.9441 | 6195508.8171 | 8325028.1274 | 20% | 15%
Contingency Costs | 12918.6144 | 747200.3888 | 1239101.7634 | 1665005.6255
Indirect Costs | 9688.9608 | 560400.2916 | 929326.3226 | 1248754.2191
Total Post Closure Costs | 74282.0326 | 4296402.2357 | 7124835.1397 | 9573782.3466
Total Closure Costs | 404346.354 | 8947182.1739 | 63355012.7058 | 110991712.0408
Contingency Costs | 12918.6144 | 1336627.1596 | 8930523.2573 | 12337279.0458
Total Closure Costs (incl Contingency) | 417264.9684 | 10283809.3335 | 72285535.9631 | 123328991.0866
Inflation Rate (Bank of Canada 5 year ave) |  | 3.7%

## Quantities
Table 8
Quantities
ID | Remediation Unit | Quantity Current (to end 2025) | Quantity Year 2 | Quantity Year 5 | Quantity LOM | Quantity End of Mine | Unit | Basis
| Mill Site | 0 | 200900 | 200900 | 200900 | 200900 | m2 | Surface footprint feasibility design file
| Temporary Offices and Fuel Management | 0 | 51600 | 0 | 0 | 0 | m2 | Surface footprint feasibility design file
| Borrow Pit and Crushing/Screening Plant and Stockpiles | 0 | 171900 | 0 | 0 | 0 | m2 | Surface footprint feasibility design file
| Mining Workshop, Go Bay, Fuel Facility | 0 | 0 | 66615 | 66615 | 66615 | m2 | Surface footprint feasibility design file
| Explosives Facilities and magazines | 0 | 200 | 29900 | 29900 | 29900 | m2 | Surface footprint feasibility design file
| Incinerator and Landfill | 0 | 6700 | 6700 | 6700 | 6700 | m2 | Surface footprint feasibility design file
| Camp Area | 42800 | 53800 | 53800 | 53800 | 53800 | m2 | Surface footprint feasibility design file
| Core Storage Area | 8200 | 12400 | 12400 | 12400 | 12400 | m2 | Surface footprint feasibility design file
| Roads | 14.27 | 15.592 | 15.5 | 20.388 | 20.388 | km | Surface footprint feasibility design file
| Lower Water Management Pond Berm | 0 | 0 | 24400 | 24400 | 24400 | m2 | Feasibility design file
| Lower Water Management Pond footprint | 0 | 0 | 151500 | 151500 | 151500 | m2 | Surface footprint feasibility design file
| Lower Water Management Pond Embankment, Excess Material Excavated | 0 | 0 | 126730 | 126730 | 126730 | m3 | Feasibility design file
| Lower Water Management Pond Embankment | 0 | 0 | 229659 | 229659 | 229659 | m3 | Feasibility design file
| Lower Water Management Pond Liner | 0 | 0 | 118856 | 118856 | 118856 | m2 | Feasibility design file
| Upper Water Management Pond Berm | 0 | 0 | 24700 | 24700 | 24700 | m2 | Feasibility design file
| Upper Water Management Pond footprint | 0 | 0 | 132800 | 132800 | 132800 | m2 | Surface footprint feasibility design file
| Upper Water Management Pond Embankment, Excess Material Excavated | 0 | 0 | 111165 | 111165 | 111165 | m3 | Feasibility design file
| Upper Water Management Pond Embankment | 0 | 0 | 198080 | 198080 | 198080 | m3 | Feasibility design file
| Upper Water Management Pond Liner | 0 | 0 | 102858 | 102858 | 102858 | m2 | Feasibility design file
| Pit Rim Pond | 0 | 0 | 35100 | 35100 | 35100 | m2 | Surface footprint feasibility design file
| Pit Rim Pond Liner | 0 | 0 | 22000 | 22000 | 22000 | m2 | Surface footprint feasibility design file
| Overburden Stockpile | 0 | 78900 | 325400 | 474700 | 474700 | m2 | Surface footprint feasibility design file
| Overburden Stockpile Collection Pond | 0 | 34700 | 34700 | 34700 | 34700 | m2 | Surface footprint feasibility design file
| Overburden Stockpile - Collection Pond Liner | 0 | 0 | 9000 | 9000 | 9000 | m2 | Feasibility design file
| Overburden Stockpile - Regrade volume (assumed 0.1 m cut) | 0 | 7890 | 32540 | 47470 | 47470 | m3 | Estimate
| Topsoil Stockpile | 0 | 42200 | 227300 | 320600 | 160300 | m2 | Surface footprint feasibility design file
| Topsoil Stockpile - Regrade volume (assumed 0.10 m cut) | 0 | 4220 | 22730 | 32060 | 16030 | m3 | Estimate
| Pit | 0 | 0 | 487900 | 881000 | 881000 | m2 | Surface footprint feasibility design file
| Pit Perimeter | 0 | 0 | 3950 | 4600 | 4600 | m | Surface footprint feasibility design file
| Pit Safety Berm Volume (m3/m) | 0 | 0 | 3.8 | 3.8 | 3.8 | m3/m | 1.5 m high, 1.5:1 side slopes, 0.3 m crest
| Pit Safety Berm Volume (m3) | 0 | 0 | 15010 | 17480 | 17480 | m3 | Calculated
| Drainage channels to be reclaimed - length | 0 | 16900 | 21900 | 33060 | 33060 | m | Surface footprint feasibility design file
| Drainage channels fill volume | 0 | 102600 | 127000 | 166400 | 166400 | m3 | Feasibility design file
| Drainage channels to be reclaimed - Regrade quantities | 0 | 5070 | 6570 | 9918 | 9918 | m3 | Estimate, D6 with 3 m wide blade, 0.1 m cut
| Finlayson Creek Pipeline | 0 | 0 | 4970 | 4970 | 4970 | m | Feasibility design file
| Dewatering Trenches - Total Area | 0 | 0 | 47500 | 0 | 0 | m2 | Surface footprint feasibility design file
| Dewatering Trenches - Regrade Area | 0 | 0 | 47500 | 0 | 0 | m2 | Surface footprint feasibility design file
| Dewatering Trenches - Backfill Quantities | 0 | 0 | 311400 | 0 | 0 | m3 | Feasibility design file
| Dewatering Trenches - Regrade Quantities | 0 | 0 | 4750 | 0 | 0 | m3 | Calculated
| Class A SF - Surface Area | 0 | 0 | 227900 | 739200 | 739200 | m2 | Feasibility design file
| Class A SF - Surface Area, Cleared not Used | 0 | 0 | 163400 | 0 | 0 | m2 | Feasibility design file | Cleared for expansion, but does not have rock or tailings placed on it
| Class A SF - Buttress Area | 0 | 0 | 134400 | 134400 | 134400 | m2 | Feasibility design file | Will be reclaimed prior to closure
| Class A - Collection Pond | 0 | 0 | 82300 | 82300 | 82300 | m2 | Surface footprint feasibility design file
| Class A - Collection Pond Liner | 0 | 0 | 25000 | 25000 | 25000 | m2 | Feasibility design file
| Class A SF - incl Buttress & Pond | 0 | 0 | 444600 | 955900 | 955900 | m2 | Calculated
| Class A SF - Progressively Reclaimed | 0 | 0 | 0 | 0 | 504000 | m2 | Estimate | All buttress and 50% Class A
| Class A SF - Final Year Surface Area | 0 | 0 | 444600 | 955900 | 451900 | m2 | Calculated | Class A Surface plus Buttress plus pond
| Class A SF - Cover Liner Protection | 0 | 0 | 113950 | 369600 | 184800 | m3 | Calculated | Surface Area Only, does not include pond area
| Class A SF - Cover Glacial Till | 0 | 0 | 113950 | 369600 | 184800 | m3 | Calculated | Surface Area Only, does not include pond area
| Class A SF - Frost Protection Layer | 0 | 0 | 683700 | 2217600 | 1108800 | m3 | Calculated | Surface Area Only, does not include pond area
| Class A SF - Growth Media - Overburden | 0 | 0 | 91200 | 143385 | 67785 | m3 | Calculated | Surface Area, Buttress, Pond
| Class A SF - Growth Media - Topsoil | 0 | 0 | 91200 | 143385 | 67785 | m3 | Calculated | Surface Area, Buttress, Pond
| Class A SF - Cover HDPE Geomembrane | 0 | 0 | 227900 | 739200 | 235200 | m2 | Calculated | Surface Area Only
| Class A SF - Revegetation Area | 0 | 0 | 608000 | 955900 | 451900 | m2 | Calculated | Surface Area, Buttress, Pond
| Class B SF - Surface Area | 0 | 0 | 242400 | 673100 | 673100 | m2 | Feasibility design file
| Class B SF - Surface Area, Cleared not Used | 0 | 0 | 77600 | 0 | 0 | m2 | Feasibility design file | Cleared for expansion, but does not have rock or tailings placed on it
| Class B SF - LGO & ROM | 0 | 0 | 151715 | 151715 | 151715 | m2 | Feasibility design file
| Class B - Collection Pond | 0 | 0 | 42400 | 42400 | 42400 | m2 | Surface footprint feasibility design file
| Class B - Collection Pond Liner | 0 | 0 | 17000 | 17000 | 17000 | m2 | Feasibility design file
| Class B SF - incl ROM & Pond | 0 | 0 | 436515 | 867215 | 867215 | m2 | Calculated
| Class B SF - Progressively Reclaimed | 0 | 0 | 0 | 0 | 336550 | m2 | Estimate
| Class B SF - Final Year Surface Area | 0 | 0 | 436515 | 867215 | 530665 | m2 | Calculated | Includes ROM and LGO
| Class B SF - Cover Liner Protection | 0 | 0 | 121200 | 336550 | 168275 | m3 | Calculated | Surface Area, does not include pond, ROM/LGO
| Class B SF - Cover Glacial Till | 0 | 0 | 121200 | 336550 | 168275 | m3 | Calculated | Surface Area, does not include pond, ROM/LGO
| Class B SF - Frost Protection Layer | 0 | 0 | 727200 | 2019300 | 1009650 | m3 | Calculated | Surface Area, does not include pond, ROM/LGO
| Class B SF - Growth Media - Overburden | 0 | 0 | 77130 | 130095 | 79605 | m3 | Calculated | Surface Area, ROM, Pond
| Class B SF - Growth Media - Topsoil | 0 | 0 | 77130 | 130095 | 79605 | m3 | Calculated | Surface Area, ROM, Pond
| Class B SF - Cover HDPE Geomembrane | 0 | 0 | 242400 | 673100 | 336550 | m2 | Calculated | Surface Area
| Class B SF - Revegetation Area | 0 | 0 | 514200 | 867300 | 530700 | m2 | Calculated | Surface Area, ROM, Pond
| Class C SF - Surface Area | 0 | 0 | 352500 | 1267000 | 1267000 | m2 | Feasibility design file
| Class C - Collection Pond | 0 | 0 | 33300 | 33300 | 33300 | m2 | Surface footprint feasibility design file
| Class C - Collection Pond Liner | 0 | 0 | 13000 | 13000 | 13000 | m2 | Feasibility design file
| Class C SF - SF & Pond | 0 | 0 | 385800 | 1300300 | 1300300 | m2 | Calculated
| Class C SF - Progressively Reclaimed | 0 | 0 | 0 | 0 | 0 | m2 | Estimate
| Class C SF - Final Year Surface Area | 0 | 0 | 385800 | 1300300 | 1300300 | m2 | Calculated
| Class C SF - Growth Media - Overburden | 0 | 0 | 57870 | 195045 | 200040 | m3 | Calculated | Surface Area, Pond
| Class C SF - Growth Media - Topsoil | 0 | 0 | 57870 | 195045 | 200040 | m3 | Calculated | Surface Area, Pond
| Class C SF - Revegetation Area | 0 | 0 | 385800 | 1300300 | 1300300 | m2 | Calculated | Surface Area, Pond
| Total revegetation area | 51000 | 653300 | 2409130 | 4383530 | 3382680 | m2 | Calculated
| Total revegetation area excluding covers | 51000 | 653300 | 1175515 | 1704230 | 1099815 | m2 | Calculated
| Total revegetation area covers | 0 | 0 | 1233615 | 2679300 | 2282865 | m2 | Calculated
| Class C material for Class A & Class B frost protection |  |  | 470300 | 1412300 | 982565 | m2 | Calculated
| Class C material for Class A & Class B frost protection |  |  | 1410900 | 4236900 | 2947695 | m3 | Calculated
| Frost Protection for Class A - cover only |  |  | 683700 | 2217600 | 2217600 | m3 | Calculated
| Frost Protection for Class B - cover only |  |  | 727200 | 2019300 | 2019300 | m3 | Calculated
| Class C Claim Fraction |  |  |  |  | 196089 | m2
| Class C Claim Fraction, Percentage |  |  |  |  | 15.4766 | %
Pit Lake Treatment
| Ferric Sulphate 60% consumption |  |  | 4473 | 31500 | 31500 | kg | Calculated mass for treatment as noted in reference pdf file
| Glycerine 80% consumption |  |  | 335475 | 2362500 | 2362500 | kg | Calculated mass for treatment as noted in reference pdf file
| Active Closure Phase Water Treatment Volumes (Combined 3 years) | 0 | 0 | 975036 | 1462683 | 1462683 | m3 | Water Balance Model
| Transitional Closure Phase Water Treatment Volumes (Combined 12 years) | 0 | 0 | 12073 | 12301 | 12301 | m3 | Water Balance Model
| Interim Closure Water Treatment Volume (2 years) | 0 | 0 | 500000 | 800000 | 800000 | m3 | Estimate
Note on F6: George Smith: These two areas now covered over by Class A WSF liner
Note on D10: George Smith: Included in camp area total
Note on F102: George Smith: At end of Year 5 14.2% of volume of final pit has been mined
Note on F105: George Smith: Assumes 2 years Active Closure as reduced disturbance compared to LOM
Note on F106: George Smith: Assumes 8 years Transition Closure as reduced disturbance compared to LOM

## EquipProd
Summary of Individual Equipment Productivities
Unit | m3/hr
D6 Rock pushing | 104.9645
D6 Loose recontouring | 334.5743
D6 Linear recontouring | 250.9307
D6 Berm building | 86.5957
D8 Rock pushing | 157.4467
D8 Loose recontouring | 541.6917
D8 Linear recontouring | 406.2688
D8 Berm building | 140.2026
D9 Rock pushing | 230.9219
D9 Rock recontouring | 479.8376
D9 Rock recontouring - long push | 109.9628
D9 Loose recontouring | 764.7412
D9 Linear recontouring | 573.5559
D9 Berm building | 197.933
D10 Rock pushing | 304.397
D10 Loose recontouring | 1083.3834
D10 Linear recontouring | 812.5376
D10 Berm building | 280.4051
Cat 329 loose loading | 252
Cat 329 digging | 132
Cat 235 loose loading | 273.6
Cat 235 digging | 156
Cat 345 loose loading | 348
Cat 345 rock loading | 276
Cat 345 digging | 240
Roller compacting | 226.2171
Zone F - Crush & Screen | 121.5789
Zone S - Crush & Screen | 143.1579
Cat 966 Rock Loading | 233.0645
Cat 980 Rock Loading | 301.6129
Cat 988 Crushed Loading | 429.8507
Cat 988 Soil/Gravel Loading | 443.0769
Cat 988 Rock Loading | 405.9701
Cat 992 Rock Loading | 631.5972
Dozer Production Rates
Job Condition Correction Factors
[6 empty] | Operator |  | Material |  | Slot Dozing | Side by Side Dozing | Visibility |  |  | Job Efficiency |  | Grades |  | 5
Dozer | Activity | Assumed Average Dozing Distance | Uncorrected Est. Dozing Production | Corrected Est. Dozing Production | Est. Linear Dozing Production | Description | Factor | Description | Factor | [5 empty] | Description | Factor | % Grade | Factor
|  | m | Lm3/hr | Lm3/hr | m/hr | [7 empty] | Weight | Linear |  |  |  |  | $/m3
CAT D6D | D6 Rock pushing | 60 | 250 | 104.9645 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | -3 | 1.05 | 2.74
CAT D6D | D6 Loose recontouring | 15 | 525 | 334.5743 |  | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 1 | 50 min/hr | 0.83 | 0 | 1 | 0.8596
CAT D6D | D6 Linear recontouring | 15 | 525 | 250.9307 | 75.2792 | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 0.75 | 50 min/hr | 0.83 | 0 | 1 | 1.1461
CAT D6D | D6 Berm building | 15 | 525 | 86.5957 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 0.75 | 50 min/hr | 0.83 | 20 | 0.55 | 3.3212
CAT D8R | D8 Rock pushing | 60 | 375 | 157.4467 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | -3 | 1.05 | 2.3344
CAT D8R | D8 Loose recontouring | 15 | 850 | 541.6917 |  | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 1 | 50 min/hr | 0.83 | 0 | 1 | 0.67852
CAT D8R | D8 Linear recontouring | 15 | 850 | 406.2688 | 121.8806 | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 0.75 | 50 min/hr | 0.83 | 0 | 1 | 0.9047
CAT D8R | D8 Berm building | 15 | 850 | 140.2026 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 0.75 | 50 min/hr | 0.83 | 20 | 0.55 | 2.6216
CAT D9N | D9 Rock pushing | 60 | 550 | 230.9219 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | -3 | 1.05 | 2.1572
CAT D9N | D9 Rock recontouring | 15 | 1200 | 479.8376 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | 0 | 1 | 1.0382
CAT D9N | D9 Rock recontouring - long push | 120 | 275 | 109.9628 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | 0 | 1 | 4.5302
CAT D9N | D9 Loose recontouring | 15 | 1200 | 764.7412 |  | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 1 | 50 min/hr | 0.83 | 0 | 1 | 0.6514
CAT D9N | D9 Linear recontouring | 15 | 1200 | 573.5559 | 172.0668 | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 0.75 | 50 min/hr | 0.83 | 0 | 1 | 0.86853
CAT D9N | D9 Berm building | 15 | 1200 | 197.933 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 0.75 | 50 min/hr | 0.83 | 20 | 0.55 | 2.5168
CAT D10N | D10 Rock pushing | 60 | 725 | 304.397 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 1 | 50 min/hr | 0.83 | -3 | 1.05 | 1.9884
CAT D10N | D10 Loose recontouring | 15 | 1700 | 1083.3834 |  | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 1 | 50 min/hr | 0.83 | 0 | 1 | 0.55867
CAT D10N | D10 Linear recontouring | 15 | 1700 | 812.5376 | 243.7613 | Average | 0.75 | Loose | 1.2 | 1 | 1 | 1 | 0.85313 | 0.75 | 50 min/hr | 0.83 | 0 | 1 | 0.74489
CAT D10N | D10 Berm building | 15 | 1700 | 280.4051 |  | Average | 0.75 | Rock | 0.8 | 1 | 1 | 1 | 0.80294 | 0.75 | 50 min/hr | 0.83 | 20 | 0.55 | 2.1585
Table 6
Excavator Production Rates
Excavator |  | Estimated Bucket Payload | Estimated Cycle Time | Assumed Travel Time | Max Production Rate | Efficiency | Actual Production Rate | Unit Cost
|  | m3 | sec | sec | m3/hr | % | m3/hr | $/m3
CAT 329 (30 ton) | Cat 329 loose loading | 1.5 | 17 |  | 315 | 80% | 252 | #N/A | [5 empty] | Base Cycle time | min | 0.55
CAT 329 (30 ton) | Cat 329 digging | 1.1 | 24 |  | 165 | 80% | 132 | #N/A | [5 empty] | Material Factor | min | 0.03
CAT 336 (40 ton) | Cat 235 loose loading | 1.9 | 20 |  | 342 | 80% | 273.6 | 1.0967 | [5 empty] | Pile | min | 0.02
CAT 336 (40 ton) | Cat 235 digging | 1.3 | 24 |  | 195 | 80% | 156 | 1.9234 | [5 empty] | Constant operation | min | -0.04
CAT 345 (45 ton) | Cat 345 loose loading | 2.9 | 24 |  | 435 | 80% | 348 | 1.0912 | [5 empty] | Fragile target | min | 0.04
CAT 345 (45 ton) | Cat 345 rock loading | 2.9 | 24 |  | 345 | 80% | 276 | 1.3759 | [5 empty] | Total | min | 0.6
CAT 345 (45 ton) | Cat 345 digging | 2.5 | 30 |  | 300 | 80% | 240 | 1.5823
[14 empty] | Job efficiency | min | 0.83333
[14 empty] | Final cycle time | min | 0.72
Vibrating Roller Rates
Excavator |  | Stated Prod | Avail | Speed | Thickness | Passes | Net Prod | Unit Cost | [5 empty] | Cycles per hour | # | 83.3333
|  | m3/hr | % | Factor | Factor | Factor | m3/hr | $/m3
CAT CP56 | Roller compacting | 299 | 92% | 0.625 | 1.9737 | 0.66667 | 226.2171 | 0.75989 | [5 empty] | Required bucket size | m3 | 4
[14 empty] | Matched Loader size | Cat | 980
|  |  | Material Factor | Pile Factor | Operation Factor | Target Factor
Loader | Activity | Base Cycle Time | Broken | Dozer Piled | Constant | Small | Cycle Time | Efficiency | Final Cycle Time | Cycles per Hour | Bucket Size | Bucket Fill Factor | Productivity
|  | min | min | min | min | min | min |  | min |  | m3 | Bucket Fill Factor | m3/hr
Cat 966 | Cat 966 Rock Loading | 0.55 | 0.04 | 0.01 | -0.02 | 0.04 | 0.62 | 0.83333 | 0.744 | 80.6452 | 3.4 | 0.85 | 233.0645
Cat 980 | Cat 980 Rock Loading | 0.55 | 0.04 | 0.01 | -0.02 | 0.04 | 0.62 | 0.83333 | 0.744 | 80.6452 | 4.4 | 0.85 | 301.6129
Cat 988 | Cat 988 Crushed Loading | 0.6 | 0.02 | 0.01 | 0 | 0.04 | 0.67 | 0.83333 | 0.804 | 74.6269 | 6.4 | 0.9 | 429.8507
Cat 988 | Cat 988 Soil/Gravel Loading | 0.6 | 0 | 0.01 | 0 | 0.04 | 0.65 | 0.83333 | 0.78 | 76.9231 | 6.4 | 0.9 | 443.0769
Cat 988 | Cat 988 Rock Loading | 0.6 | 0.04 | 0.01 | -0.02 | 0.04 | 0.67 | 0.83333 | 0.804 | 74.6269 | 6.4 | 0.85 | 405.9701
Cat 992 | Cat 992 Rock Loading | 0.65 | 0.04 | 0.01 | -0.02 | 0.04 | 0.72 | 0.83333 | 0.864 | 69.4444 | 10.7 | 0.85 | 631.5972
DOZER PRODUCTIVITY FROM CAT HANDBOOK - edition 48
Source: Caterpillar Performance Handbook Edition 40 | [8 empty] | Source: Caterpillar Performance Handbook Edition 40
EXCAVATOR PRODUCTIVITY FROM CAT HANDBOOK
Source: Caterpillar Performance Handbook Edition 40
LOADER PRODUCTIVITY FROM CAT HANDBOOK
GRADER PRODUCTIVITY FROM CAT HANDBOOK
Grader Size
| Grader Productivity - Heavy Shaping |  | 12 | 14 | 16
| Operating Speed | km/hr | 2 | 2 | 2
| Effective blade length | m | 3.17 | 3.7 | 4.22
| Width of overlap | m | 1.585 | 1.85 | 2.11
| Job efficiency | % | 0.4 | 0.4 | 0.4
| Productivity | m2/hr | 1268 | 1480 | 1688
Grader Size
| Grader Productivity - Road Maintenance |  | 12 | 14 | 16
| Operating Speed | km/hr | 5 | 5 | 5
| Effective blade length | m | 3.17 | 3.7 | 4.22
| Width of overlap | m | 0.7925 | 0.925 | 1.055
| Job efficiency | % | 0.7 | 0.7 | 0.7
| Productivity | m2/hr | 8321.25 | 9712.5 | 11077.5
Grader Size
| Grader Productivity - Ripping |  | 12 | 14 | 16
| Operating Speed | km/hr | 2.5 | 2.5 | 2.5
| Ripper Width | m | 2.3 | 2.3 | 2.3
| Width of overlap | m | 0 | 0 | 0
| Job efficiency | % | 0.5 | 0.5 | 0.5
| Productivity | m2/hr | 2875 | 2875 | 2875
| km/hr by road width (m) | 6 | 0.47917 | 0.47917 | 0.47917
| km/hr by road width (m) | 8 | 0.35938 | 0.35938 | 0.35938
| km/hr by road width (m) | 10 | 0.2875 | 0.2875 | 0.2875
| km/hr by road width (m) | 12 | 0.23958 | 0.23958 | 0.23958
| km/hr by road width (m) | 14 | 0.20536 | 0.20536 | 0.20536
| km/hr by road width (m) | 16 | 0.17969 | 0.17969 | 0.17969
| km/hr by road width (m) | 18 | 0.15972 | 0.15972 | 0.15972
| km/hr by road width (m) | 20 | 0.14375 | 0.14375 | 0.14375
| km/hr by road width (m) | 22 | 0.13068 | 0.13068 | 0.13068
| km/hr by road width (m) | 24 | 0.11979 | 0.11979 | 0.11979
| km/hr by road width (m) | 26 | 0.11058 | 0.11058 | 0.11058
| km/hr by road width (m) | 28 | 0.10268 | 0.10268 | 0.10268
| km/hr by road width (m) | 30 | 0.095833 | 0.095833 | 0.095833
Note on N53: Joel Ray: Changed from 0.8, no need to assume full time visibility issues

## LHD
Table 7
Load, Haul, Dump | [20 empty] | 5
Task Description | From | To | Loader | Truck | Loader Job Classification | Unit Transported Volume | Truck Position Time | Load Time | Haul Distance | Average Haul Speed | Dump Time | Haul Back Distance | Turn-a-round Time | Efficiency | Daily Work Duration | Loads per Day per Truck | Volume per Day per Truck | Productivity per Truck | Number of Trucks Required | Fleet Productivity | Truck Rate | Excavator Rate | Total Equipment Rate | Volume Cost
[6 empty] | m3/load |  | min | km | km/hr | min | km | min | Min/hour | hours | LPD | m3 | m3/hr |  | m3/hr | $/hr | $/hr | $/hr | $/m3
ROM Pad Cleanup | Ore Stockpile Pads | Class A SF | CAT 345 (45 ton) | 90 ton Rigid Haul Truck | Cat 345 loose loading | 64.1 | 0.25 | 11.0517 | 1.6 | 30 | 1 | 1.6 | 18.7017 | 50 | 12 | 32.0826 | 2056.4949 | 171.3746 | 3 | 348 | 500.1 | 379.75 | 1880.05 | 5.4024
Explosive Magazine Cleanup | Explosives plant | Class A SF | CAT 345 (45 ton) | 90 ton Rigid Haul Truck | Cat 345 loose loading | 64.1 | 0.25 | 11.0517 | 5.4 | 30 | 1 | 5.4 | 33.9017 | 50 | 12 | 17.6982 | 1134.4556 | 94.538 | 4 | 348 | 500.1 | 379.75 | 2380.15 | 6.8395
Mining Workshop Overburden | Overburden SP | Mining Workshop | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 3.4 | 30 | 1 | 3.4 | 23.5302 | 50 | 12 | 25.4991 | 1634.4947 | 136.2079 | 4 | 443.0769 | 500.1 | 398.55 | 2398.95 | 5.4143
Mining Workshop Topsoil | Workshop Topsoil SP | Mining Workshop | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 0.3 | 30 | 1 | 0.3 | 11.1302 | 50 | 12 | 53.9073 | 3455.4609 | 287.9551 | 2 | 443.0769 | 500.1 | 398.55 | 1398.75 | 3.1569
Mill Site Overburden | Overburden SP | Mill Site | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 3.9 | 30 | 1 | 3.9 | 25.7973 | 50 | 12 | 23.2583 | 1490.8542 | 124.2378 | 4 | 429.8507 | 500.1 | 398.55 | 2398.95 | 5.5809
Mill Site Topsoil | Mill Topsoil SP | Mill Site | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 0.3 | 30 | 1 | 0.3 | 11.1302 | 50 | 12 | 53.9073 | 3455.4609 | 287.9551 | 2 | 443.0769 | 500.1 | 398.55 | 1398.75 | 3.1569
Topsoil - General Areas | General Areas Topsoil SP | General Areas | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 0.3 | 30 | 1 | 0.3 | 11.1302 | 50 | 12 | 53.9073 | 3455.4609 | 287.9551 | 2 | 443.0769 | 500.1 | 398.55 | 1398.75 | 3.1569
Class A Glacial Till | Class A & B Cover Mat SP | Class A SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 0.7 | 30 | 1 | 0.7 | 12.9973 | 50 | 12 | 46.1635 | 2959.078 | 246.5898 | 2 | 429.8507 | 500.1 | 398.55 | 1398.75 | 3.254
Class A Liner Protection | Crush & Screen Plant | Class A SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 2.5 | 30 | 1 | 2.5 | 19.9302 | 50 | 12 | 30.1051 | 1929.734 | 160.8112 | 3 | 443.0769 | 500.1 | 398.55 | 1898.85 | 4.2856
Class A Frost Protect - Progressive | Pit | Class A SF |  | 140 ton Rigid Haul Truck | 400 ton Excavator | 84 | 0.25 | 5 | 0.7 | 30 | 1 | 0.7 | 9.05 | 50 | 12 | 66.2983 | 5569.0608 | 464.0884 | [5 empty] | 0.37 | Price difference between hauling to Class A and Class C
Class A Frost Protection - Closure - YG | Class A & B Cover Mat SP | Class A SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Rock Loading | 64.1 | 0.25 | 9.4736 | 0.7 | 30 | 1 | 0.7 | 13.5236 | 50 | 12 | 44.3669 | 2843.9167 | 236.9931 | 2 | 405.9701 | 500.1 | 398.55 | 1398.75 | 3.4455
Class A Frost Protection - Closure - BMC | Class A & B Cover Mat SP | Class A SF | CAT 992 | 140 ton Rigid Haul Truck | Cat 992 Rock Loading | 84 | 0.25 | 7.9798 | 0.7 | 30 | 1 | 0.7 | 12.0298 | 50 | 12 | 49.8763 | 4189.6066 | 349.1339 | 2 | 631.5972 | 575.3 | 398.55 | 1549.15 | 2.4527
Class A Overburden | Class A Overburden SP | Class A SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 0.7 | 30 | 1 | 0.7 | 12.9973 | 50 | 12 | 46.1635 | 2959.078 | 246.5898 | 2 | 429.8507 | 500.1 | 398.55 | 1398.75 | 3.254
Class A Topsoil | Class A Topsoil SP | Class A SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 0.7 | 30 | 1 | 0.7 | 12.7302 | 50 | 12 | 47.132 | 3021.1603 | 251.7634 | 2 | 443.0769 | 500.1 | 398.55 | 1398.75 | 3.1569
Class B Glacial Till | Class B Cover Mat SP | Class B SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 0.8 | 30 | 1 | 0.8 | 13.3973 | 50 | 12 | 44.7852 | 2870.7295 | 239.2275 | 2 | 429.8507 | 500.1 | 398.55 | 1398.75 | 3.254
Class B Liner Protection | Crush & Screen Plant | Class B SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 2.1 | 30 | 1 | 2.1 | 18.3302 | 50 | 12 | 32.7329 | 2098.1758 | 174.848 | 3 | 443.0769 | 500.1 | 398.55 | 1898.85 | 4.2856
Class B Frost Protect - Progressive | Pit | Class B SF |  | 140 ton Rigid Haul Truck | 400 ton Excavator | 84 | 0.25 | 5 | 0.7 | 30 | 1 | 0.7 | 9.05 | 50 | 12 | 66.2983 | 5569.0608 | 464.0884 | [5 empty] | 0 | Price difference between hauling to Class B and Class C
Class B Frost Protection - Closure - YG | Class A & B Cover Mat SP | Class B SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Rock Loading | 64.1 | 0.25 | 9.4736 | 0.8 | 30 | 1 | 0.8 | 13.9236 | 50 | 12 | 43.0923 | 2762.2161 | 230.1847 | 2 | 405.9701 | 500.1 | 398.55 | 1398.75 | 3.4455
Class B Frost Protection - Closure - BMC | Class A & B Cover Mat SP | Class B SF | CAT 992 | 140 ton Rigid Haul Truck | Cat 992 Rock Loading | 84 | 0.25 | 7.9798 | 0.8 | 30 | 1 | 0.8 | 12.4298 | 50 | 12 | 48.2712 | 4054.7817 | 337.8985 | 2 | 631.5972 | 575.3 | 398.55 | 1549.15 | 2.4527
Class B Overburden | Class B Overburden SP | Class B SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 0.8 | 30 | 1 | 0.8 | 13.3973 | 50 | 12 | 44.7852 | 2870.7295 | 239.2275 | 2 | 429.8507 | 500.1 | 398.55 | 1398.75 | 3.254
Class B Topsoil | Class B Topsoil SP | Class B SF | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 0.8 | 30 | 1 | 0.8 | 13.1302 | 50 | 12 | 45.6962 | 2929.1234 | 244.0936 | 2 | 443.0769 | 500.1 | 398.55 | 1398.75 | 3.1569
Class C Overburden | Overburden SP | Class C Storage | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Crushed Loading | 64.1 | 0.25 | 8.9473 | 3.2 | 30 | 1 | 3.2 | 22.9973 | 50 | 12 | 26.09 | 1672.3708 | 139.3642 | 4 | 429.8507 | 500.1 | 398.55 | 2398.95 | 5.5809
Class C Topsoil | Overburden SP | Class C Storage | CAT 988 | 90 ton Rigid Haul Truck | Cat 988 Soil/Gravel Loading | 64.1 | 0.25 | 8.6802 | 1.4 | 30 | 1 | 1.4 | 15.5302 | 50 | 12 | 38.6344 | 2476.4639 | 206.372 | 3 | 443.0769 | 500.1 | 398.55 | 1898.85 | 4.2856
0.15788
Load, Haul, Dump, Spread, Compact, etc
Task Description | From | To | Volume Cost
$/m3
ROM Pad Cleanup | Ore Stockpile Pads | Class A SF | 5.4024
Explosive Magazine Cleanup | Explosives plant | Class A SF | 6.8395
Mining Workshop Overburden | Overburden SP | Mining Workshop | 5.4143
Mining Workshop Topsoil | Workshop Topsoil SP | Mining Workshop | 3.1569
Mill Site Overburden | Overburden SP | Mill Site | 5.5809
Mill Site Topsoil | Mill Topsoil SP | Mill Site | 3.1569
Topsoil - General Areas | General Areas Topsoil SP | General Areas | 3.1569
Class A Glacial Till | Class A & B Cover Mat SP | Class A SF | 10.7263 | Zone S Material
Class A Liner Protection | Crush & Screen Plant | Class A SF | 13.639 | Zone F Material
Class A Frost Protect - Progressive | Pit | Class A SF | 1.4082
Class A Frost Protection - Closure - YG | Class A & B Cover Mat SP | Class A SF | 4.4836
Class A Frost Protection - Closure - BMC | Class A & B Cover Mat SP | Class A SF | 3.4909
Class A Overburden | Class A Overburden SP | Class A SF | 3.9054
Class A Topsoil | Class A Topsoil SP | Class A SF | 3.8083
Class B Glacial Till | Class B Cover Mat SP | Class B SF | 10.7263 | Zone S Material
Class B Liner Protection | Crush & Screen Plant | Class B SF | 13.639 | Zone F Material
Class B Frost Protect - Progressive | Pit | Class B SF | 1.0382
Class B Frost Protection - Closure - YG | Class A & B Cover Mat SP | Class B SF | 4.4836
Class B Frost Protection - Closure - BMC | Class A & B Cover Mat SP | Class B SF | 3.4909
Class B Overburden | Class B Overburden SP | Class B SF | 3.9054
Class B Topsoil | Class B Topsoil SP | Class B SF | 3.8083
Class C Overburden | Overburden SP | Class C Storage | 6.2323
Class C Topsoil | Overburden SP | Class C Storage | 4.937
Note on E46: George Smith: 1.9 density to convert $/t to $/m3
Note on E47: George Smith: 1.9 density to convert $/t to $/m3
Note on E53: George Smith: 1.9 density to convert $/t to $/m3
Note on E54: George Smith: 1.9 density to convert $/t to $/m3

## Labour & Equip Hrs
TOTAL LABOUR HOURS |  | Year 2 | Year 5 | EOM
Labour Classification |  | Hrs | Hrs | Hrs
Blaster |  | 0 | 60 | 60
General Labourer |  | 4699.1317 | 40135.959 | 55524.002
Trades Labourer |  | 194 | 3215 | 3215
Camp Labourer |  | 0 | 0 | 0
Site Caretaker |  | 0 | 0 | 0
Mechanic |  | 0 | 0 | 0
Environmental Monitor |  | 0 | 0 | 0
Site Supervisor |  | 0 | 0 | 0
Design Engineer |  | 0 | 0 | 0
Environmental Scientist |  | 20 | 190 | 190
Passive Treatment Manager |  | 0 | 0 | 0
Project Manager |  | 0 | 0 | 0
Total |  | 4913.1317 | 43600.959 | 58989.002
Estimated workforce |  | 4.2538 | 18.8749 | 17.0242
Years |  | 1 | 2 | 3
EQUIPMENT AND LABOUR HOURS (BUILD INTO MATERIAL MOVEMENT RATES) | [12 empty] | YEAR 2 | [6 empty] | YEAR 5 | [9 empty] | EOM/LOM
Material Load & Haul | m3 |  | Excavator | Loader | Truck | Dozer | Compact roller | Crush / Screen | Loading Style | Dozer Style | Crush / Screen Style | Roller Style | Excavator Hours | Loader Hours | Truck Hours | Dozer Hours | Roller Hours | Crush / Screen Hours | Total Labour Hours | Material Load & Haul | m3 |  | Excavator Hours | Loader Hours | Truck Hours | Dozer Hours | Roller Hours | Crush / Screen Hours | Total Labour Hours | Material Load & Haul | m3 | Excavator Hours | Loader Hours | Truck Hours | Dozer Hours | Roller Hours | Crush / Screen Hours | Total Labour Hours
ROM Pad Cleanup | 0 |  |  | 1 | 1 | 1 | 1 | 1 | Cat 345 loose loading | D9 Loose recontouring | Zone F - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 | 0 | 0 | ROM Pad Cleanup | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | ROM Pad Cleanup | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Explosive Magazine Cleanup | 50 |  |  | 1 | 1 | 1 | 1 |  | Cat 345 loose loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0.14368 | 0.52889 | 0.065382 | 0.22103 |  | 0.95897 | Explosive Magazine Cleanup | 7475 |  |  | 21.4799 | 79.0688 | 9.7745 | 33.0435 |  | 143.3667 | Explosive Magazine Cleanup | 7475 |  | 21.4799 | 79.0688 | 9.7745 | 33.0435 |  | 143.3667
Mining Workshop Overburden | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Mining Workshop Overburden | 33307.5 |  |  | 75.1732 | 244.5343 | 43.5539 | 147.2369 |  | 510.4983 | Mining Workshop Overburden | 33307.5 |  | 75.1732 | 244.5343 | 43.5539 | 147.2369 |  | 510.4983
Mining Workshop Topsoil | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Mining Workshop Topsoil | 9992.25 |  |  | 22.552 | 34.7007 | 13.0662 | 44.1711 |  | 114.4899 | Mining Workshop Topsoil | 9992.25 |  | 22.552 | 34.7007 | 13.0662 | 44.1711 |  | 114.4899
Mill Site Overburden | 60270 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 140.2115 | 485.1179 | 78.811 | 266.4255 |  | 970.5658 | Mill Site Overburden | 60270 |  |  | 140.2115 | 485.1179 | 78.811 | 266.4255 |  | 970.5658 | Mill Site Overburden | 60270 |  | 140.2115 | 485.1179 | 78.811 | 266.4255 |  | 970.5658
Mill Site Topsoil | 30135 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 68.013 | 104.6517 | 39.4055 | 133.2127 |  | 345.283 | Mill Site Topsoil | 30135 |  |  | 68.013 | 104.6517 | 39.4055 | 133.2127 |  | 345.283 | Mill Site Topsoil | 30135 |  | 68.013 | 104.6517 | 39.4055 | 133.2127 |  | 345.283
Topsoil - General Areas | 9105 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 20.5495 | 31.6195 | 11.906 | 40.2489 |  | 104.3239 | Topsoil - General Areas | 61470 |  |  | 138.7344 | 213.4708 | 80.3801 | 271.7301 |  | 704.3154 | Topsoil - General Areas | 61470 |  | 138.7344 | 213.4708 | 80.3801 | 271.7301 |  | 704.3154
Class A Glacial Till | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Glacial Till | 113950 |  |  | 265.092 | 462.1034 | 149.0046 | 503.7196 |  | 1379.9197 | Class A Glacial Till | 184800 |  | 429.9167 | 749.4226 | 241.6504 | 816.9144 |  | 2237.904
Class A Liner Protection | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Liner Protection | 113950 |  |  | 257.1788 | 708.5951 | 149.0046 | 503.7196 |  | 1618.4982 | Class A Liner Protection | 184800 |  | 417.0833 | 1149.1739 | 241.6504 | 816.9144 |  | 2624.822
Class A Frost Protect - Progressive | 0 |  |  | 1 | 1 | 1 | 1 |  | 400 ton Excavator | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  |  | 0 | 0 | 0 |  | 0 | Class A Frost Protect - Progressive | 0 |  |  |  | 0 | 0 | 0 |  | 0 | Class A Frost Protect - Progressive | 0 |  |  | 0 | 0 | 0 |  | 0
Class A Frost Protection - Closure - YG | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Rock Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Frost Protection - Closure - YG | 683700 |  |  | 1684.114 | 2884.8946 | 894.0279 | 3022.3179 |  | 8485.3544 | Class A Frost Protection - Closure - YG | 1108800 |  | 2731.2353 | 4678.6181 | 1449.9022 | 4901.4861 |  | 13761.2417
Class A Frost Protection - Closure - BMC | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 992 Rock Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Frost Protection - Closure - BMC | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | Class A Frost Protection - Closure - BMC | 0 |  | 0 | 0 | 0 | 0 |  | 0
Class A Overburden | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Overburden | 91200 |  |  | 212.1667 | 369.8449 | 119.256 | 403.1525 |  | 1104.4202 | Class A Overburden | 67785 |  | 157.6943 | 274.8897 | 88.6378 | 299.6458 |  | 820.8675
Class A Topsoil | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class A Topsoil | 91200 |  |  | 205.8333 | 362.2449 | 119.256 | 403.1525 |  | 1090.4868 | Class A Topsoil | 67785 |  | 152.987 | 269.2409 | 88.6378 | 299.6458 |  | 810.5115
Class B Glacial Till | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Glacial Till | 121200 |  |  | 281.9583 | 506.6308 | 158.485 | 535.7685 |  | 1482.8426 | Class B Glacial Till | 168275 |  | 391.4731 | 703.4101 | 220.0417 | 743.8651 |  | 2058.79
Class B Liner Protection | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Liner Protection | 121200 |  |  | 273.5417 | 693.1736 | 158.485 | 535.7685 |  | 1660.9687 | Class B Liner Protection | 168275 |  | 379.7873 | 962.4074 | 220.0417 | 743.8651 |  | 2306.1016
Class B Frost Protect - Progressive | 0 |  |  | 1 | 1 | 1 | 1 |  | 400 ton Excavator | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  |  | 0 | 0 | 0 |  | 0 | Class B Frost Protect - Progressive | 0 |  |  |  | 0 | 0 | 0 |  | 0 | Class B Frost Protect - Progressive | 0 |  |  | 0 | 0 | 0 |  | 0
Class B Frost Protection - Closure - YG | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Rock Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Frost Protection - Closure - YG | 727200 |  |  | 1791.2647 | 3159.2025 | 950.9099 | 3214.611 |  | 9115.9881 | Class B Frost Protection - Closure - YG | 1009650 |  | 2487.0055 | 4386.2608 | 1320.2505 | 4463.1903 |  | 12656.7071
Class B Frost Protection - Closure - BMC | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 992 Rock Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Frost Protection - Closure - BMC | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | Class B Frost Protection - Closure - BMC | 0 |  | 0 | 0 | 0 | 0 |  | 0
Class B Overburden | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Overburden | 77130 |  |  | 179.4344 | 322.4128 | 100.8576 | 340.9556 |  | 943.6605 | Class B Overburden | 79605 |  | 185.1922 | 332.7586 | 104.094 | 351.8965 |  | 973.9413
Class B Topsoil | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class B Topsoil | 77130 |  |  | 174.0781 | 315.9853 | 100.8576 | 340.9556 |  | 931.8767 | Class B Topsoil | 79605 |  | 179.6641 | 326.1249 | 104.094 | 351.8965 |  | 961.7794
Class C Overburden | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Crushed Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class C Overburden | 57870 |  |  | 134.6281 | 415.2428 | 75.6727 | 255.8162 |  | 881.3598 | Class C Overburden | 200040 |  | 465.3708 | 1435.3754 | 261.5787 | 884.2833 |  | 3046.6082
Class C Topsoil | 0 |  |  | 1 | 1 | 1 | 1 |  | Cat 988 Soil/Gravel Loading | D9 Loose recontouring | Zone S - Crush & Screen | Roller compacting |  | 0 | 0 | 0 | 0 |  | 0 | Class C Topsoil | 57870 |  |  | 130.6094 | 280.416 | 75.6727 | 255.8162 |  | 742.5142 | Class C Topsoil | 200040 |  | 451.4792 | 969.3176 | 261.5787 | 884.2833 |  | 2566.6587
0
Total | 99560 | [11 empty] | 0 | 228.9176 | 621.918 | 130.1878 | 440.1082 | 0 | 1421.1317 | Total | 2536249.75 |  | 0 | 6056.0634 | 11642.291 | 3316.4809 | 11211.5737 | 0 | 32226.409 | Total | 3722109.75 | 0 | 8895.0526 | 17398.5442 | 4867.1492 | 16453.706 | 0 | 47614.452
OTHER LABOUR HOURS |  | Year 2 | Year 5 | EOM
Labour Classification |  | Hrs | Hrs | Hrs
Blaster |  | 0 | 60 | 60
General Labourer |  | 3278 | 7909.55 | 7909.55
Trades Labourer |  | 194 | 3215 | 3215
Camp Labourer |  | 0 | 0 | 0
Site Caretaker |  | 0 | 0 | 0
Mechanic |  | 0 | 0 | 0
Environmental Monitor |  | 0 | 0 | 0
Site Supervisor |  | 0 | 0 | 0
Design Engineer |  | 0 | 0 | 0
Environmental Scientist |  | 20 | 190 | 190
Passive Treatment Manager |  | 0 | 0 | 0
Project Manager |  | 0 | 0 | 0
Total |  | 3492 | 11374.55 | 11374.55
OTHER EQUIPMENT HOURS |  | Year 2 | Year 5 | EOM | [15 empty] | TOTAL EQUIPMENT HOURS |  | Year 2 | Year 5 | EOM
Equipment Type |  | Hrs | Hrs | Hrs | [15 empty] | Equipment Type |  | Hrs | Hrs | Hrs
CAT 420F |  | 0 | 0 | 0 | [15 empty] | CAT 420F |  | 0 | 0 | 0
John Deere 410L |  | 0 | 0 | 0 | [15 empty] | John Deere 410L |  | 0 | 0 | 0
CAT CP56 |  | 0 | 0 | 0 | [15 empty] | CAT CP56 |  | 440.1082 | 11211.5737 | 16453.706
Walk-behind vibrating (30 in) |  | 0 | 0 | 0 | [15 empty] | Walk-behind vibrating (30 in) |  | 0 | 0 | 0
CAT D6D |  | 224.4976 | 3271.8318 | 439.165 | [15 empty] | CAT D6D |  | 224.4976 | 3271.8318 | 439.165
CAT D7 |  | 0 | 0 | 0 | [15 empty] | CAT D7 |  | 0 | 0 | 0
CAT D8R |  | 0 | 0 | 0 | [15 empty] | CAT D8R |  | 0 | 0 | 0
CAT D9N |  | 240.9104 | 895.1998 | 1345.5631 | [15 empty] | CAT D9N |  | 371.0982 | 4211.6807 | 6212.7123
CAT D10N |  | 0 | 0 | 0 | [15 empty] | CAT D10N |  | 0 | 0 | 0
Air Rotary, 200 cfm compressor |  | 0 | 0 | 0 | [15 empty] | Air Rotary, 200 cfm compressor |  | 0 | 0 | 0
Air track production drill rig (900cfm) |  | 0 | 0 | 0 | [15 empty] | Air track production drill rig (900cfm) |  | 0 | 0 | 0
CAT 325 (30 ton) |  | 0 | 0 | 0 | [15 empty] | CAT 325 (30 ton) |  | 0 | 0 | 0
CAT 336 (40 ton) |  | 270.756 | 5875.1 | 5901.984 | [15 empty] | CAT 336 (40 ton) |  | 270.756 | 5875.1 | 5901.984
CAT 336 w hammer |  | 0 | 340 | 340 | [15 empty] | CAT 336 w hammer |  | 0 | 340 | 340
CAT 345 (45 ton) |  | 0 | 62.5417 | 72.8333 | [15 empty] | CAT 345 (45 ton) |  | 0 | 62.5417 | 72.8333
CAT 16G grader |  | 0 | 0 | 0 | [15 empty] | CAT 16G grader |  | 0 | 0 | 0
CAT 140H |  | 7.796 | 10.235 | 12.679 | [15 empty] | CAT 140H |  | 7.796 | 10.235 | 12.679
30 ton Articulated Haul Truck |  | 0 | 0 | 0 | [15 empty] | 30 ton Articulated Haul Truck |  | 0 | 0 | 0
35 ton Articulated Haul Truck |  | 0 | 24.85 | 24.85 | [15 empty] | 35 ton Articulated Haul Truck |  | 0 | 24.85 | 24.85
40 ton Articulated Haul Truck |  | 35 | 1940 | 1940 | [15 empty] | 40 ton Articulated Haul Truck |  | 35 | 1940 | 1940
90 ton Rigid Haul Truck |  | 0 | 0 | 0 | [15 empty] | 90 ton Rigid Haul Truck |  | 621.918 | 11642.291 | 17398.5442
30 ton Crane |  | 17 | 2360 | 2360 | [15 empty] | 30 ton Crane |  | 17 | 2360 | 2360
CAT 950 |  | 0 | 0 | 0 | [15 empty] | CAT 950 |  | 0 | 0 | 0
CAT 966 |  | 0 | 0 | 0 | [15 empty] | CAT 966 |  | 0 | 0 | 0
CAT 980 |  | 0 | 0 | 0 | [15 empty] | CAT 980 |  | 0 | 0 | 0
CAT 988 |  | 0 | 0 | 0 | [15 empty] | CAT 988 |  | 228.9176 | 6056.0634 | 8895.0526
Tractor Trailer - 60 ton - lowbed |  | 72.5 | 129.5 | 129.5 | [15 empty] | Tractor Trailer - 60 ton - lowbed |  | 72.5 | 129.5 | 129.5
Hiab Flatdeck truck |  | 0 | 0 | 0 | [15 empty] | Hiab Flatdeck truck |  | 0 | 0 | 0
Water Truck (3,000 gal) |  | 0 | 0 | 0 | [15 empty] | Water Truck (3,000 gal) |  | 0 | 0 | 0
Water Truck (4,000 gal) |  | 0 | 0 | 0 | [15 empty] | Water Truck (4,000 gal) |  | 0 | 0 | 0
Water Truck (5,000 gal) |  | 0 | 0 | 0 | [15 empty] | Water Truck (5,000 gal) |  | 0 | 0 | 0
Concrete Transit Mix Truck |  | 0 | 0 | 0 | [15 empty] | Concrete Transit Mix Truck |  | 0 | 0 | 0
Fuel Truck |  | 0 | 0 | 0 | [15 empty] | Fuel Truck |  | 0 | 0 | 0
Highway, Line Truck, with Aerial Platform |  | 0 | 0 | 0 | [15 empty] | Highway, Line Truck, with Aerial Platform |  | 0 | 0 | 0
Pickup Truck (short term) |  | 0 | 0 | 0 | [15 empty] | Pickup Truck (short term) |  | 0 | 0 | 0
Pickup Truck (long term) |  | 0 | 0 | 0 | [15 empty] | Pickup Truck (long term) |  | 0 | 0 | 0
Pilot Vehicle |  | 0 | 0 | 0 | [15 empty] | Pilot Vehicle |  | 0 | 0 | 0
Total |  | 868.4599 | 14909.2583 | 12566.5745 | [15 empty] | Total |  | 2289.5916 | 47135.6673 | 60181.0265
Note on U21: Joel Ray: 2 Operators
Note on AH21: Joel Ray: 2 Operators
Note on AT21: Joel Ray: 2 Operators

## T2 - Unit Rates
Table 2
Summary Unit Rates and Costs
EQUIPMENT
Category | Type | Item | Unit | Yukon 3rd Party Rate (Wet) - 2026 | Yukon 3rd Party Mob/Demob Rate | BC 25/26 Blue Book Rate AF (All Found/Wet) | BC 25/26 Blue Book Rate LO (Less Operator) | BC 25/26 Blue Book Rate Mob-Demob (LO + TT) | Owner Rate (Wet) | Capacity | Comment |  | -100%
Backhoes
| Backhoes | CAT 420F | $/hr |  |  | 150.95 | 87.7 | 310.3 | 113.2125 |  |  |  | -100%
|  | John Deere 410L | $/hr |  |  | 150.45 | 87.2 | 309.8 | 112.8375
Compactors
| Compactors | CAT CP56 | $/hr |  |  | 171.9 | 108.65 | 331.25 | 168.9
|  | Walk-behind vibrating (30 in) | $/hr |  |  | 17.05 | 17.05 | 239.65 | 17.05
Dozers
| Dozers | CAT D6D | $/hr |  |  | 287.6 | 224.35 | 446.95 | 185.8
|  | CAT D7 | $/hr |  |  | 367.55 | 304.3 | 526.9 | 214.7
|  | CAT D8R | $/hr |  |  | 367.55 | 304.3 | 526.9 | 246.1 |  |  |  | -100%
|  | CAT D9N | $/hr |  |  | 498.15 | 434.9 | 657.5 | 259.8 |  |  |  | -100%
|  | CAT D10N | $/hr |  |  | 605.25 | 542 | 764.6 | 314.1 |  |  |  | -100%
Drills
| Drills | Air Rotary, 200 cfm compressor | $/hr |  |  | 526.85 | 400.35 | 622.95 | 395.1375
|  | Air track production drill rig (900cfm) | $/hr |  |  | 415.55 | 289.05 | 511.65 | 311.6625
Excavators
| Excavators | CAT 325 (30 ton) | $/hr |  |  | 249.45 | 186.2 | 408.8 | 187.0875 |  |  |  | -100%
|  | CAT 336 (40 ton) | $/hr |  |  | 300.05 | 236.8 | 459.4 | 225.0375 |  |  |  | -100%
|  | CAT 336 w hammer | $/hr |  |  | 466.6 | 403.35 | 625.95 | 349.95 |  |  |  | -100%
|  | CAT 345 (45 ton) | $/hr |  |  | 379.75 | 316.5 | 539.1 | 284.8125 |  |  |  | -100%
Graders
| Graders | CAT 16G grader | $/hr |  |  | 307.7 | 244.45 | 467.05 | 236.3 |  |  |  | -100%
|  | CAT 140H | $/hr |  |  | 220 | 156.75 | 379.35 | 198.3 |  |  |  | -100%
Haul Trucks
| Haul Trucks | 30 ton Articulated Haul Truck | $/hr |  |  | 266.75 | 203.5 | 426.1 | 200.0625 | 18 | Capacity in m3 |  | -100%
|  | 35 ton Articulated Haul Truck | $/hr |  |  | 329.7 | 266.45 | 489.05 | 247.275 | 21 | Capacity in m3 |  | -100%
|  | 40 ton Articulated Haul Truck | $/hr |  |  | 337.7 | 274.45 | 497.05 | 234.7 | 24 | Capacity in m3 |  | -100%
|  | 90 ton Rigid Haul Truck | $/hr |  |  | 500.1 | 436.85 | 659.45 | 310.3 | 64.1 | Capacity in m3
|  | 140 ton Rigid Haul Truck | $/hr |  |  | 575.3 | 512.05 | 734.65 | 503.7 | 84 | Capacity in m3
Lifting
| Lifting | 30 ton Crane | $/hr |  |  | 255.4 | 192.15 | 414.75 | 191.55 |  |  |  | -100%
Loaders
| Loaders | CAT 950 | $/hr |  |  | 228.15 | 164.9 | 387.5 | 171.1125 |  |  |  | -100%
|  | CAT 966 | $/hr |  |  | 274.7 | 211.45 | 434.05 | 175.3 |  |  |  | -100%
|  | CAT 980 | $/hr |  |  | 332.8 | 269.55 | 492.15 | 198.8 |  |  |  | -100%
|  | CAT 988 | $/hr |  |  | 398.55 | 335.3 | 557.9 | 321.7
|  | CAT 992 | $/hr |  |  | 398.55 | 335.3 | 557.9 | 466.2
Support Vehicles
| Support Vehicles | Tractor Trailer - 60 ton - lowbed | $/hr |  |  | 222.6 | 159.35 | 381.95 | 166.95
|  | Hiab Flatdeck truck | $/hr |  |  | 183.6 | 120.35 | 342.95 | 137.7
|  | Water Truck (3,000 gal) | $/hr |  |  | 142.9 | 79.65 | 302.25 | 107.175
|  | Water Truck (4,000 gal) | $/hr |  |  | 163 | 99.75 | 322.35 | 122.25
|  | Water Truck (5,000 gal) | $/hr |  |  | 176.05 | 112.8 | 335.4 | 132.0375
|  | Concrete Transit Mix Truck | $/hr |  |  | 148.85 | 85.6 | 308.2 | 111.6375
|  | Fuel Truck | $/hr |  |  | 176.05 | 112.8 | 335.4 | 132.0375
|  | Highway, Line Truck, with Aerial Platform | $/hr |  |  |  |  | 222.6
|  | Pickup Truck (short term) | $/month |  |  | 3854.4 | 3854.4 | 4077 | 0
|  | Pickup Truck (long term) | $/month |  |  | 3854.4 | 3854.4 | 4077 | 0
|  | Pilot Vehicle | $/hr |  |  | 91.35 | 28.1 | 250.7 | 91.35
PERSONNEL
Personnel | Rate Used in Estimate ($/hr) | Base Wage ($/hr) | Loading Rate (%) | Rotation | Weeks per Year | Days per Week | Hours Per Day | Total Hours Annually | Ave Hours / Month | Total Annual Salary | Monthly Rate ($/mo) | Source
Blaster | 57.75 | 38.5 | 150% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 151767 | 12647.25 | YG-FWS April 1, 2026, Category B
General Labourer | 46.5 | 31 | 150% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 122202 | 10183.5 | YG-FWS April 1, 2026, Category D
Trades Labourer | 64.425 | 42.95 | 150% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 169308.9 | 14109.075 | YG-FWS April 1, 2026, Category A
Camp Labourer | 46.5 | 31 | 150% | 2 in -2 out | 26.0714 | 7 | 12 | 2190 | 182.5 | 101835 | 8486.25 | YG-FWS April 1, 2026, Category D
Site Caretaker | 51.24 | 34.16 | 150% | 2 in -2 out | 26.0714 | 7 | 12 | 2190 | 182.5 | 112215.6 | 9351.3 | YG-FWS April 1, 2026, Category C
Mechanic | 64.425 | 42.95 | 150% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 169308.9 | 14109.075 | YG-FWS April 1, 2026, Category A
Environmental Monitor | 57.75 | 38.5 | 150% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 151767 | 12647.25 | YG-FWS April 1, 2026, Category B
Site Supervisor | 198 | 198 | 100% | 2 in -2 out | 26.0714 | 7 | 12 | 2190 | 182.5 | 433620 | 36135 | 2026 rates from engineering provider to BMC for supervisor
Design Engineer | 131 | 131 | 100% | 2 in -2 out | 26.0714 | 7 | 12 | 2190 | 182.5 | 286890 | 23907.5 | 2026 rates from engineering provider to BMC for intermediate engineer
Environmental Scientist | 220 | 220 | 100% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 578160 | 48180 | Assumed
Passive Treatment Manager | 275 | 275 | 100% | 3 in -2 out | 31.2857 | 7 | 12 | 2628 | 219 | 722700 | 60225 | Assumed
Project Manager | 246 | 246 | 100% | 2 in -2 out | 26.0714 | 7 | 12 | 2190 | 182.5 | 538740 | 44895 | 2026 rates from engineering provider to BMC for project manager
MATERIAL
| Type | Item | Unit | Unit Rate (C$) | Unit Rate (US$)
| Crush & Screen | Zone F - Crush & Screen | per t | 4.58 |  | 2026 Equipment and Labour Estimate
|  | Zone S - Crush & Screen | per t | 3.19 |  | 2026 Equipment and Labour Estimate
| Revegetation | Revegetation Seed Mix | per kg | 38.095 |  | 2026 Quote, plus freight allowance
|  | Revegetation Seed Mix - 50kg/ha | per ha | 1904.75
|  | Fertilizer | per kg | 2.26 |  | 2026 Quote, plus freight allowance
|  | Fertilizer - 250kg/ha | per ha | 565
|  | Tree Seedlings (1,000 seedlings per ha) | per ha | 3390 |  | 2026 Quote, average of three seedling species, plus planting cost
|  | Seed/Fertilizer Application | per ha | 2100 |  | 2026 Quote
|  | Erosion Barrier | per sq.m | 3 |  | Allowance
|  | Revegetation incl Application | per ha | 4569.75
| Liners | Geotextile | per sq.m | 4 |  | Allowance
|  | Geomembrane - HDPE | per sq.m | 13 |  | 2026 Quote
| Pit Lake Treatment | Ferric Sulphate 60%, 1,350 kg Tote | per kg |  | 1.38 | 2026 Quote, includes US$0.50/kg freight to site
|  | Glycerine 80%, 22MT bulk tanker | per kg |  | 1.3 | 2026 Quote
|  | Ferric distribution system | lump sum | 60000 |  | Allowance
|  | Glycerine distribution system | lump sum | 250000 |  | Allowance
POST CLOSURE MONTHLY COSTS
Category | RCP Ref Section |  | Unit | Unit Rate (C$)
Physical/Geotech Stability Monitoring | 7.11.1 |  | monitoring period | 20069 |  | 2026 Estimate
Surface Water Monitoring | 7.11.2 |  | monitoring period | 17008 |  | 2026 Estimate
Groundwater Monitoring | 7.11.2 |  | monitoring period | 78761 |  | 2026 Estimate
Revegetation Success | 7.11.3 |  | monitoring period | 54889 |  | 2026 Estimate
Soil and Vegetation Chemistry | 7.11.3 |  | monitoring period | 86663 |  | 2026 Estimate
Wildlife Aerial Surveys | 7.11.3 |  | monitoring period | 157466 |  | 2026 Estimate
Aquatics | 7.11.4 |  | monitoring period | 103824 |  | 2026 Estimate
Effluent | 7.11.4 |  | monitoring period | 21455 |  | 2026 Estimate
MISCELLANEOUS
|  | Contractor Unit Rates & Camp Costs | Unit | Unit Rate
|  | Camp Cost | $/manday | 108 |  | 2026 Quote, 26-50 personnel
|  | Power and Heat | $/month | 5500 |  | Allowance
|  | Employee Transport Costs | $/month | 5000 |  | Allowance
|  | General Admin Expenses | $/month | 2000 |  | Allowance
|  | Sundry equipment maintenance | $/yr | 5000 |  | Allowance
|  | Water Treatment Plant | $/m3 | 2.09 |  | 2026 Estimate, plant averaging 60% capacity throughput
|  | Cut and Fold Liner | $/m2 | 0.2325 |  | Allowance
|  | Silt curtains | $/m2 | 3 |  | Allowance
|  | Enviro matting | $/m2 | 3 |  | Allowance
|  | Annual Road Maintenance | $/yr | 10560 |  | Allowance
|  | Financial | Unit | Value
|  | USD:CAD Exchange Rate | - | 0.8 |  | Assumption
Data is no longer publicly available.
Will add if YG provides.

## T3 - G&A
| Table 3 |  |  | 5 |  |  |  | Active Closure Years | 1 |  | 2 |  | 3
| General and Administration Costs | [6 empty] | Transitional Closure Years | 4 |  | 8 |  | 12
[6 empty] | Current |  | Year 2 |  | Year 5 |  | EOM |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment / Labour | Unit Rates | Units | Quantity | Total | Quantity | Total | Quantity | Total | Quantity | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Onsite Management
Project Management and Engineering - Included in indirect cost percentage
Pickup truck
| Pickup truck (2 trucks) Active Closure |  | Pickup Truck (short term) | 3854.4 | monthly |  | 0 | 24 | 92505.6 | 48 | 185011.2 | 72 | 277516.8
| Pickup truck (1 truck) Transitional Closure |  | Pickup Truck (short term) | 3854.4 | monthly |  | 0 | 16 | 61670.4 | 32 | 123340.8 | 48 | 185011.2
Camp and General
| Sundry equipment maintenance |  | Sundry equipment maintenance | 5000 | annually |  | 0 | 5 | 25000 | 10 | 50000 | 15 | 75000
| Power and heat (5 months per year) |  | Power and Heat | 5500 | monthly |  | 0 | 25 | 137500 | 50 | 275000 | 75 | 412500
| General Administrative expenses (5 months per year, 3 years) |  | General Admin Expenses | 2000 | monthly |  | 0 | 25 | 50000 | 50 | 100000 | 75 | 150000
| Camp Costs (Active Closure period) |  | Camp Cost | 108 | man-day |  | 0 | 3650 | 394200 | 7300 | 788400 | 10950 | 1182600
| Camp Costs (Transitional Closure period) |  | Camp Cost | 108 | man-day |  | 0 | 1825 | 197100 | 3650 | 394200 | 5475 | 591300
| Sub-Total | [5 empty] | 0 |  | 760876 |  | 1521752 |  | 2282628
Transport Costs
| Employee transport costs (Active Closure period) |  | Employee Transport Costs | 5000 | monthly |  | 0 | 12 | 60000 | 24 | 120000 | 36 | 180000
| Employee transport costs (Transitional Closure period) |  | Employee Transport Costs | 5000 | monthly |  | 0 | 16 | 80000 | 32 | 160000 | 48 | 240000
| Road Maintenance |  | Annual Road Maintenance | 10560 | annually |  | 0 | 5 | 52800 | 10 | 105600 | 15 | 158400
| Sub-Total | [5 empty] | 0 |  | 192800 |  | 385600 |  | 578400
Health and Safety
| Site Specific Health and Safety Plan |  | Unit Cost Basis | 5000 | LS |  | 0 | 1 | 5000 | 1 | 5000 | 1 | 5000
| Worker Orientation |  | Unit Cost Basis | 70 | each |  | 0 | 30 | 2100 | 60 | 4200 | 90 | 6300
| First Aid Supplies |  | Unit Cost Basis | 5000 | annually |  | 0 | 5 | 25000 | 10 | 50000 | 15 | 75000
| Sub-Total | [5 empty] | 0 |  | 32100 |  | 59200 |  | 86300
Total Estimated Cost for General & Administration During Closure | [6 empty] | 0 |  | 985776 |  | 1966552 |  | 2947328 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Notes:
Note on K4: George Smith: 1 year active closure
Note on M4: George Smith: 2 years active closure
Note on O4: George Smith: 3 years active closure
Note on C8: Joel Ray: Covered in ICMM & PCMM
Note on C9: George Smith: Assume Year 2 scenario 1 year active closure Year 5 scenario 2 years active closure EOM 3 years active closure
Note on C10: George Smith: Assume Year 2 scenario 5 years transition closure Year 5 scenario 10 years transition closure EOM 15 years transition closure One month per quarter monitoring during transitional closure
Note on C16: George Smith: 10 personnel for active closure
Note on C17: George Smith: 5 people for transitional closure, one month per quarter
Note on C20: Joel Ray: Covered in PCMM & NPV calcs
Note on C27: George Smith: Allow one induction per year per person

## T4 - Exploration
Table 4
Exploration Disturbances
[5 empty] | Current |  | Year 2 |  | Year 5 |  | EOM
Item No. | Work Item Description | Equipment / Labour | Unit Rates | Units | Quantity | Total | Quantity | Total | Quantity | Total | Quantity | Total
Roads and Trails
Re-grading
Revegetation
Sub-Total
Drill Hole Abandonment
| Capping | unit cost basis | 100000 | LS | 1 | 100000 | 1 | 100000 | 1 | 100000 | 1 | 100000
Roads
Clearing
| Sub-Total |  |  |  |  | 100000 |  | 100000 |  | 100000 |  | 100000
Total Estimated Cost in Reclaiming Exploration Disturbances | [5 empty] | 100000 |  | 100000 |  | 100000 |  | 100000
Note:

## T5 - ClosurePlan
Table 5
Closure Planning
[5 empty] | Current |  | Year 2 |  | Year 5 |  | EOM
Item No. | Work Item Description | Equipment / Labour | Unit Rates | Units | Quantity | Total | Quantity | Total | Quantity | Total | Quantity | Total
Technical Studies and Investigations
| Reclamation Research |  | 2000000 | ls |  | 0 |  | 100000 | 0.5 | 1000000 | 1 | 2000000
| AMPs |  | 200000 | ls |  | 0 |  | 50000 | 0.5 | 100000 | 1 | 200000
| Materials testing |  | 40000 | ls |  | 0 |  | 10000 | 0.5 | 20000 | 1 | 40000
| Sub-total |  |  |  |  | 0 |  | 160000 |  | 1120000 |  | 2240000
Engineering Designs for Civil Structures
Included in Indirect Costs
Sub-total
Permitting
Included in Indirect Costs
Sub-total
Other
Sub-total
Total Estimated Cost for Closure Planning | [5 empty] | 0 |  | 160000 |  | 1120000 |  | 2240000
Note:

## T6 - Pits
Table 6
| Mine Workings Open Pits & Underground | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM | EOM | EOM | EOM | EOM | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Code Ref | Work Item Description | Code | Equipment/Labour | Equipment Job Class | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
General
| Removal of mobile equipment |  | allowance |  |  |  | 5000 | ea |  |  |  | LS | 0 |  |  | 0 | LS | 0 |  |  | 1 | LS | 5000 |  |  | 1 | LS | 5000
| Removal of fixed equipment |  | allowance |  |  |  | 5000 | ea |  |  |  | LS | 0 |  |  | 0 | LS | 0 |  |  | 1 | LS | 5000 |  |  | 1 | LS | 5000
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 10000 |  |  |  |  | 10000
Equipment Decontamination
| Cleaning of Salvaged Equipment | 1 | General Labourer |  |  |  | 46.5 | $/hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 20 | hr | 930 |  |  | 20 | hr | 930 | General Labourer | 0 |  |  |  |  | General Labourer | 20 |  |  |  |  | General Labourer | 20
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 930 |  |  |  |  | 930
Removal of Assets to Off-Site
| Removal of Assets to Off-Site |  | allowance |  |  |  | 10000 | ea |  |  |  | ls | 0 |  |  | 0 | ls | 0 |  |  | 1 | ls | 10000 |  |  | 1 | ls | 10000
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 10000 |  |  |  |  | 10000
Access Control
Perimeter Safety Berms/Trenches
|  | 2 | CAT 345 (45 ton) | Cat 345 digging | 240 | m3/hr | 379.75 | hr |  | m3 | 0 | hr | 0 | 0 | m3 | 0 | hr | 0 | 15010 | m3 | 62.5417 | hr | 23750.1979 | 17480 | m3 | 72.8333 | hr | 27658.4583 |  |  | CAT 345 (45 ton) | 0 |  |  |  |  | CAT 345 (45 ton) | 62.5417 |  |  |  |  | CAT 345 (45 ton) | 72.8333
|  | 2 | CAT D9N | D9 Berm building | 197.933 | m3/hr | 498.15 | hr |  | m3 | 0 | hr | 0 | 0 | m3 | 0 | hr | 0 | 15010 | m3 | 75.8337 | hr | 37776.5728 | 17480 | m3 | 88.3127 | hr | 43992.9709 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 75.8337 |  |  |  |  | CAT D9N | 88.3127
| Block Roads | [5 empty] | 2000 | ea |  |  |  | ls | 0 |  |  | 0 | ls | 0 |  |  | 1 | ls | 2000 |  |  | 1 | ls | 2000
| Signage | [5 empty] | 250 | ea |  |  | 0 |  | 0 |  |  | 0 | ls | 0 |  |  | 6 | ls | 1500 |  |  | 6 | ls | 1500
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 65026.7707 |  |  |  |  | 75151.4292
Geotechnical Control
| Pit Wall Stabilization |  | allowance |  |  |  | 10000 | ea |  |  |  | ls | 0 |  |  | 0 | ls | 0 |  |  | 1 | ls | 10000 |  |  | 1 | ls | 10000
| Unloading Pit Crest |  | allowance |  |  |  | 10000 | ea |  |  |  | ls | 0 |  |  | 0 | ls | 0 |  |  | 1 | ls | 10000 |  |  | 1 | ls | 10000
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 20000 |  |  |  |  | 20000
Filling of Pit
Insitu Pit Lake Treatment
| Ferric Sulphate reagent | [5 empty] | 1.725 | kg |  | kg | 0 | kg | 0 |  | kg | 0 | kg | 0 | 4473 | kg | 4473 | kg | 7715.925 | 31500 | kg | 31500 | kg | 54337.5
| Glycerine Reagent | [5 empty] | 1.625 | kg |  | kg | 0 | kg | 0 |  | kg | 0 | kg | 0 | 335475 | kg | 335475 | kg | 545146.875 | 2362500 | kg | 2362500 | kg | 3839062.5
| Distribution Systems | [5 empty] | 310000 | LS |  |  | 0 | LS |  |  |  | 0 | LS |  |  |  | 1 | LS | 310000 |  |  | 1 | LS | 310000
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 862862.8 |  |  |  |  | 4203400
Revegetation
NA
Sealing/Backfilling of openings to surface
| Sealing of openings to surface |  | allowance |  |  |  | 10000 | ea |  |  | 0 | ls | 0 |  |  | 0 | ls | 0 |  |  | 0 | ls | 0 |  |  | 2 | ls | 20000
| Sub-totals | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 20000
Total Estimated Cost in Reclaiming Open Pits | [12 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 968819.5707 |  |  |  |  | 4339481.4292 |  | 0 |  | 0 |  | 0 |  | 158.3754 |  | 138.3754 |  | 0 |  | 181.146 |  | 161.146 |  | 0

## T7 - WSF
[47 empty] | 5 | Equipment Costing
| Table 7 | [45 empty] | 6 | LOM or EOM
| Waste Rock and Tailings Storage Facilities | [5 empty] | 5 | [39 empty] | 1 | YG or Contract Rates
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM | EOM | EOM | EOM | EOM | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour | Equipment Job Class | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Dump Physical Stabilization - Class A Storage Facility incl. collection pond
Equipment
| Crest - Regrading | 2 | CAT D9N | D9 Rock recontouring | 479.8376 | Lm3/hr | 498.15 | hr | 0 | m3 |  | hr | 0 | 0 | m3 | 0 | hr | 0 | 36230 | m3 | 75.5047 | hr | 37612.6688 | 36960 | m3 | 77.0261 | hr | 38370.5283 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | m3 |  |  |  |  | CAT D9N | 77.0261
| Resloping/Grading Collection Pond | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr | 0 | m3 | 0 | hr | 0 | 0 | m3 |  | hr | 0 | 24690 | m3 | 32.2854 | hr | 16082.9869 | 24690 | m3 | 32.2854 | hr | 16082.9869 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | m3 |  |  |  |  | CAT D9N | 32.2854
Load, Haul, Dump, Spread, Compact, etc
| Class A SF - Cover Liner Protection | 3 | Zone F Material | Class A Liner Protection |  |  | 13.639 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 113950 | m3 | 1554163.5662 |  |  | 184800 | m3 | 2520486.4154 |  |  |  |  | Class A Liner Protection | 0 |  |  |  |  | Class A Liner Protection | 113950 |  |  |  |  | Class A Liner Protection | 184800
| Class A SF - Cover Glacial Till | 3 | Zone S Material | Class A Glacial Till |  |  | 10.7263 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 113950 | m3 | 1222264.4763 |  |  | 184800 | m3 | 1982224.4425 |  |  |  |  | Class A Glacial Till | 0 |  |  |  |  | Class A Glacial Till | 113950 |  |  |  |  | Class A Glacial Till | 184800
| Class A SF - Frost Protection Layer | 3 | Class C Material | Class A Frost Protection - Closure - YG |  |  | 4.4836 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 683700 | m3 | 3065446.8995 |  |  | 1108800 | m3 | 4971431.2157 |  |  |  |  | Class A Frost Protection - Closure - YG | 0 |  |  |  |  | Class A Frost Protection - Closure - YG | 683700 |  |  |  |  | Class A Frost Protection - Closure - YG | 1108800
| Class A SF - Growth Media - Overburden | 3 | Overburden | Class A Overburden |  |  | 3.9054 | per m3 |  |  | 0 | m3 | 0 |  |  | 0 | m3 | 0 |  |  | 91200 | m3 | 356175.5128 |  |  | 67785 | m3 | 264729.7931 |  |  |  |  | Class A Overburden | 0 |  |  |  |  | Class A Overburden | 91200 |  |  |  |  | Class A Overburden | 67785
| Class A SF - Growth Media - Topsoil | 3 | Topsoil | Class A Topsoil |  |  | 3.8083 | per m3 |  |  |  | m3 | 0 |  | m3 | 0 | m3 | 0 |  | m3 | 91200 | m3 | 347316.7628 |  |  | 67785 | m3 | 258145.4689 |  |  |  |  | Class A Topsoil | 0 |  |  |  |  | Class A Topsoil | 91200 |  |  |  |  | Class A Topsoil | 67785
Materials
| Class A SF - Cover HDPE Geomembrane |  |  | Geomembrane - HDPE |  |  | 13 | per m2 |  |  | 0 | m2 | 0 |  |  |  | m2 | 0 |  |  | 227900 | m2 | 2962700 |  |  | 235200 | m2 | 3057600
| Class A SF - Revegetation Area |  |  | Revegetation incl Application |  |  | 4569.75 | per ha | 0 | m2 |  | ha | 0 | 0 | m2 | 0 | ha | 0 | 608000 | m2 | 60.8 | ha | 277840.8 | 451900 | m2 | 45.19 | ha | 206507.0025
Labour
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 9839603.6733 |  |  |  |  | 13315577.8533
Dump Physical Stabilization - Class B Storage Facility incl. collection pond and ore stockpile area
Equipment
| Crest - Regrading | 2 | CAT D9N | D9 Rock recontouring | 479.8376 | Lm3/hr | 498.15 | hr | 0 | m3 |  | hr | 0 | 0 | m3 |  | hr | 0 | 43651.5 | m3 | 90.9714 | hr | 45317.4003 | 53066.5 | m3 | 110.5926 | hr | 55091.711 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | m3 |  |  |  |  | CAT D9N | 110.5926
| Resloping/Grading Collection Pond | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr |  | m3 | 0 | hr | 0 | 0 | m3 |  | hr | 0 | 12720 | m3 | 16.6331 | hr | 8285.7672 | 12720 | m3 | 16.6331 | hr | 8285.7672 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | m3 |  |  |  |  | CAT D9N | 16.6331
Load, Haul, Dump, Spread, Compact, etc
| Class B SF - Cover Liner Protection | 3 | Zone F Material | Class B Liner Protection |  |  | 13.639 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 121200 | m3 | 1653046.2854 |  |  | 168275 | m3 | 2295102.0106 |  |  |  |  | Class B Liner Protection | 0 |  |  |  |  | Class B Liner Protection | 121200 |  |  |  |  | Class B Liner Protection | 168275
| Class B SF - Cover Glacial Till | 3 | Zone S Material | Class B Glacial Till |  |  | 10.7263 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 121200 | m3 | 1300030.3162 |  |  | 168275 | m3 | 1804971.9592 |  |  |  |  | Class B Glacial Till | 0 |  |  |  |  | Class B Glacial Till | 121200 |  |  |  |  | Class B Glacial Till | 168275
| Class B SF - Frost Protection Layer | 3 | Class C Material (Mine Fleet) | Class B Frost Protection - Closure - YG |  |  | 4.4836 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 727200 | m3 | 3260484.109 |  |  | 1009650 | m3 | 4526880.8864 |  |  |  |  | Class B Frost Protection - Closure - YG | 0 |  |  |  |  | Class B Frost Protection - Closure - YG | 727200 |  |  |  |  | Class B Frost Protection - Closure - YG | 1009650
| Class B SF - Growth Media - Overburden | 3 | Overburden | Class B Overburden |  |  | 3.9054 | per m3 |  |  | 0 | m3 | 0 |  |  | 0 | m3 | 0 |  |  | 77130 | m3 | 301226.0669 |  |  | 79605 | m3 | 310892.0142 |  |  |  |  | Class B Overburden | 0 |  |  |  |  | Class B Overburden | 77130 |  |  |  |  | Class B Overburden | 79605
| Class B SF - Growth Media - Topsoil | 3 | Topsoil | Class B Topsoil |  |  | 3.8083 | per m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 77130 | m3 | 293734.0122 |  |  | 79605 | m3 | 303159.5494 |  |  |  |  | Class B Topsoil | 0 |  |  |  |  | Class B Topsoil | 77130 |  |  |  |  | Class B Topsoil | 79605
Materials
| Class B SF - Cover HDPE Geomembrane |  |  | Geomembrane - HDPE |  |  | 13 | per m2 |  |  | 0 | m2 | 0 |  |  |  | m2 | 0 |  |  | 242400 | m2 | 3151200 |  |  | 336550 | m2 | 4375150
| Class B SF - Revegetation Area |  |  | Revegetation incl Application |  |  | 4569.75 | per ha | 0 | m2 |  | ha | 0 | 0 | m2 |  | ha | 0 | 514200 | m2 | 51.42 | ha | 234976.545 | 530700 | m2 | 53.07 | ha | 242516.6325
Labour
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 10248300.5023 |  |  |  |  | 13922050.5306
Dump Physical Stabilization - Class C Storage Facility incl. collection pond
Equipment
| Crest - Regrading | 2 | CAT D9N | D9 Rock recontouring | 479.8376 | Lm3/hr | 498.15 | hr | 0 | m3 |  | hr | 0 | 0 | m3 |  | hr | 0 | 38580 | m3 | 80.4022 | hr | 40052.3534 | 130030 | m3 | 270.9875 | hr | 134992.4186 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 80.4022 |  |  |  |  | CAT D9N | 270.9875
| Resloping/Grading Collection Pond | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr |  | m3 | 0 | hr | 0 | 0 | m3 |  | hr | 0 | 9990 | m3 | 13.0632 | hr | 6507.454 | 9990 | m3 | 13.0632 | hr | 6507.454 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 13.0632 |  |  |  |  | CAT D9N | 13.0632
Load, Haul, Dump, Spread, Compact, etc
| Class C SF - Growth Media - Overburden | 3 | Overburden | Class C Overburden |  |  | 6.2323 | per m3 |  |  | 0 | m3 | 0 |  |  | 0 | m3 | 0 |  |  | 57870 | m3 | 360662.4731 |  |  | 200040 | m3 | 1246706.7757 |  |  |  |  | Class C Overburden | 0 |  |  |  |  | Class C Overburden | 57870 |  |  |  |  | Class C Overburden | 200040
| Class C SF - Growth Media - Topsoil | 3 | Topsoil | Class C Topsoil |  |  | 4.937 | per m3 |  |  | 0 | m3 | 0 |  |  | 0 | m3 | 0 |  |  | 57870 | m3 | 285703.9443 |  |  | 200040 | m3 | 987596.6307 |  |  |  |  | Class C Topsoil | 0 |  |  |  |  | Class C Topsoil | 57870 |  |  |  |  | Class C Topsoil | 200040
Materials
| Class C SF - Revegetation Area |  | Revegetation including application costs | Revegetation incl Application |  |  | 4569.75 | per ha | 0 | m2 |  | ha | 0 | 0 | m2 |  | ha | 0 | 385800 | m2 | 38.58 | ha | 176300.955 | 1300300 | m2 | 130.03 | ha | 594204.5925
Labour
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 869227.1797 |  |  |  |  | 2970007.8715
Overburden Stockpile Area incl. collection pond
Equipment
| Resloping/Grading | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr | 0 | m3 |  | hr | 0 | 7890 | m3 | 10.3172 | hr | 5139.5207 | 32540 | m3 | 42.5503 | hr | 21196.4517 | 47470 | m3 | 62.0733 | hr | 30921.8059 |  |  | CAT D9N | 10.3172 |  |  |  |  | CAT D9N | 42.5503 |  |  |  |  | CAT D9N | 62.0733
| Resloping/Grading Collection Pond | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr |  | m3 | 0 | hr | 0 | 6940 | m3 | 9.075 | hr | 4520.6938 | 10410 | m3 | 13.6124 | hr | 6781.0406 | 10410 | m3 | 13.6124 | hr | 6781.0406 |  |  | CAT D9N | 9.075 |  |  |  |  | CAT D9N | 13.6124 |  |  |  |  | CAT D9N | 13.6124
Load, Haul, Dump
| Revegetation |  |  | Revegetation incl Application |  |  | 4569.75 | per ha | 0 | m2 |  | ha | 0 | 113600 | m2 | 11.36 | ha | 51912.36 | 360100 | m2 | 36.01 | ha | 164556.6975 | 509400 | m2 | 50.94 | ha | 232783.065
Materials
Labour
| Sub-Total | [11 empty] | 0 |  |  |  |  | 61572.5745 |  |  |  |  | 192534.1899 |  |  |  |  | 270485.9116
Topsoil Stockpile area
Equipment
| Resloping/Grading | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr | 0 | m3 |  | hr | 0 | 4220 | m3 | 5.5182 | hr | 2748.8945 | 22730 | m3 | 29.7225 | hr | 14806.2492 | 16030 | m3 | 20.9613 | hr | 10441.8906 |  |  | CAT D9N | 5.5182 |  |  |  |  | CAT D9N | 29.7225 |  |  |  |  | CAT D9N | 20.9613
Load, Haul, Dump, Spread, Compact, etc
| Revegetation |  | Revegetation including application costs | Revegetation incl Application |  |  | 4569.75 | per ha | 0 | m2 |  | ha | 0 | 42200 | m2 | 4.22 | ha | 19284.345 | 227300 | m2 | 22.73 | ha | 103870.4175 | 160300 | m2 | 16.03 | ha | 73253.0925
Materials
Labour
| Sub-Total | [11 empty] | 0 |  |  |  |  | 22033.2395 |  |  |  |  | 118676.6667 |  |  |  |  | 83694.9831
Total Estimated Cost in Reclaiming Overburden and Waste Rock Dumps | [12 empty] | 0 |  |  |  |  | 83605.814 |  |  |  |  | 21268342.2118 |  |  |  |  | 30561817.15 |  | 24.9104 |  | 24.9104 |  | 0 |  | 179.3507 |  | 179.3507 |  | 2333600 |  | 617.235 |  | 617.235 |  | 3519460

## T8 - Facilities
Table 8
| Surface Facilities Mine and Process Plant Area | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM | EOM | EOM | EOM | EOM | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour | Equipment Job Class | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Ore Stockpiles - Included in Class B Storage Reclamation
Equipment
Labour
Load, Haul, Dump
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Hazardous Materials Cleanup, Removal and Disposal
Equipment
| Transport off site | 2 | Tractor Trailer - 60 ton - lowbed |  |  |  | 222.6 | hr |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | 42 | hr | 9349.2 |  |  | 42 | hr | 9349.2 |  |  | Tractor Trailer - 60 ton - lowbed | 0 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 42 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 42
Labour
| Transfer Hazardous Materials and cleanup storage tanks | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 108 | hr | 5022 |  |  | 108 | hr | 5022 | General Labourer | 0 |  |  |  |  | General Labourer | 108 |  |  |  |  | General Labourer | 108
Materials
| Hazardous Material Removal to Cerfied Facility |  | Misc. |  |  |  | 25000 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 1 | LS | 25000 |  |  | 1 | LS | 25000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 39371.2 |  |  |  |  | 39371.2
Mill Building Demolition
Equipment
| Remove salvageable equipment | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 450 | hr | 114930 |  |  | 450 | hr | 114930 |  |  | 30 ton Crane | 0 |  |  |  |  | 30 ton Crane | 450 |  |  |  |  | 30 ton Crane | 450
| Dismantle Building | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 3500 | hr | 1050175 |  |  | 3500 | hr | 1050175 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 3500 |  |  |  |  | CAT 336 (40 ton) | 3500
|  | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 1750 | hr | 446950 |  |  | 1750 | hr | 446950 |  |  | 30 ton Crane | 0 |  |  |  |  | 30 ton Crane | 1750 |  |  |  |  | 30 ton Crane | 1750
| Concrete Demolition | 2 | CAT 336 w hammer |  |  |  | 466.6 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 100 | hr | 46660 |  |  | 100 | hr | 46660 |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 100 |  |  |  |  | CAT 336 w hammer | 100
|  | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 75 | hr | 22503.75 |  |  | 75 | hr | 22503.75 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 75 |  |  |  |  | CAT 336 (40 ton) | 75
|  | 2 | CAT D9N |  |  |  | 498.15 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 75 | hr | 37361.25 |  |  | 75 | hr | 37361.25 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 75 |  |  |  |  | CAT D9N | 75
| Haul scrap to solid waste facility | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 1750 | hr | 525087.5 |  |  | 1750 | hr | 525087.5 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 1750 |  |  |  |  | CAT 336 (40 ton) | 1750
|  | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 1750 | hr | 590975 |  |  | 1750 | hr | 590975 |  |  | 40 ton Articulated Haul Truck | 0 |  |  |  |  | 40 ton Articulated Haul Truck | 1750 |  |  |  |  | 40 ton Articulated Haul Truck | 1750
Labour
| Remove salvageable equipment | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 550 | hr | 25575 |  |  | 550 | hr | 25575 | General Labourer | 0 |  |  |  |  | General Labourer | 550 |  |  |  |  | General Labourer | 550
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 600 | hr | 38655 |  |  | 600 | hr | 38655 | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 600 |  |  |  |  | Trades Labourer | 600
| Decontaminate Building-hosing and clean-up | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 160 | hr | 10308 |  |  | 160 | hr | 10308 | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 160 |  |  |  |  | Trades Labourer | 160
| Dismantle Building | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 1750 | hr | 81375 |  |  | 1750 | hr | 81375 | General Labourer | 0 |  |  |  |  | General Labourer | 1750 |  |  |  |  | General Labourer | 1750
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 1750 | hr | 112743.75 |  |  | 1750 | hr | 112743.75 | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 1750 |  |  |  |  | Trades Labourer | 1750
| Concrete Demolition | 1 | Blaster |  |  |  | 57.75 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 40 | hr | 2310 |  |  | 40 | hr | 2310 | Blaster | 0 |  |  |  |  | Blaster | 40 |  |  |  |  | Blaster | 40
Materials
| Misc. Supplies & Tools |  | Misc. |  |  |  | 20000 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 1 | LS | 20000 |  |  | 1 | LS | 20000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 3125609.25 |  |  |  |  | 3125609.25
Other Mill Area Building Demolition
Equipment
| Remove salvageable equipment | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 25 | hr | 6385 |  |  | 25 | hr | 6385 |  |  | 30 ton Crane | 0 |  |  |  |  | 30 ton Crane | 25 |  |  |  |  | 30 ton Crane | 25
| Dismantle Building | 2 | CAT 336 w hammer |  |  |  | 466.6 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 200 | hr | 93320 |  |  | 200 | hr | 93320 |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 200 |  |  |  |  | CAT 336 w hammer | 200
|  | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 100 | hr | 25540 |  |  | 100 | hr | 25540 |  |  | 30 ton Crane | 0 |  |  |  |  | 30 ton Crane | 100 |  |  |  |  | 30 ton Crane | 100
| Concrete Demolition | 2 | CAT 336 w hammer |  |  |  | 466.6 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 30 | hr | 13998 |  |  | 30 | hr | 13998 |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 30 |  |  |  |  | CAT 336 w hammer | 30
|  | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 20 | hr | 6001 |  |  | 20 | hr | 6001 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 20 |  |  |  |  | CAT 336 (40 ton) | 20
|  | 2 | CAT D9N |  |  |  | 498.15 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 22 | hr | 10959.3 |  |  | 22 | hr | 10959.3 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 22 |  |  |  |  | CAT D9N | 22
| Haul scrap to solid waste facility | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 100 | hr | 30005 |  |  | 100 | hr | 30005 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 100 |  |  |  |  | CAT 336 (40 ton) | 100
|  | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 100 | hr | 33770 |  |  | 100 | hr | 33770 |  |  | 40 ton Articulated Haul Truck | 0 |  |  |  |  | 40 ton Articulated Haul Truck | 100 |  |  |  |  | 40 ton Articulated Haul Truck | 100
Labour
| Remove salvageable equipment | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 275 | hr | 12787.5 |  |  | 275 | hr | 12787.5 | General Labourer | 0 |  |  |  |  | General Labourer | 275 |  |  |  |  | General Labourer | 275
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 275 | hr | 17716.875 |  |  | 275 | hr | 17716.875 | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 275 |  |  |  |  | Trades Labourer | 275
| Dismantle Building | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 180 | hr | 8370 |  |  | 180 | hr | 8370 | General Labourer | 0 |  |  |  |  | General Labourer | 180 |  |  |  |  | General Labourer | 180
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 90 | hr | 5798.25 |  |  | 90 | hr | 5798.25 | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 90 |  |  |  |  | Trades Labourer | 90
| Concrete Demolition | 1 | Blaster |  |  |  | 57.75 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 20 | hr | 1155 |  |  | 20 | hr | 1155 | Blaster | 0 |  |  |  |  | Blaster | 20 |  |  |  |  | Blaster | 20
Misc.
| Misc. Supplies & Tools |  | Misc. |  |  |  | 10000 | LS |  |  |  | LS | 0 |  |  | 0 | LS | 0 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000
| Salvage and remove powerline and poles |  | Misc. |  |  |  | 27500 | LS |  |  |  | LS | 0 |  |  | 0 | LS | 0 |  |  | 1 | LS | 27500 |  |  | 1 | LS | 27500
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 303305.925 |  |  |  |  | 303305.925
Fuel Storage Area
Equipment
| Remove bulk fuel storage and piping facilities | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  | 15 | hr | 3831 |  |  | 30 | hr | 7662 |  |  | 30 | hr | 7662 |  |  | 30 ton Crane | 15 |  |  |  |  | 30 ton Crane | 30 |  |  |  |  | 30 ton Crane | 30
|  |  | Support Equipment |  |  |  | 2500 | LS |  |  |  | LS | 0 |  |  | 1 | LS | 2500 |  |  | 1 | LS | 2500 |  |  | 1 | LS | 2500
|  | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 20 | hr | 6001 |  |  | 40 | hr | 12002 |  |  | 40 | hr | 12002 |  |  | CAT 336 (40 ton) | 20 |  |  |  |  | CAT 336 (40 ton) | 40 |  |  |  |  | CAT 336 (40 ton) | 40
|  | 2 | Tractor Trailer - 60 ton - lowbed |  |  |  | 222.6 | hr |  |  |  | hr | 0 |  |  | 15 | hr | 3339 |  |  | 30 | hr | 6678 |  |  | 30 | hr | 6678 |  |  | Tractor Trailer - 60 ton - lowbed | 15 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 30 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 30
| Fold and Bury Liner | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 10 | hr | 3000.5 |  |  | 20 | hr | 6001 |  |  | 20 | hr | 6001 |  |  | CAT 336 (40 ton) | 10 |  |  |  |  | CAT 336 (40 ton) | 20 |  |  |  |  | CAT 336 (40 ton) | 20
| Re-contour area and slopes to bury footings and establish drainage | 2 | CAT D9N |  |  |  | 498.15 | hr |  |  |  | hr | 0 |  |  | 15 | hr | 7472.25 |  |  | 30 | hr | 14944.5 |  |  | 30 | hr | 14944.5 |  |  | CAT D9N | 15 |  |  |  |  | CAT D9N | 30 |  |  |  |  | CAT D9N | 30
Labour
| Cleanout tanks-remove sludge, pressure wash | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 30 | hr | 1395 |  |  | 60 | hr | 2790 |  |  | 60 | hr | 2790 | General Labourer | 30 |  |  |  |  | General Labourer | 60 |  |  |  |  | General Labourer | 60
| Remove bulk fuel storage and piping facilities | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 50 | hr | 2325 |  |  | 100 | hr | 4650 |  |  | 100 | hr | 4650 | General Labourer | 50 |  |  |  |  | General Labourer | 100 |  |  |  |  | General Labourer | 100
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 60 | hr | 3865.5 |  |  | 120 | hr | 7731 |  |  | 120 | hr | 7731 | Trades Labourer | 60 |  |  |  |  | Trades Labourer | 120 |  |  |  |  | Trades Labourer | 120
| Test soils for contamination | 1 | Environmental Scientist |  |  |  | 220 | hr |  |  |  | hr | 0 |  |  | 20 | hr | 4400 |  |  | 35 | hr | 7700 |  |  | 35 | hr | 7700 | Environmental Scientist | 20 |  |  |  |  | Environmental Scientist | 35 |  |  |  |  | Environmental Scientist | 35
Load, Haul, Dump
| Closure Cover - Overburden for Revegetation | 3 | Overburden | Mining Workshop Overburden |  |  | 5.4143 | m3 | 0 | m2 |  | m3 | 0 | 0 | m2 | 0 | m3 | 0 | 66615 | m2 | 33307.5 | m3 | 180336.6932 | 66615 | m2 | 33307.5 | m3 | 180336.6932 |  |  |  |  | Mining Workshop Overburden | 0 |  |  |  |  | Mining Workshop Overburden | 33307.5 |  |  |  |  | Mining Workshop Overburden | 33307.5
| Closure Cover - Topsoil for revegetation | 3 | Topsoil | Mining Workshop Topsoil |  |  | 3.1569 | m3 | 0 | m2 |  | m3 | 0 | 0 | m2 | 0 | m3 | 0 | 66615 | m2 | 9992.25 | m3 | 31544.5444 | 66615 | m2 | 9992.25 | m3 | 31544.5444 |  |  |  |  | Mining Workshop Topsoil | 0 |  |  |  |  | Mining Workshop Topsoil | 9992.25 |  |  |  |  | Mining Workshop Topsoil | 9992.25
Materials
| Revegetate area |  | Revegetation cost per ha. Including application cost | Revegetation incl Application |  |  | 4569.75 | ha | 0 | m2 |  | ha | 0 | 0 | m2 | 0 | ha | 0 | 66615 | m2 | 6.6615 | ha | 30441.3896 | 66615 | m2 | 6.6615 | ha | 30441.3896
Misc.
| Cleanout tanks-remove sludge, pressure wash |  | Removal to Licensed facility |  |  |  | 10000 | LS |  |  |  | LS | 0 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 48129.25 |  |  |  |  | 324981.1272 |  |  |  |  | 324981.1272
Land Reclamation - Entire Mill area
Equipment
| Haul any contaminated soils to Land Treatment Facility | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 5 | hr | 1500.25 |  |  | 20 | hr | 6001 |  |  | 20 | hr | 6001 |  |  | CAT 336 (40 ton) | 5 |  |  |  |  | CAT 336 (40 ton) | 20 |  |  |  |  | CAT 336 (40 ton) | 20
| Haul any contaminated soils to Land Treatment Facility | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  |  | hr | 0 |  |  | 5 | hr | 1688.5 |  |  | 20 | hr | 6754 |  |  | 20 | hr | 6754 |  |  | 40 ton Articulated Haul Truck | 5 |  |  |  |  | 40 ton Articulated Haul Truck | 20 |  |  |  |  | 40 ton Articulated Haul Truck | 20
| Re-contour area and slopes to bury footings and establish drainage | 2 | CAT D9N |  |  |  | 498.15 | hr |  |  |  | hr | 0 |  |  | 200 | hr | 99630 |  |  | 250 | hr | 124537.5 |  |  | 250 | hr | 124537.5 |  |  | CAT D9N | 200 |  |  |  |  | CAT D9N | 250 |  |  |  |  | CAT D9N | 250
Labour
| Test soils for contamination | 1 | Environmental Scientist |  |  |  | 220 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 35 | hr | 7700 |  |  | 35 | hr | 7700 | Environmental Scientist | 0 |  |  |  |  | Environmental Scientist | 35 |  |  |  |  | Environmental Scientist | 35
Load, Haul, Dump
| Closure Cover - Overburden | 3 | Overburden | Mill Site Overburden |  |  | 5.5809 | m3 | 0 | m2 |  | m3 | 0 | 200900 | m2 | 60270 | m3 | 336360.278 | 200900 | m2 | 60270 | m3 | 336360.278 | 200900 | m2 | 60270 | m3 | 336360.278 |  |  |  |  | Mill Site Overburden | 60270 |  |  |  |  | Mill Site Overburden | 60270 |  |  |  |  | Mill Site Overburden | 60270
| Closure Cover - Topsoil for revegetation | 3 | Topsoil | Mill Site Topsoil |  |  | 3.1569 | m3 | 0 | m2 |  | m3 | 0 | 200900 | m2 | 30135 | m3 | 95133.2129 | 200900 | m2 | 30135 | m3 | 95133.2129 | 200900 | m2 | 30135 | m3 | 95133.2129 |  |  |  |  | Mill Site Topsoil | 30135 |  |  |  |  | Mill Site Topsoil | 30135 |  |  |  |  | Mill Site Topsoil | 30135
Materials
| Test soils for contamination |  | Analytical Costs |  |  |  | 6000 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 1 | LS | 6000 |  |  | 1 | LS | 6000
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha | 0 | m2 |  | ha | 0 | 200900 | m2 | 20.09 | ha | 91806.2775 | 200900 | m2 | 20.09 | ha | 91806.2775 | 200900 | m2 | 20.09 | ha | 91806.2775
| Sub-Total | [11 empty] | 0 |  |  |  |  | 626118.5184 |  |  |  |  | 674292.2684 |  |  |  |  | 674292.2684
Mill Reagents
Equipment
| Load and return extra reagents/chemicals |  | Support Equipment |  |  |  | 2500 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 2 | LS | 5000 |  |  | 2 | LS | 5000
Labour
| Load and return extra reagents/chemicals | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  |  | hr | 0 |  |  | 100 | hr | 4650 |  |  | 100 | hr | 4650 | General Labourer | 0 |  |  |  |  | General Labourer | 100 |  |  |  |  | General Labourer | 100
Disposal
| Disposal Cost-bulk materials | [5 empty] | 5000 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 2 | LS | 10000 |  |  | 2 | LS | 10000
| Disposal Cost-lab pacs | [5 empty] | 2000 | pallets |  |  |  | pallets | 0 |  |  |  | pallets | 0 |  |  | 2 | pallets | 4000 |  |  | 2 | pallets | 4000
| Removal of drums, steel, oils, glycol & batteries | [5 empty] | 61080 | LS |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 2 | LS | 122160 |  |  | 2 | LS | 122160
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 145810 |  |  |  |  | 145810
Total Estimated Cost in Reclaiming Facilities | [12 empty] | 0 |  |  |  |  | 674247.7684 |  |  |  |  | 4613369.7706 |  |  |  |  | 4613369.7706
[30 empty] | 445 |  | 285 |  | 90405 |  | 16777 |  | 10529 |  | 133704.75 |  | 16777 |  | 10529 |  | 133704.75
Note on W74: Joel Ray: Based on area percentage of mill site
Note on AB74: Joel Ray: Based on area percentage of mill site
Note on P81: George Smith: Cover for temporary fuel storage costed in T10

## T9 - Ponds
Table 9
| Water Storage Ponds | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM | EOM | EOM | EOM | EOM | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour |  | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Upper Water Management Pond Reclamation
Equipment
| Breach Dam | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr | [8 empty] | hr | 0 | 86915 |  | 113.6528 | hr | 56616.1525 | 86915 | m3 | 113.6528 | hr | 56616.1525 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 113.6528 |  |  |  |  | CAT D9N | 113.6528
Labour
| Pump down impounded water, over spillway (using reclaim pumps) | 1 | General Labourer |  |  |  | 46.5 | hr | [8 empty] | hr | 0 |  |  | 96 | hr | 4464 |  |  | 96 | hr | 4464 | General Labourer | 0 |  |  |  |  | General Labourer | 96 |  |  |  |  | General Labourer | 96
| Environmental Scientist | 1 | Environmental Scientist |  |  |  | 220 | hr | [8 empty] | hr | 0 |  |  | 60 | hr | 13200 |  |  | 60 | hr | 13200 | Environmental Scientist | 0 |  |  |  |  | Environmental Scientist | 60 |  |  |  |  | Environmental Scientist | 60
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - topsoil for Revegetation | 3 | Load & Haul plus D9 Dozer | Topsoil - General Areas |  |  | 3.1569 | m3 |  |  | 0 | m3 | 0 |  |  |  | m3 | 0 |  |  | 19920 | m3 | 62885.4688 |  |  | 19920 | m3 | 62885.4688 |  |  |  |  | Topsoil - General Areas | 0 |  |  |  |  | Topsoil - General Areas | 19920 |  |  |  |  | Topsoil - General Areas | 19920
Misc.
| Misc. Supplies and Tools |  | Misc. |  |  |  | 8000 | LS | [8 empty] | LS | 0 |  |  | 1 | LS | 8000 |  |  | 1 | LS | 8000
| Engineering design for final structure include appropriate flow determination, channel designs, etc. | [5 empty] | 20000 | LS | [8 empty] | LS | 0 |  |  | 1 | LS | 20000 |  |  | 1 | LS | 20000
| Cut and fold liner and dispose |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 102858 | m2 | 28914.485 |  |  | 102858 | m2 | 28914.485
| Stabilize slopes with erosion barriers |  | Silt curtains |  |  |  | 3 | m2 | [8 empty] | m2 | 0 |  |  | 15000 | m2 | 45000 |  |  | 15000 | m2 | 45000
|  |  | Enviro matting |  |  |  | 3 | m2 | [8 empty] | m2 | 0 |  |  | 15000 | m2 | 45000 |  |  | 15000 | m2 | 45000
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha | 0 | m2 | 0 | ha | 0 | 0 | m2 |  | ha | 0 | 108100 | m2 | 10.81 | ha | 49398.9975 | 108100 | m2 | 10.81 | ha | 49398.9975
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 333479.1038 |  |  |  |  | 333479.1038
Lower Water Management Pond Reclamation
Equipment
| Breach Dam | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr | [8 empty] | hr | 0 | 102929 |  | 134.5932 | hr | 67047.6208 | 102929 | m3 | 134.5932 | hr | 67047.6208 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 134.5932 |  |  |  |  | CAT D9N | 134.5932
Labour
| Pump down impounded water, over spillway (using reclaim pumps) | 1 | General Labourer |  |  |  | 46.5 | hr | [8 empty] | hr | 0 |  |  | 96 | hr | 4464 |  |  | 96 | hr | 4464 | General Labourer | 0 |  |  |  |  | General Labourer | 96 |  |  |  |  | General Labourer | 96
| Environmental Scientist | 1 | Environmental Scientist |  |  |  | 220 | hr | [8 empty] | hr | 0 |  |  | 60 | hr | 13200 |  |  | 60 | hr | 13200 | Environmental Scientist | 0 |  |  |  |  | Environmental Scientist | 60 |  |  |  |  | Environmental Scientist | 60
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - topsoil for Revegetation | 3 | Load & Haul plus D9 Dozer spread | Topsoil - General Areas |  |  | 3.1569 | m3 |  |  | 0 | m3 |  |  |  |  | m3 | 0 |  |  | 22725 | m3 | 71740.5762 |  |  | 22725 | m3 | 71740.5762 |  |  |  |  | Topsoil - General Areas | 0 |  |  |  |  | Topsoil - General Areas | 22725 |  |  |  |  | Topsoil - General Areas | 22725
Misc.
| Misc. Supplies and Tools |  | Misc. |  |  |  | 8000 | LS | [8 empty] | LS | 0 |  |  | 1 | LS | 8000 |  |  | 1 | LS | 8000
| Engineering design for final structure include appropriate flow determination, channel designs, etc. | [5 empty] | 20000 | LS | [8 empty] | LS | 0 |  |  | 1 | LS | 20000 |  |  | 1 | LS | 20000
| Cut and fold liner and dispose |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 118856 | m2 | 32634.02 |  |  | 118856 | m2 | 32634.02
| Stabilize slopes with erosion barriers |  | Silt curtains |  |  |  | 3 | m2 | [8 empty] | m2 | 0 |  |  | 15000 | m2 | 45000 |  |  | 15000 | m2 | 45000
|  |  | Enviro matting |  |  |  | 3 | m2 | [8 empty] | m2 | 0 |  |  | 15000 | m2 | 45000 |  |  | 15000 | m2 | 45000
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 | 0 | ha | 0 | 0 | m2 |  | ha | 0 | 127100 | m2 | 12.71 | ha | 58081.5225 | 127100 | m2 | 12.71 | ha | 58081.5225
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 365167.7395 |  |  |  |  | 365167.7395
Pit Rim Pond Reclamation
Equipment
| Resloping/Grading | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr |  | m3 | 0 | hr | 0 | 0 | m3 |  | hr | 0 | 10530 | m3 | 13.7694 | hr | 6859.2083 | 10530 | m3 | 13.7694 | hr | 6859.2083 |  |  | CAT D9N | 0 |  |  |  |  | CAT D9N | 13.7694 |  |  |  |  | CAT D9N | 13.7694
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - Topsoil for Revegetation | 3 | Load & Haul plus D9 Dozer spread | Topsoil - General Areas |  |  | 3.1569 | m3 |  | m2 | 0 | m3 | 0 | 0 | m2 |  | m3 | 0 | 35100 | m2 | 5265 | m3 | 16621.084 | 35100 | m2 | 5265 | m3 | 16621.084 |  |  |  |  | Topsoil - General Areas | 0 |  |  |  |  | Topsoil - General Areas | 5265 |  |  |  |  | Topsoil - General Areas | 5265
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 | 0 | ha | 0 | 0 | m2 |  | ha | 0 | 35100 | m2 | 3.51 | ha | 16039.8225 | 35100 | m2 | 3.51 | ha | 16039.8225
Misc.
| Cut and fold liner and dispose |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 22000 | m2 | 10115 |  |  | 22000 | m2 | 10115
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 49635.1147 |  |  |  |  | 49635.1147
WRSF Collection Ponds
Misc.
| Cut and fold liner and dispose - Class A Pond |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 25000 | m2 | 10812.5 |  |  | 25000 | m2 | 10812.5
| Cut and fold liner and dispose - Class B Pond |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 17000 | m2 | 8952.5 |  |  | 17000 | m2 | 8952.5
| Cut and fold liner and dispose - Class C Pond |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 13000 | m2 | 8022.5 |  |  | 13000 | m2 | 8022.5
| Cut and fold liner and dispose - OB Pond |  | Cut and Fold Liner |  |  |  | 0.2325 | m2 |  |  |  | m2 |  |  |  |  | m2 | 0 |  |  | 9000 | m2 | 7092.5 |  |  | 9000 | m2 | 7092.5
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 34880 |  |  |  |  | 34880
Total Estimated Cost in Reclaiming Water Storage Ponds | [12 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 783161.958 |  |  |  |  | 783161.958 |  | 0 |  | 0 |  | 0 |  | 574.0154 |  | 262.0154 |  | 47910 |  | 574.0154 |  | 262.0154 |  | 47910
Note on U8: Joel Ray: Total Berm fill less sub-surface excavated material during construction
Note on Z8: Joel Ray: Total Berm fill less sub-surface excavated material during construction
Note on Y18: Joel Ray: $5,000 added for transport off site
Note on AD18: Joel Ray: $5,000 added for transport off site
Note on U22: Joel Ray: Used Basin footprint but not Berm to account for stream channel being left through the combined facility
Note on Z22: Joel Ray: Used Basin footprint but not Berm to account for stream channel being left through the combined facility
Note on U28: Joel Ray: Total Berm fill less sub-surface excavated material during construction
Note on Z28: Joel Ray: Total Berm fill less sub-surface excavated material during construction
Note on Y38: Joel Ray: $5,000 added for transport off site
Note on AD38: Joel Ray: $5,000 added for transport off site
Note on U42: Joel Ray: Used Basin footprint but not Berm to account for stream channel being left through the combined facility
Note on Z42: Joel Ray: Used Basin footprint but not Berm to account for stream channel being left through the combined facility
Note on Y53: Joel Ray: $5,000 added for transport off site
Note on AD53: Joel Ray: $5,000 added for transport off site
Note on C55: George Smith: Reclamation included in T7. Liner removal and disposal covered here.
Note on Y57: Joel Ray: $5,000 added for transport off site
Note on AD57: Joel Ray: $5,000 added for transport off site
Note on Y58: Joel Ray: $5,000 added for transport off site
Note on AD58: Joel Ray: $5,000 added for transport off site
Note on Y59: Joel Ray: $5,000 added for transport off site
Note on AD59: Joel Ray: $5,000 added for transport off site
Note on Y60: Joel Ray: $5,000 added for transport off site
Note on AD60: Joel Ray: $5,000 added for transport off site

## T10 - Infrastructure
Table 10
| Infrastructure | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM |  |  |  |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour |  | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Mine Camp and Related Infrastructure
Equipment
| Dismantle buildings | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  | 50 | hr | 15002.5 |  |  | 150 | hr | 45007.5 |  |  | 200 | hr | 60010 |  |  | 200 | hr | 60010 |  |  | CAT 336 (40 ton) | 150 |  |  |  |  | CAT 336 (40 ton) | 200 |  |  |  |  | CAT 336 (40 ton) | 200
| Haul scrap to Solid Waste Facility | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  | 20 | hr | 6754 |  |  | 30 | hr | 10131 |  |  | 40 | hr | 13508 |  |  | 40 | hr | 13508 |  |  | 40 ton Articulated Haul Truck | 30 |  |  |  |  | 40 ton Articulated Haul Truck | 40 |  |  |  |  | 40 ton Articulated Haul Truck | 40
| Demobilize buildings | 2 | Tractor Trailer - 60 ton - lowbed |  |  |  | 222.6 | hr | 19 |  | 17.5 | hr | 74014.5 | 57 | ea | 17.5 | hr | 222043.5 | 73 | ea | 17.5 | hr | 284371.5 | 73 | ea | 17.5 | hr | 284371.5 |  |  | Tractor Trailer - 60 ton - lowbed | 17.5 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 17.5 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 17.5
Labour
| Disconnect Services | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  | 75 | hr | 4831.875 |  |  | 110 | hr | 7086.75 |  |  | 150 | hr | 9663.75 |  |  | 150 | hr | 9663.75 | Trades Labourer | 110 |  |  |  |  | Trades Labourer | 150 |  |  |  |  | Trades Labourer | 150
| Remove salvageable equipment | 1 | General Labourer |  |  |  | 46.5 | hr |  |  | 600 | hr | 27900 |  |  | 950 | hr | 44175 |  |  | 1200 | hr | 55800 |  |  | 1200 | hr | 55800 | General Labourer | 950 |  |  |  |  | General Labourer | 1200 |  |  |  |  | General Labourer | 1200
| Dismantle buildings | 1 | General Labourer |  |  |  | 46.5 | hr |  |  | 500 | hr | 23250 |  |  | 1400 | hr | 65100 |  |  | 2000 | hr | 93000 |  |  | 2000 | hr | 93000 | General Labourer | 1400 |  |  |  |  | General Labourer | 2000 |  |  |  |  | General Labourer | 2000
| Site Clean-Up | 1 | General Labourer |  |  |  | 46.5 | hr |  |  | 500 | hr | 23250 |  |  | 800 | hr | 37200 |  |  | 1000 | hr | 46500 |  |  | 1000 | hr | 46500 | General Labourer | 800 |  |  |  |  | General Labourer | 1000 |  |  |  |  | General Labourer | 1000
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - Topsoil for Revegetation | 3 | Topsoil | Topsoil - General Areas |  |  | 3.1569 | m3 | 53800 | m2 | 8070 | m3 | 25476.1914 | 53800 | m2 | 8070 | m3 | 25476.1914 | 53800 | m2 | 8070 | m3 | 25476.1914 | 53800 | m2 | 8070 | m3 | 25476.1914 |  |  |  |  | Topsoil - General Areas | 8070 |  |  |  |  | Topsoil - General Areas | 8070 |  |  |  |  | Topsoil - General Areas | 8070
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha | 53800 | m2 | 5.38 | ha | 24585.255 | 53800 | m2 | 5.38 | ha | 24585.255 | 53800 | m2 | 5.38 | ha | 24585.255 | 53800 | m2 | 5.38 | ha | 24585.255
Misc
| Remove sewage system |  | Lump Sum |  |  |  | 5000 | ea |  |  | 1 | LS | 5000 |  |  | 1 | LS | 5000 |  |  | 1 | LS | 5000 |  |  | 1 | LS | 5000
| Sub-Total | [11 empty] | 230064.3214 |  |  |  |  | 485805.1964 |  |  |  |  | 617914.6964 |  |  |  |  | 617914.6964
Explosives Plant Site
Equipment
| Dismantle buildings | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 30 | hr | 9001.5 |  |  | 30 | hr | 9001.5 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 30 |  |  |  |  | CAT 336 (40 ton) | 30
| Crane services | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  | 2 | hr | 510.8 |  |  | 5 | hr | 1277 |  |  | 5 | hr | 1277 |  |  | 30 ton Crane | 2 |  |  |  |  | 30 ton Crane | 5 |  |  |  |  | 30 ton Crane | 5
| Haul scrap to Solid Waste Facility | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 30 | hr | 10131 |  |  | 30 | hr | 10131 |  |  | 40 ton Articulated Haul Truck | 0 |  |  |  |  | 40 ton Articulated Haul Truck | 30 |  |  |  |  | 40 ton Articulated Haul Truck | 30
|  | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 10 | hr | 3000.5 |  |  | 10 | hr | 3000.5 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 10 |  |  |  |  | CAT 336 (40 ton) | 10
| Concrete Demolition - Broken up and buried in place | 2 | CAT 336 w hammer |  |  |  | 466.6 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 10 | hr | 4666 |  |  | 10 | hr | 4666 |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 10 |  |  |  |  | CAT 336 w hammer | 10
Labour
| Remove salvageable equipment | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 16 | hr | 744 |  |  | 100 | hr | 4650 |  |  | 100 | hr | 4650 | General Labourer | 16 |  |  |  |  | General Labourer | 100 |  |  |  |  | General Labourer | 100
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 16 | hr | 1030.8 |  |  | 50 | hr | 3221.25 |  |  | 50 | hr | 3221.25 | Trades Labourer | 16 |  |  |  |  | Trades Labourer | 50 |  |  |  |  | Trades Labourer | 50
| Dismantle buildings | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 32 | hr | 1488 |  |  | 200 | hr | 9300 |  |  | 200 | hr | 9300 | General Labourer | 32 |  |  |  |  | General Labourer | 200 |  |  |  |  | General Labourer | 200
| Disconnect Services | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 8 | hr | 515.4 |  |  | 20 | hr | 1288.5 |  |  | 20 | hr | 1288.5 | Trades Labourer | 8 |  |  |  |  | Trades Labourer | 20 |  |  |  |  | Trades Labourer | 20
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - Topsoil for Revegetation | 3 | Topsoil | Topsoil - General Areas |  |  | 3.1569 | m3 |  | m2 |  | m3 | 0 | 200 | m2 | 30 | m3 | 94.707 | 29900 | m2 | 4485 | m3 | 14158.7012 | 29900 | m2 | 4485 | m3 | 14158.7012 |  |  |  |  | Topsoil - General Areas | 30 |  |  |  |  | Topsoil - General Areas | 4485 |  |  |  |  | Topsoil - General Areas | 4485
| Explosive Magazine Cleanup | 3 |  | Explosive Magazine Cleanup |  |  | 6.8395 | m3 |  | m2 |  | m3 | 0 | 200 | m2 | 50 | m3 | 341.9756 | 29900 | m2 | 7475 | m3 | 51125.3484 | 29900 | m2 | 7475 | m3 | 51125.3484 |  |  |  |  | Explosive Magazine Cleanup | 50 |  |  |  |  | Explosive Magazine Cleanup | 7475 |  |  |  |  | Explosive Magazine Cleanup | 7475
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 |  | ha | 0 | 200 | m2 | 0.02 | ha | 91.395 | 29900 | m2 | 2.99 | ha | 13663.5525 | 29900 | m2 | 2.99 | ha | 13663.5525
Misc
| Removal and destruction of explosives and blasting agents |  | Lump Sum |  |  |  | 5000 | ea |  |  |  | LS | 0 |  |  | 0 | LS | 0 |  |  | 0 | LS | 0 |  |  | 0 | LS | 0
| Sub-Total | [11 empty] | 0 |  |  |  |  | 4817.0776 |  |  |  |  | 125483.3521 |  |  |  |  | 125483.3521
Temporary Construction Areas (Offices, Crush and Screen)
Equipment
| Dismantle buildings | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 8 | hr | 2400.4 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | CAT 336 (40 ton) | 8 |  |  |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 0
| Crane services | 2 | 30 ton Crane |  |  |  | 255.4 | hr |  |  |  | hr | 0 |  |  | 4 | hr | 1021.6 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | 30 ton Crane | 4 |  |  |  |  | 30 ton Crane | 0 |  |  |  |  | 30 ton Crane | 0
| Haul scrap to Solid Waste Facility | 2 | 40 ton Articulated Haul Truck |  |  |  | 337.7 | hr |  |  |  | hr | 0 |  |  | 2 | hr | 675.4 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | 40 ton Articulated Haul Truck | 2 |  |  |  |  | 40 ton Articulated Haul Truck | 0 |  |  |  |  | 40 ton Articulated Haul Truck | 0
|  | 2 | CAT 336 (40 ton) |  |  |  | 300.05 | hr |  |  |  | hr | 0 |  |  | 2 | hr | 600.1 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | CAT 336 (40 ton) | 2 |  |  |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 0
| Concrete Demolition - Broken up and buried in place | 2 | CAT 336 w hammer |  |  |  | 466.6 | hr |  |  |  | hr | 0 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 0 |  |  |  |  | CAT 336 w hammer | 0
Labour
| Remove salvageable equipment | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 20 | hr | 930 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 | General Labourer | 20 |  |  |  |  | General Labourer | 0 |  |  |  |  | General Labourer | 0
|  | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 20 | hr | 1288.5 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 | Trades Labourer | 20 |  |  |  |  | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 0
| Dismantle buildings | 1 | General Labourer |  |  |  | 46.5 | hr |  |  |  | hr | 0 |  |  | 50 | hr | 2325 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 | General Labourer | 50 |  |  |  |  | General Labourer | 0 |  |  |  |  | General Labourer | 0
| Disconnect Services | 1 | Trades Labourer |  |  |  | 64.425 | hr |  |  |  | hr | 0 |  |  | 15 | hr | 966.375 |  |  | 0 | hr | 0 |  |  | 0 | hr | 0 | Trades Labourer | 15 |  |  |  |  | Trades Labourer | 0 |  |  |  |  | Trades Labourer | 0
Load, Haul, Dump, Spread, Compact, etc
| Closure Cover - Topsoil for Revegetation | 3 | Topsoil | Topsoil - General Areas |  |  | 3.1569 | m3 |  | m2 |  | m3 | 0 | 223500 | m2 | 33525 | m3 | 105835.1074 | 0 | m2 | 0 | m3 | 0 |  | m2 | 0 | m3 | 0 |  |  |  |  | Topsoil - General Areas | 33525 |  |  |  |  | Topsoil - General Areas | 0 |  |  |  |  | Topsoil - General Areas | 0
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 |  | ha | 0 | 223500 | m2 | 22.35 | ha | 102133.9125 | 0 | m2 | 0 | ha | 0 |  | m2 | 0 | ha | 0
Misc
| Sub-Total | [11 empty] | 0 |  |  |  |  | 218176.3949 |  |  |  |  | 0 |  |  |  |  | 0
Total Estimated Cost in Reclaiming Infrastructure | [12 empty] | 230064.3214 |  |  |  |  | 708798.6689 |  |  |  |  | 743398.0485 |  |  |  |  | 743398.0485 |  | 3531.5 |  | 199.5 |  | 8150 |  | 5062.5 |  | 342.5 |  | 20030 |  | 5062.5 |  | 342.5 |  | 20030
Note on C44: Joel Ray: Will be built into the contract to remove remaining materials

## T11 - Wastes
Table 11
| Waste Disposal / Remediation | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM |  |  |  |  | Year 2 | [5 empty] | EOM | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour |  | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Waste Management Facility
Equipment
| Remove recyclables and special waste materials | 2 | Tractor Trailer - 60 ton - lowbed |  |  |  | 222.6 | hr |  |  |  | hr | 0 |  |  | 40 | hr | 8904 |  |  | 40 | hr | 8904 |  |  | 40 | hr | 8904 |  |  | Tractor Trailer - 60 ton - lowbed | 40 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 40 |  |  |  |  | Tractor Trailer - 60 ton - lowbed | 40
| Recontour | 2 | CAT D9N | D9 Loose recontouring | 764.7412 | Lm3/hr | 498.15 | hr |  | m3 |  | hr | 0 | 670 | m3 | 1 | hr | 498.15 | 670 | m3 | 1 | hr | 498.15 | 670 | m3 | 1 | hr | 498.15 |  |  | CAT D9N | 1 |  |  |  |  | CAT D9N | 1 |  |  |  |  | CAT D9N | 1
Labour
Load, Haul, Dump
| Closure Cover - Topsoil for Revegetation | 3 | Topsoil | Topsoil - General Areas |  |  | 3.1569 | m3 |  | m2 |  | m3 | 0 | 6700 | m2 | 1005 | m3 | 3172.6855 | 6700 | m2 | 1005 | m3 | 3172.6855 | 6700 | m2 | 1005 | m3 | 3172.6855 |  |  |  |  | Topsoil - General Areas | 1005 |  |  |  |  | Topsoil - General Areas | 1005 |  |  |  |  | Topsoil - General Areas | 1005
Materials
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 |  | ha | 0 | 6700 | m2 | 0.67 | ha | 3061.7325 | 6700 | m2 | 0.67 | ha | 3061.7325 | 6700 | m2 | 0.67 | ha | 3061.7325
Misc
| Prepare detailed closure plan | [5 empty] | 2000 | ea |  |  |  | LS | 0 |  |  | 1 | LS | 2000 |  |  | 1 | LS | 2000 |  |  | 1 | LS | 2000
| Characterize final waste area | [5 empty] | 2000 | ea |  |  |  | LS | 0 |  |  | 1 | LS | 2000 |  |  | 1 | LS | 2000 |  |  | 1 | LS | 2000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 19636.568 |  |  |  |  | 19636.568 |  |  |  |  | 19636.568
Total Estimated Cost in Reclaiming Waste Facilities | [12 empty] | 0 |  |  |  |  | 19636.568 |  |  |  |  | 19636.568 |  |  |  |  | 19636.568 |  | 41 |  | 41 |  | 1005 |  | 41 |  | 41 |  | 1005 |  | 41 |  | 41 |  | 1005

## T12 - Roads
Table 12
| Roads and Trails | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM |  |  |  |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour |  | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Site Roads
Equipment
| Recontour | 2 | CAT 336 (40 ton) |  | 5.5 | hr/km | 300.05 | hr | 14.27 | km | 78.485 | hr | 23549.4243 | 15.592 | km | 85.756 | hr | 25731.0878 | 15.5 | km | 85.25 | hr | 25579.2625 | 20.388 | km | 112.134 | hr | 33645.8067 |  |  | CAT 336 (40 ton) | 85.756 |  |  |  |  | CAT 336 (40 ton) | 85.25 |  |  |  |  | CAT 336 (40 ton) | 112.134
| Scarify | 2 | CAT 140H |  | 2 | km/hr | 220 | hr | 14.27 | km | 7.135 | hr | 1569.7 | 15.592 | km | 7.796 | hr | 1715.12 | 15.5 | km | 7.75 | hr | 1705 | 20.388 | km | 10.194 | hr | 2242.68 |  |  | CAT 140H | 7.796 |  |  |  |  | CAT 140H | 7.75 |  |  |  |  | CAT 140H | 10.194
Labour
Load, Haul, Dump
| Revegetation |  |  | Revegetation incl Application |  |  | 4569.75 | per ha | 71350 | m2 | 7.135 | ha | 32605.1662 | 77960 | m2 | 7.796 | ha | 35625.771 | 77500 | m2 | 7.75 | ha | 35415.5625 | 101940 | m2 | 10.194 | ha | 46584.0315
Materials
| Erosion Barriers |  | Erosion Barrier |  |  |  | 3 | m2 | 14.27 | km | 7135 | m2 | 21405 | 15.592 | km | 7796 | m2 | 23388 | 15.5 | km | 7750 | m2 | 23250 | 20.388 | km | 10194 | m2 | 30582
| Sub-Total | [11 empty] | 79129.2905 |  |  |  |  | 86459.9788 |  |  |  |  | 85949.825 |  |  |  |  | 113054.5182
Total Estimated Cost in Reclaiming Roads and Trails | [12 empty] | 79129.2905 |  |  |  |  | 86459.9788 |  |  |  |  | 85949.825 |  |  |  |  | 113054.5182 |  | 93.552 |  | 93.552 |  | 0 |  | 93 |  | 93 |  | 0 |  | 122.328 |  | 122.328 |  | 0

## T13 - Water
Table 13
| Water Management | [5 empty] | 5
[9 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | Year 5 |  |  |  |  | EOM |  |  |  |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Code | Equipment/Labour |  | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Reclaim Site Diversions
Equipment
| Regrade site diversions | 2 | CAT D6D | D6 Linear recontouring | 75.2792 | m/hr | 287.6 | hr |  | m |  | m3 | 0 | 16900 | m | 224.4976 | hr | 64565.4964 | 21900 | m | 290.9169 | hr | 83667.7143 | 33060 | m | 439.165 | hr | 126303.8645 |  |  | CAT D6D | 224.4976 |  |  |  |  | CAT D6D | 290.9169 |  |  |  |  | CAT D6D | 439.165
Labour
Load, Haul, Dump
Misc
| Fault Creek Diversion | [5 empty] | 150000 | LS |  |  |  | LS | 0 |  |  | 1 | LS | 150000 |  |  | 1 | LS | 150000 |  |  | 1 | LS | 150000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 214565.4964 |  |  |  |  | 233667.7143 |  |  |  |  | 276303.8645
Finlayson Creek Pipeline Decommissioning
Equipment
| Load sections of pipe for disposal | 2 | CAT 336 (40 ton) |  | 200 | m/hr | 300.05 | hr | 0 | m | 0 | hr | 0 | 0 | m | 0 | hr | 0 | 4970 | m | 24.85 | hr | 7456.2425 | 4970 | m | 24.85 | hr | 7456.2425 |  |  | CAT 336 (40 ton) | 0 |  |  |  |  | CAT 336 (40 ton) | 24.85 |  |  |  |  | CAT 336 (40 ton) | 24.85
| Haul sections of pipe for disposal | 2 | 35 ton Articulated Haul Truck |  | 200 | m/hr | 329.7 | hr | 0 | m | 0 | hr | 0 | 0 | m | 0 | hr | 0 | 4970 | m | 24.85 | hr | 8193.045 | 4970 | m | 24.85 | hr | 8193.045 |  |  | 35 ton Articulated Haul Truck | 0 |  |  |  |  | 35 ton Articulated Haul Truck | 24.85 |  |  |  |  | 35 ton Articulated Haul Truck | 24.85
| Scarify pipe corridor and any associated maintenance road | 2 | CAT 140H |  | 2 | km/hr | 220 | hr | 0 | km | 0 | hr | 0 | 0 | km | 0 | hr | 0 | 4.97 | km | 2.485 | hr | 546.7 | 4.97 | km | 2.485 | hr | 546.7 |  |  | CAT 140H | 0 |  |  |  |  | CAT 140H | 2.485 |  |  |  |  | CAT 140H | 2.485
Labour
| Cut pipe into 10 m sections | 1 | General Labourer |  | 0.015 | hr/m | 46.5 | hr | 0 | m | 0 | hr | 0 | 0 | m | 0 | hr | 0 | 4970 | m | 74.55 | hr | 3466.575 | 4970 | m | 74.55 | hr | 3466.575 | General Labourer | 0 |  |  |  |  | General Labourer | 74.55 |  |  |  |  | General Labourer | 74.55
Load, Haul, Dump
Misc
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 19662.5625 |  |  |  |  | 19662.5625
Reclaim Dewatering Trenches
Equipment
| Regrade dewatering Trenches | 2 | CAT D6D | D6 Loose recontouring | 334.5743 | Lm3/hr | 287.6 | hr | 0 | m2 | 0 | m3 | 0 |  | m3 | 0 | hr | 0 | 4750 | m3 | 14.1971 | hr | 4083.0991 | 0 | m2 | 0 | hr | 0 |  |  | CAT D6D | 0 |  |  |  |  | CAT D6D | 14.1971 |  |  |  |  | CAT D6D | 0
| Backfill trenches | 2 | CAT D6D | D6 Rock pushing | 104.9645 | Lm3/hr | 287.6 | hr | 0 | m3 | 0 | m4 | 0 |  | m3 | 0 | hr | 0 | 311400 | m3 | 2966.7177 | hr | 853228.0204 | 0 | m3 | 0 | hr | 0 |  |  | CAT D6D | 0 |  |  |  |  | CAT D6D | 2966.7177 |  |  |  |  | CAT D6D | 0
Labour
Load, Haul, Dump
Misc
| Revegetate area |  |  | Revegetation incl Application |  |  | 4569.75 | ha |  | m2 |  | ha | 0 |  | m2 | 0 | ha | 0 | 47500 | m2 | 4.75 | ha | 21706.3125 | 0 | m2 | 0 | ha | 0
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 879017.432 |  |  |  |  | 0
Groundwater Well Decommissioning
Equipment
Labour
Load, Haul, Dump
Misc
| Production Wells |  | Lump Sum |  |  |  | 10000 | ea |  |  |  | LS | 0 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000
| De-watering Wells |  | Lump Sum |  |  |  | 10000 | ea |  |  |  | LS | 0 |  |  |  | LS | 0 |  |  | 1 | LS | 10000 |  |  | 1 | LS | 10000
| Sub-Total | [11 empty] | 0 |  |  |  |  | 10000 |  |  |  |  | 20000 |  |  |  |  | 20000
Site Effluents
Active Treatment
| Active Treatment Operating Costs (3 yr Active closure) |  | Water Treatment Plant |  |  |  | 2.09 | m3 | Variable | yr |  | m3 | 0 | Variable | yr |  | m3 | 0 | Variable | yr | 975036 | m3 | 2037825.24 | Variable | yr | 1462683 | m3 | 3057007.47
| Active Treatment Operating Costs (12 yr Transitional closure) |  | Water Treatment Plant |  |  |  | 2.09 | m3 | Variable | yr |  | m3 | 0 | Variable | yr |  | m3 | 0 | Variable | yr | 12073 | m3 | 25232.57 | Variable | yr | 12301 | m3 | 25709.09
Passive Treatment
| Passive Treatment Capital Costs | [5 empty] | 1200000 | ea |  |  |  | ea | 0 |  |  |  | ea | 0 |  |  | 1 | ea | 1200000 |  |  | 1 | ea | 1200000
| Passive Treatment Operating Costs |  | Included in PCMM NPV Calculations
| Sub-Total | [11 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 3263057.81 |  |  |  |  | 4282716.56
Total Estimated Cost for Water & Solutions Management | [12 empty] | 0 |  |  |  |  | 224565.4964 |  |  |  |  | 4415405.5187 |  |  |  |  | 4598682.987 |  | 224.4976 |  | 224.4976 |  | 0 |  | 3398.5668 |  | 3324.0168 |  | 0 |  | 565.9 |  | 491.35 |  | 0
Note on W53: George Smith: Assume 2 years Active Closure as reduced disturbance compared to LOM with 3 years Active Closure

## T16-Borrow (hidden)
Table 8
Quarries & Borrow Pits
[7 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | End Of Mine
Item No. | Work Item Description | Equipment/Labour | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total
Stabilize Slopes/Walls
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Remediation
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Access Control
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total Estimated Cost in Reclaiming Quarries & Borrow Pits | [10 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0

## T14 - MobDemob
| 7 | 5 | 1400
Table 14
Mobilization - Demobilization Costs
[6 empty] | ICMM at Year 2 |  | ICMM during operations |  | Year 2 |  | Year 5 and LOM
Equipment | Mob/Demob ($/hr) | 1-way Shipping Distance (km) | Average Speed (km/hr) | 1-way Travel Time (hr) | Total Cost Per Equip. | Qty Mob (Transitional Closure) | ICMM Mob costs | Qty Mob (Active Closure) | ICMM Mob costs | Qty Mob (Active Closure) | Active Closure Mob costs | Qty Mob (Active Closure) | Active Closure Mob costs | Qty Mob (Transitional Closure) | Transitional Closure Mob costs | Qty Mob (Post Closure) | Post Closure Mob-Demob costs | Comments | 1
Backhoe | [18 empty] | 2
CAT 420F | 310.3 | 1400 | 80 | 17.5 | 5430.25 | 1 | 5430.25 | 1 | 5430.25 | 1 | 5430.25 | 1 | 5430.25 | 1 | 5430.25 | 1 | 5430.25 |  | 3
John Deere 410L | 309.8 | 1400 | 80 | 17.5 | 5421.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4
5
Compactors | [18 empty] | 6
CAT CP56 | 331.25 | 1400 | 80 | 17.5 | 5796.875 |  | 0 |  | 0 | 0 | 0 | 1 | 5796.875 |  | 0 |  | 0 |  | 7
8
Dozers | [18 empty] | 9
CAT D6D | 446.95 | 1400 | 80 | 17.5 | 7821.625 |  | 0 | 1 | 7821.625 | 1 | 7821.625 | 1 | 7821.625 | 1 | 7821.625 | 1 | 7821.625 |  | 10
CAT D7 | 526.9 | 1400 | 80 | 17.5 | 9220.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10
CAT D8R | 526.9 | 1400 | 80 | 17.5 | 9220.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11
CAT D9N | 657.5 | 1400 | 80 | 17.5 | 11506.25 |  | 0 |  | 0 | 1 | 11506.25 | 1 | 11506.25 |  | 0 |  | 0 |  | 12
CAT D10N | 764.6 | 1400 | 80 | 17.5 | 13380.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13
14
Drills | [18 empty] | 15
Air Rotary, 200 cfm compressor | [18 empty] | 16
Air track production drill rig (900cfm) | [18 empty] | 17
18
Excavators | [18 empty] | 19
CAT 336 (40 ton) | 459.4 | 1400 | 80 | 17.5 | 8039.5 |  | 0 | 1 | 8039.5 | 1 | 8039.5 | 1 | 8039.5 |  | 0 |  | 0 |  | 20
CAT 336 w hammer | 625.95 | 1400 | 80 | 17.5 | 10954.125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21
CAT 345 (45 ton) | 539.1 | 1400 | 80 | 17.5 | 9434.25 |  | 0 |  | 0 | 0 | 0 | 1 | 9434.25 |  | 0 |  | 0 |  | 22
23
Graders | [18 empty] | 24
CAT 16G grader | 467.05 | 1400 | 80 | 17.5 | 8173.375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25
CAT 140H | 379.35 | 1400 | 80 | 17.5 | 6638.625 | 1 | 6638.625 | 1 | 6638.625 | 1 | 6638.625 | 1 | 6638.625 | 1 | 6638.625 | 1 | 6638.625 |  | 26
27
Haul Trucks | [18 empty] | 28
30 ton Articulated Haul Truck | 426.1 | 1400 | 80 | 17.5 | 7456.75 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 29
35 ton Articulated Haul Truck | 489.05 | 1400 | 80 | 17.5 | 8558.375 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 8558.375 |  | 0 |  | 30
40 ton Articulated Haul Truck | 497.05 | 1400 | 80 | 17.5 | 8698.375 |  | 0 |  | 0 | 0 | 0 | 1 | 8698.375 |  | 0 |  | 0 |  | 31
90 ton Rigid Haul Truck | 659.45 | 1400 | 80 | 17.5 | 11540.375 |  | 0 |  | 0 | 2 | 23080.75 | 4 | 46161.5 |  | 0 |  | 0 |  | 32
Lifting | [18 empty] | 33
30 ton Crane | 414.75 | 1400 | 80 | 17.5 | 7258.125 |  | 0 |  | 0 | 0 | 0 | 1 | 7258.125 |  | 0 |  | 0 |  | 34
35
Loaders | [18 empty] | 36
CAT 950 | 387.5 | 1400 | 80 | 17.5 | 6781.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37
CAT 966 | 434.05 | 1400 | 80 | 17.5 | 7595.875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38
CAT 980 | 492.15 | 1400 | 80 | 17.5 | 8612.625 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 39
Cat 988 | 557.9 | 1400 | 80 | 17.5 | 9763.25 |  | 0 |  | 0 | 1 | 9763.25 | 1 | 9763.25 | 1 | 9763.25 | 1 | 9763.25 |  | 40
Support Vehicles | [18 empty] | 41
Tractor Trailer - 60 ton - lowbed | 381.95 | 1400 | 80 | 17.5 | 6684.125 |  | 0 |  | 0 | 1 | 6684.125 | 1 | 6684.125 |  | 0 |  | 0 |  | 42
Hiab Flatdeck truck | 342.95 | 1400 | 80 | 17.5 | 6001.625 |  | 0 |  | 0 | 1 | 6001.625 | 1 | 6001.625 |  | 0 |  | 0 |  | 43
Water Truck (3,000 gal) | 302.25 | 1400 | 80 | 17.5 | 5289.375 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 44
Water Truck (4,000 gal) | 322.35 | 1400 | 80 | 17.5 | 5641.125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 45
Water Truck (5,000 gal) | 335.4 | 1400 | 80 | 17.5 | 5869.5 |  | 0 |  | 0 | 1 | 5869.5 | 1 | 5869.5 |  | 0 |  | 0 |  | 46
Concrete Transit Mix Truck | 308.2 | 1400 | 80 | 17.5 | 5393.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 47
Fuel Truck | 335.4 | 1400 | 80 | 17.5 | 5869.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 48
Highway, Line Truck, with Aerial Platform | 222.6 | 1400 | 80 | 17.5 | 3895.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 49
Pickup Truck (short term) | 4077 | 1400 | 80 | 17.5 | 71347.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 50
Pickup Truck (long term) | 4077 | 1400 | 80 | 17.5 | 71347.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 51
Pilot Vehicle | 250.7 | 1400 | 80 | 17.5 | 4387.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 52
53
Totals (1-way) | [6 empty] | 12068.875 |  | 27930 |  | 90835.5 |  | 145103.875 |  | 38212.125 |  | 29653.75 |  | 54
Totals (mob-demob) | [6 empty] | 24137.75 |  | 55860 |  | 181671 |  | 290207.75 |  | 76424.25 |  | 59307.5 |  | 55
Notes:
- Rates sourced from 2025/2026 BC Road Builders Blue Book
- YG Third Party Equipment Rental Rates are no longer publicly available.

## T15-ICMM
Table 15
| Interim Care, Maintenance, and Monitoring | [5 empty] | 5
[9 empty] | Year 2 |  |  | Year 5 |  |  | EOM |  |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Comments | Equipment/Labour | Code | Unit Rate | Units | Unit Rate | Units | Quantity | Units | Cost | Quantity | Units | Cost | Quantity | Units | Cost | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Onsite Management
Field Support Staff
| Site Caretaker | 2 years | Site Caretaker | 1 | 182.5 | hr/mo | 51.24 | hr | 0 | hr | 0 | 8760 | hr | 448862.4 | 8760 | hr | 448862.4 | Site Caretaker | 0 |  |  |  |  | Site Caretaker | 8760 |  |  |  |  | Site Caretaker | 8760
| Electrician | 1 month/year, 2 years | Trades Labourer | 1 | 219 | hr/mo | 64.425 | hr | 96 | hr | 6184.8 | 438 | hr | 28218.15 | 438 | hr | 28218.15 | Trades Labourer | 96 |  |  |  |  | Trades Labourer | 438 |  |  |  |  | Trades Labourer | 438
| Mechanic | 1 month/year, 2 years | Trades Labourer | 1 | 219 | hr/mo | 64.425 | hr | 96 | hr | 6184.8 | 438 | hr | 28218.15 | 438 | hr | 28218.15 | Trades Labourer | 96 |  |  |  |  | Trades Labourer | 438 |  |  |  |  | Trades Labourer | 438
| Senior Operator/Supervisor | 2 month/year, 2 years | Site Supervisor | 1 | 182.5 | hr/mo | 198 | hr | 96 | hr | 19008 | 730 | hr | 144540 | 730 | hr | 144540 | Site Supervisor | 96 |  |  |  |  | Site Supervisor | 730 |  |  |  |  | Site Supervisor | 730
Field support Vehicles
| Pick-up trucks |  | Pickup Truck (short term) |  |  |  | 3854.4 | mo | 2 | mo | 7708.8 | 48 | mo | 185011.2 | 48 | mo | 185011.2
Camp and General
| Sundry equipment maintenance |  | annual allowance |  |  |  | 5000 | an | 1 | an | 5000 | 2 | an | 10000 | 2 | an | 10000
| Communications |  | annual allowance |  |  |  | 1000 | an | 1 | an | 1000 | 2 | an | 2000 | 2 | an | 2000
| Misc. supplies |  | annual allowance |  |  |  | 5000 | an | 1 | an | 5000 | 2 | an | 10000 | 2 | an | 10000
| Camp Cost |  | Man-days |  |  |  | 108 | day | 40 | day | 4320 | 879.8333 | day | 95022 | 879.8333 | day | 95022
| Power and heat |  | 5 month/year, 2 years |  |  |  | 5500 | mo | 2 | mo | 11000 | 10 | mo | 55000 | 10 | mo | 55000
Misc
| Sub-Total | [9 empty] | 65406.4 |  |  | 1006871.9 |  |  | 1006871.9
Water Treatment
Active Treatment System
| Operation and maintenance |  | Water Treatment Plant |  |  |  | 2.09 | m3 | 0 | m3 | 0 | 500000 | m3 | 1045000 | 800000 | m3 | 1672000
| Capital Replacement |  | annual allowance
Passive Treatment System
| Operation and maintenance |  | annual allowance |  |  |  | 0 |  | 0 | yr | 0 | 0 | yr | 0 | 0 | yr | 0
| Sub-Total | [9 empty] | 0 |  |  | 1045000 |  |  | 1672000
Site Maintenance
| Road Maintenance | annual allowance | CAT 140H | 2 | 48 | hr/yr | 220 | /hr | 96 | hr | 21120 | 96 | hr | 21120 | 96 | hr | 21120 |  |  | CAT 140H | 96 |  |  |  |  | CAT 140H | 96 |  |  |  |  | CAT 140H | 96
| Earthwork Repair allowance | annual allowance | CAT 420F | 2 | 48 | hr/yr | 150.95 | /hr | 96 | hr | 14491.2 | 96 | hr | 14491.2 | 96 | hr | 14491.2 |  |  | CAT 420F | 96 |  |  |  |  | CAT 420F | 96 |  |  |  |  | CAT 420F | 96
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
|  | annual allowance |  |  |  | hr/yr |  | /hr |  | hr | 0 |  | hr | 0 |  | hr | 0
| Sub-Total | [9 empty] | 35611.2 |  |  | 35611.2 |  |  | 35611.2
Transportation Costs
| Employee Transport Costs |  | 5 months/year, 2 years |  |  |  | 5000 | mo | 4 | mo | 20000 | 10 | mo | 50000 | 10 | mo | 50000
| Heavy Equipment mob-demob | allowance | [6 empty] | 2 | yr | 48275.5 | 2 | yr | 111720 | 2 | yr | 111720
| Sub-Total | [9 empty] | 68275.5 |  |  | 161720 |  |  | 161720
Water Quality Monitoring
| Surface Water | [5 empty] | 15000 | ea | 12 | mo | 180000 | 24 | mo | 360000 | 24 | mo | 360000
| Groundwater | [5 empty] | 10000 | ea | 4 | qu | 40000 | 8 | qu | 80000 | 8 | qu | 80000
| Sub-Total | [9 empty] | 220000 |  |  | 440000 |  |  | 440000
Monitoring
| Physical/Geotech Stability Monitoring | [5 empty] | 20069 | ea | 0 | ea | 0 | 1 | ea | 20069 | 1 | ea | 20069
[8 empty] | ea | 0 | ea | 0 | 0 | ea | 0 | 0 | ea | 0
[8 empty] | ea | 0 | ea | 0 | 0 | ea | 0 | 0 | ea | 0
| Sub-Total | [9 empty] | 0 |  |  | 20069 |  |  | 20069
Road Closure and Reclamation
[8 empty] | ea | 0 | an | 0 | 0 | an | 0 | 0 | ea | 0
[8 empty] | ea | 0 | an | 0 | 0 | an | 0 | 0 | ea | 0
[8 empty] | ea | 0 | an | 0 | 0 | an | 0 | 0 | ea | 0
| Sub-Total | [9 empty] | 0 |  |  | 0 |  |  | 0
Total Estimated Cost for Interim Care and Maintenance | [10 empty] | 389293.1 |  |  | 2709272.1 |  |  | 3336272.1 |  | 480 |  | 192 |  | 0 |  | 10558 |  | 192 |  | 0 |  | 10558 |  | 192 |  | 0
Note on K4: Joel Ray: Camp will not be opened, site inspections, general maintenance and monitoring only.
Note on K8: Joel Ray: No/minimal requirement due to no infrastructure being installed at Year 2.
Note on N8: George Smith: 2 caretakers on alternate rosters 2 year period
Note on Q8: George Smith: 2 caretakers on alternate rosters 2 year period
Note on K9: Joel Ray: No/minimal requirement due to no infrastructure being installed at Year 2.
Note on K10: Joel Ray: No/minimal requirement due to no infrastructure being installed at Year 2.
Note on K11: Joel Ray: No/minimal requirement due to no infrastructure being installed at Year 2.
Note on K13: Joel Ray: 1 month in spring and fall of each year
Note on K43: Joel Ray: Travel/meal allowance as camp will not be open

## T16-PCMM
Table 16
| Post Closure Care, Maintenance, and Monitoring | [5 empty] | 5
[9 empty] | Current |  |  | Year 2 |  |  | Year 5 |  |  | EOM |  |  | Year 2 | [5 empty] | Year 5 | [5 empty] | EOM
Item No. | Work Item Description | Comments | Equipment/Labour | Code | Unit Rate | Units | Unit Rate | Units | Quantity | Units | Annual Cost | Quantity | Units | Annual Cost | Quantity | Units | Annual Cost | Quantity | Units | Annual Cost | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty | Manpower | Manpower Hours | Equipment | Equipment Hours | Material | Material Qty
Capital Costs
Pre-Closure Site Environmental Assessment
| Contamination Surveys | [5 empty] | 100000 | ea |  | ea | 0 | 0.5 | ea | 50000 | 1 | ea | 100000 | 1 | ea | 100000
| Reporting | [5 empty] | 20000 | ea |  | ea | 0 | 0.5 | ea | 10000 | 1 | ea | 20000 | 1 | ea | 20000
| Sub-Total | [9 empty] | 0 |  |  | 60000 |  |  | 120000 |  |  | 120000
Post-Closure Site Environmental Assessment
| Confirmatory Sampling and analysis | [5 empty] | 50000 | ea |  | ea | 0 | 0.5 | ea | 25000 | 1 | ea | 50000 | 1 | ea | 50000
| Reporting | [5 empty] | 20000 | ea |  | ea | 0 | 0.5 | ea | 10000 | 1 | ea | 20000 | 1 | ea | 20000
| Sub-Total | [9 empty] | 0 |  |  | 35000 |  |  | 70000 |  |  | 70000
Instrumentation
| Water Quality | [13 empty] | 1 | ea | 5000 | 1 | ea | 5000
| Flowrate | [13 empty] | 1 | ea | 10000 | 1 | ea | 10000
| Meteorological | [13 empty] | 1 | ea | 10000 | 1 | ea | 10000
| Sub-Total | [9 empty] | 0 |  |  | 0 |  |  | 25000 |  |  | 25000
Total Estimated One Time Costs for Post Closure Care, Maintenance, and Monitoring | [10 empty] | 0 |  |  | 95000 |  |  | 215000 |  |  | 215000
Recurring Costs
Water Treatment
| Active Treatment System | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Operation and maintenance | Water Treatment Plant |  |  |  |  | 2.09 | m3 |  | yr |  | Variable | yr |  | Variable | yr |  | Variable | yr
| Passive Treatment System | Wetlands | [8 empty] | 0 |  |  | 0 |  |  | 10525.95 |  |  | 10525.95
| General Labourer | 2 weeks/year | General Labourer | 1 | 109.5 | hr/yr | 46.5 | hr |  | hr | 0 |  | hr | 0 | 109.5 | hr | 5091.75 | 109.5 | hr | 5091.75 | General Labourer | 0 |  |  |  |  | General Labourer | 109.5 |  |  |  |  | General Labourer | 109.5
| Earthwork Repair allowance | Backhoe | CAT 420F | 2 | 36 | hr/yr | 150.95 | hr |  | hr | 0 |  | hr | 0 | 36 | hr | 5434.2 | 36 | hr | 5434.2 |  |  | CAT 420F | 0 |  |  |  |  | CAT 420F | 36 |  |  |  |  | CAT 420F | 36
| Sub-Total | [9 empty] | 0 |  |  | 0 |  |  | 10525.95 |  |  | 10525.95
| Field Support Staff & Vehicles | [9 empty] | 0 |  |  | 32001.375 |  |  | 32001.375 |  |  | 32001.375
| Trades Labourer | 1 month/year | Trades Labourer | 1 | 219 | hr/mo | 64.425 | hr |  | hr | 0 | 219 | hr | 14109.075 | 219 | hr | 14109.075 | 219 | hr | 14109.075 | Trades Labourer | 219 |  |  |  |  | Trades Labourer | 219 |  |  |  |  | Trades Labourer | 219
| General Labourer | 1 month/year | General Labourer | 1 | 219 | hr/mo | 46.5 | hr |  | hr | 0 | 219 | hr | 10183.5 | 219 | hr | 10183.5 | 219 | hr | 10183.5 | General Labourer | 219 |  |  |  |  | General Labourer | 219 |  |  |  |  | General Labourer | 219
| Pick-up trucks (2 required) |  | Pickup Truck (short term) |  |  |  | 3854.4 | mo |  |  |  | 2 | mth | 7708.8 | 2 | mth | 7708.8 | 2 | mth | 7708.8
| Project Management | Covered in G&A | [8 empty] | 0 |  |  | 44895 |  |  | 105120 |  |  | 105120
| Project Manager | 1 month/year | Project Manager | 1 | 182.5 | hr/mo | 246 | hr |  | hr | 0 | 182.5 | hr | 44895 | 182.5 | hr | 44895 | 182.5 | hr | 44895 | Project Manager | 182.5 |  |  |  |  | Project Manager | 182.5 |  |  |  |  | Project Manager | 182.5
| Passive Treatment Manager | 1 month/year | Passive Treatment Manager | 1 | 219 | hr/mo | 275 | hr |  | hr | 0 |  | hr | 0 | 219 | hr | 60225 | 219 | hr | 60225 | Passive Treatment Manager | 0 |  |  |  |  | Passive Treatment Manager | 219 |  |  |  |  | Passive Treatment Manager | 219
| Camp and General | [9 empty] | 0 |  |  | 22948.5 |  |  | 26229 |  |  | 26229
| Sundry equipment maintenance | annual allowance |  |  |  |  | 5000 | an |  |  |  | 1 | an | 5000 | 1 | an | 5000 | 1 | an | 5000
| Communications | annual allowance |  |  |  |  | 1000 | an |  |  |  | 1 | an | 1000 | 1 | an | 1000 | 1 | an | 1000
| Misc. supplies | annual allowance |  |  |  |  | 5000 | an |  |  |  | 1 | an | 5000 | 1 | an | 5000 | 1 | an | 5000
| Camp Cost | Man-days |  |  |  |  | 108 | day |  |  |  | 59.7083 | an | 6448.5 | 90.0833 | an | 9729 | 90.0833 | an | 9729
| Power and heat | 1 month/year |  |  |  |  | 5500 | mo |  |  |  | 1 | an | 5500 | 1 | an | 5500 | 1 | an | 5500
| Sub-Total | [9 empty] | 0 |  |  | 99844.875 |  |  | 163350.375 |  |  | 163350.375
Reclamation Maintenance
Cover repairs
| Load, haul, dump, spread | 1% of total cover area | Topsoil - General Areas | 3 |  |  | 3.1569 | m3 |  | m3 | 0 | 0 | m3 | 0 | 1850.4225 | m3 | 5841.6007 | 4018.95 | m3 | 12687.4274 |  |  |  |  | Topsoil - General Areas | 0 |  |  |  |  | Topsoil - General Areas | 1850.4225 |  |  |  |  | Topsoil - General Areas | 4018.95
| Seed/Fertilize: broadcast seeding | 5% of total cover area | Revegetation incl Application |  |  |  | 4569.75 | ha |  | ha | 0 | 0 | ha | 0 | 6.1681 | ha | 28186.5607 | 13.3965 | ha | 61218.6559
Site Revegetation
| Seed/Fertilize: broadcast seeding | 5% of total site area (excluding covers) | Revegetation incl Application |  |  |  | 4569.75 | ha |  | ha | 0 | 3.2665 | ha | 14927.0884 | 5.8776 | ha | 26859.0484 | 8.5212 | ha | 38939.5252
| Sub-Total | [9 empty] | 0 |  |  | 14927.0884 |  |  | 60887.2098 |  |  | 112845.6085
Site Maintenance
| Road Maintenance | annual allowance | CAT 140H | 2 | 48 | hr/yr | 220 | hr |  | hr | 0 | 48 | hr | 10560 | 48 | hr | 10560 | 48 | hr | 10560 |  |  | CAT 140H | 48 |  |  |  |  | CAT 140H | 48 |  |  |  |  | CAT 140H | 48
| Earthwork Repair allowance | annual allowance | CAT 420F | 2 | 48 | hr/yr | 150.95 | hr |  | hr | 0 | 48 | hr | 7245.6 | 48 | hr | 7245.6 | 48 | hr | 7245.6 |  |  | CAT 420F | 48 |  |  |  |  | CAT 420F | 48 |  |  |  |  | CAT 420F | 48
| Sub-Total | [9 empty] | 0 |  |  | 17805.6 |  |  | 17805.6 |  |  | 17805.6
Transportation Costs
| Personnel Transportation | Employee Transport Costs |  |  |  |  | 5000 | mth |  | yr | 0 | 1 | mth | 5000 | 1 | mth | 5000 | 1 | mth | 5000
| Heavy Equipment mob-demob |  | annual allowance | [6 empty] | yr | 0 | 1 | yr | 24137.75 | 1 | yr | 59307.5 | 1 | yr | 59307.5
| Sub-Total | [9 empty] | 0 |  |  | 29137.75 |  |  | 64307.5 |  |  | 64307.5
Water Quality Monitoring
[8 empty] | ea |  | ea | 0 | 1 | ea | 0 | 1 | ea | 0 | 1 | ea | 0
| To Delete these rows, after fixing NPV calc sheets | [6 empty] | ea |  | ea | 0 | 1 | ea | 0 | 1 | ea | 0 | 1 | ea | 0
| Sub-Total | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
Monitoring
| Physical/Geotech Stability Monitoring | RCP ref 7.11.1 |  |  |  |  | 20069 | ea |  | ea | 0 | 1 | ea | 20069 | 1 | ea | 20069 | 1 | ea | 20069
| Surface Water Monitoring | RCP ref 7.11.2 |  |  |  |  | 17008 | ea |  | ea | 0 | 1 | ea | 17008 | 1 | ea | 17008 | 1 | ea | 17008
| Groundwater Monitoring | RCP ref 7.11.2 |  |  |  |  | 78761 | ea |  | ea | 0 | 1 | ea | 78761 | 1 | ea | 78761 | 1 | ea | 78761
| Revegetation Success | RCP ref 7.11.3 |  |  |  |  | 54889 | ea |  | ea | 0 | 1 | ea | 54889 | 1 | ea | 54889 | 1 | ea | 54889
| Soil and Vegetation Chemistry | RCP ref 7.11.3 |  |  |  |  | 86663 | ea |  | ea | 0 | 1 | ea | 86663 | 1 | ea | 86663 | 1 | ea | 86663
| Wildlife Aerial Surveys | RCP ref 7.11.3 |  |  |  |  | 157466 | ea |  | ea | 0 | 1 | ea | 157466 | 1 | ea | 157466 | 1 | ea | 157466
| Aquatics | RCP ref 7.11.4 |  |  |  |  | 103824 | ea |  | ea | 0 | 1 | ea | 103824 | 1 | ea | 103824 | 1 | ea | 103824
| Effluent | RCP ref 7.11.4 |  |  |  |  | 21455 | ea |  | ea | 0 | 1 | ea | 21455 | 1 | ea | 21455 | 1 | ea | 21455
| Sub-Total | [9 empty] | 0 |  |  | 540135 |  |  | 540135 |  |  | 540135
Instrumentation Maintenance/Replacement
| Water Quality | [5 empty] | 5000 | ea |  | an | 0 | 1 | an | 5000 | 1 | an | 5000 | 1 | an | 5000
| Flowrate | [5 empty] | 10000 | ea |  | an | 0 | 1 | an | 10000 | 1 | an | 10000 | 1 | an | 10000
| Meteorological | [5 empty] | 5000 | ea |  | an | 0 | 1 | an | 5000 | 1 | an | 5000 | 1 | an | 5000
| Sub-Total | [9 empty] | 0 |  |  | 20000 |  |  | 20000 |  |  | 20000
Table 7.24 | Road Closure and Reclamation
| Current | [5 empty] | 79129.2905 | ea | 1 | ea | 79129.2905 |  | ea | 0 |  | ea | 0 |  | ea | 0
| Year 2 | [5 empty] | 86459.9788 | ea |  | ea | 0 | 1 | ea | 86459.9788 |  | ea | 0 |  | ea | 0
| Year 5 | [5 empty] | 85949.825 | ea |  | ea | 0 |  | ea | 0 | 1 | ea | 85949.825 |  | ea | 0
| LOM | [5 empty] | 113054.5182 | ea |  | ea | 0 |  | ea | 0 |  | ea | 0 | 1 | ea | 113054.5182
| Sub-Total | [9 empty] | 79129.2905 |  |  | 86459.9788 |  |  | 85949.825 |  |  | 113054.5182
Total Estimated Annual Cost for Post Closure Care, Maintenance, and Monitoring | [10 empty] | 79129.2905 |  |  | 808310.2922 |  |  | 962961.4598 |  |  | 1042024.5517 |  | 716.5 |  | 96 |  | 0 |  | 1081 |  | 132 |  | 1850.4225 |  | 1081 |  | 132 |  | 4018.95

## T17-NPV-YR0
Table 17
NPV-Post Closure Care, Maintenance, and Monitoring
| Full Annual Cost/Cost Rate |  |  | Discount Rate |  |  | 7%
| Task | Cost | Units | Number of PC years to include |  |  | 5 |  | *Enter the number of years AFTER transitional closure is complete
| Active Treatment System | 0 | an
| Passive Treatment System | 0 | an
| Field Support Staff & Vehicles | 0 | an
| Project Management | 0 | an
| Camp and General | 0 | an
| Reclamation Maintenance | 0 | an
| Site Maintenance | 0 | an
| Transportation Costs | 0 | an
| Water Quality Monitoring | 0 | ea
| Physical/Geotech Stability Monitoring | 0 | ea
| Surface Water Monitoring | 0 | ea
| Groundwater Monitoring | 0 | ea
| Revegetation Success | 0 | ea
| Soil and Vegetation Chemistry | 0 | ea
| Wildlife Aerial Surveys | 0 | ea
| Aquatics | 0 | ea
| Effluent | 0 | ea
| Instrumentation Maintenance/Replacement | 0 | an
| Road Closure and Reclamation | 79129.2905 | an
| Implementation Schedule |  | Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Active Treatment System
Passive Treatment System
Field Support Staff & Vehicles
Project Management
Camp and General
Reclamation Maintenance
Site Maintenance
Transportation Costs
Water Quality Monitoring
Physical/Geotech Stability Monitoring
Surface Water Monitoring
Groundwater Monitoring
Revegetation Success
Soil and Vegetation Chemistry
Wildlife Aerial Surveys
Aquatics
Effluent
Instrumentation Maintenance/Replacement
Road Closure and Reclamation | bar: Year 3
| Undiscounted Cost |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 0
| Active Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Passive Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff/Equipment | 0
| Field Support Staff & Vehicles | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Camp and General | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance | 0
| Reclamation Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 0
| Transportation Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring | 79129.2905
| Water Quality Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Physical/Geotech Stability Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surface Water Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Groundwater Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revegetation Success | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil and Vegetation Chemistry | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wildlife Aerial Surveys | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aquatics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effluent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instrumentation Maintenance/Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Road Closure and Reclamation | 79129.2905 | 0 | 0 | 79129.2905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 79129.2905 | 0 | 0 | 79129.2905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NPV |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 0
| Active Treatment System | 0
| Passive Treatment System | 0
Staff/Equipment | 0
| Field Support Staff & Vehicles | 0
| Project Management | 0
| Camp and General | 0
Maintenance | 0
| Reclamation Maintenance | 0
| Site Maintenance | 0
Transportation | 0
| Transportation Costs | 0
Monitoring | 64593.0718
| Water Quality Monitoring | 0
| Physical/Geotech Stability Monitoring | 0
| Surface Water Monitoring | 0
| Groundwater Monitoring | 0
| Revegetation Success | 0
| Soil and Vegetation Chemistry | 0
| Wildlife Aerial Surveys | 0
| Aquatics | 0
| Effluent | 0
| Instrumentation Maintenance/Replacement | 0
| Road Closure and Reclamation | 64593.0718 | Year 3: 64593.0718
| Total | 64593.0718 | 0 | 0 | 64593.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## T18-NPV-YR2
Table 18
NPV-Post Closure Care, Maintenance, and Monitoring
| Full Annual Cost/Cost Rate |  |  | Discount Rate |  |  | 7%
| Task | Cost | Units | Number of PC years to include |  |  | 5 |  | *Enter the number of years AFTER transitional closure is complete
| Active Treatment System | 0 | an
| Passive Treatment System | 0 | an
| Field Support Staff & Vehicles | 32001.375 | an
| Project Management | 44895 | an
| Camp and General | 22948.5 | an
| Reclamation Maintenance | 14927.0884 | an
| Site Maintenance | 17805.6 | an
| Transportation Costs | 29137.75 | an
| Water Quality Monitoring | 0 | ea
| Physical/Geotech Stability Monitoring | 0 | ea
| Surface Water Monitoring | 20069 | ea
| Groundwater Monitoring | 54889 | ea
| Revegetation Success | 86663 | ea
| Soil and Vegetation Chemistry | 157466 | ea
| Wildlife Aerial Surveys | 103824 | ea
| Aquatics | 21455 | ea
| Effluent | 0 | ea
| Instrumentation Maintenance/Replacement | 20000 | an
| Road Closure and Reclamation | 86459.9788 | an
| Implementation Schedule |  | Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Active Treatment System
Passive Treatment System | bar: Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
| Field Support Staff & Vehicles |  | Year 2: 1; Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Project Management |  | Year 2: 1; Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Camp and General |  | Year 2: 1; Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Reclamation Maintenance |  | Year 2: 1; Year 3: 1; Year 4: 0.5; Year 5: 0.5; Year 6: 0.25; Year 7: 0.25; Year 8: 0.25; Year 9: 0.25; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Site Maintenance |  | Year 2: 1; Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Transportation Costs |  | Year 2: 1; Year 3: 1; Year 4: 0.5; Year 5: 0.5; Year 6: 0.25; Year 7: 0.25; Year 8: 0.25; Year 9: 0.25; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
Water Quality Monitoring | bar: Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Physical/Geotech Stability Monitoring | bar: Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
| Surface Water Monitoring |  | Year 1: 12; Year 2: 12; Year 3: 6; Year 4: 6; Year 5: 4; Year 6: 2; Year 7: 2; Year 8: 2; Year 9: 2; Year 10: 1; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Groundwater Monitoring |  | Year 1: 4; Year 2: 4; Year 3: 2; Year 4: 2; Year 5: 2; Year 6: 1; Year 7: 1; Year 8: 1; Year 9: 1; Year 10: 1; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
Revegetation Success | bar: Year 1 to Year 3; Year 5; Year 7; Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Soil and Vegetation Chemistry | bar: Year 1; Year 4; Year 7; Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Wildlife Aerial Surveys | bar: Year 1; Year 4; Year 7; Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Aquatics | bar: Year 1; Year 4; Year 7; Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Effluent | bar: Year 1; Year 4; Year 7; Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Instrumentation Maintenance/Replacement | bar: Year 1 to Year 10; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
| Road Closure and Reclamation |  | Year 1: 0.25; Year 5: 0.75; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Undiscounted Cost |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 0
| Active Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Passive Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff/Equipment | 599069.25
| Field Support Staff & Vehicles | 192008.25 | 0 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0
| Project Management | 269370 | 0 | 44895 | 44895 | 44895 | 44895 | 22447.5 | 22447.5 | 22447.5 | 22447.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0 | 0 | 0 | 0 | 44895 | 0
| Camp and General | 137691 | 0 | 22948.5 | 22948.5 | 22948.5 | 22948.5 | 11474.25 | 11474.25 | 11474.25 | 11474.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0 | 0 | 0 | 0 | 22948.5 | 0
Maintenance | 166541.9535
| Reclamation Maintenance | 59708.3535 | 0 | 14927.0884 | 14927.0884 | 7463.5442 | 7463.5442 | 3731.7721 | 3731.7721 | 3731.7721 | 3731.7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0 | 0 | 0 | 0 | 14927.0884 | 0
| Site Maintenance | 106833.6 | 0 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0
Transportation | 116551
| Transportation Costs | 116551 | 0 | 29137.75 | 29137.75 | 14568.875 | 14568.875 | 7284.4375 | 7284.4375 | 7284.4375 | 7284.4375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0 | 0 | 0 | 0 | 29137.75 | 0
Monitoring | 3963689.9788
| Water Quality Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Physical/Geotech Stability Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surface Water Monitoring | 983381 | 240828 | 240828 | 120414 | 120414 | 80276 | 40138 | 40138 | 40138 | 40138 | 20069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0
| Groundwater Monitoring | 1042891 | 219556 | 219556 | 109778 | 109778 | 109778 | 54889 | 54889 | 54889 | 54889 | 54889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0
| Revegetation Success | 519978 | 86663 | 86663 | 86663 | 0 | 86663 | 0 | 86663 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0
| Soil and Vegetation Chemistry | 629864 | 157466 | 0 | 0 | 157466 | 0 | 0 | 157466 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0
| Wildlife Aerial Surveys | 415296 | 103824 | 0 | 0 | 103824 | 0 | 0 | 103824 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0
| Aquatics | 85820 | 21455 | 0 | 0 | 21455 | 0 | 0 | 21455 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0
| Effluent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instrumentation Maintenance/Replacement | 200000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0
| Road Closure and Reclamation | 86459.9788 | 21614.9947 | 0 | 0 | 0 | 64844.9841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0 | 0 | 0 | 0 | 86459.9788 | 0
| Total | 4845852.1823 | 871406.9947 | 728762.3134 | 498570.3134 | 672619.8942 | 501244.8783 | 184868.4471 | 554276.4471 | 184868.4471 | 184868.4471 | 464366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0 | 0 | 0 | 0 | 712541.2922 | 0
| NPV |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 0
| Active Treatment System | 0
| Passive Treatment System | 0 | Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
Staff/Equipment | 436635.1577
| Field Support Staff & Vehicles | 139946.346 | Year 2: 27951.2403; Year 3: 26122.6545; Year 4: 24413.6958; Year 5: 22816.5381; Year 6: 10661.9337; Year 7: 9964.424; Year 8: 9312.5458; Year 9: 8703.3138; Year 41: 1997.2561; Year 46: 1424.016; Year 51: 1015.3037; Year 56: 723.8975; Year 61: 516.1289; Year 66: 367.9928; Year 71: 262.3738; Year 76: 187.0689; Year 81: 133.3775; Year 86: 95.0963; Year 91: 67.8024; Year 96: 48.3422; Year 101: 34.4673; Year 106: 24.5747; Year 111: 17.5214; Year 116: 12.4925; Year 121: 8.907; Year 126: 6.3506; Year 131: 4.5279; Year 136: 3.2283; Year 141: 2.3017; Year 146: 1.6411; Year 151: 1.1701; Year 156: 0.83426; Year 161: 0.59481; Year 166: 0.42409; Year 171: 0.30237; Year 176: 0.21559; Year 181: 0.15371; Year 186: 0.10959; Year 191: 0.078139; Year 196: 0.055712; Year 201: 0.039722; Year 206: 0.028321; Year 211: 0.020193; Year 216: 0.014397; Year 221: 0.010265; Year 226: 0.0073187; Year 231: 0.0052181; Year 236: 0.0037205; Year 241: 0.0026526; Year 246: 0.0018913; Year 251: 0.0013485; Year 256: 0.00096144; Year 261: 0.00068549; Year 266: 0.00048875; Year 271: 0.00034847; Year 276: 0.00024845; Year 281: 0.00017714; Year 286: 0.0001263; Year 291: 9.0051e-05; Year 296: 6.4205e-05; Year 301: 4.5777e-05; Year 306: 3.2639e-05; Year 311: 2.3271e-05; Year 316: 1.6592e-05; Year 321: 1.183e-05; Year 326: 8.4345e-06; Year 331: 6.0137e-06; Year 336: 4.2877e-06; Year 341: 3.057e-06; Year 346: 2.1796e-06; Year 351: 1.554e-06; Year 356: 1.108e-06; Year 361: 7.9e-07; Year 366: 5.6326e-07; Year 371: 4.0159e-07; Year 376: 2.8633e-07; Year 381: 2.0415e-07; Year 386: 1.4556e-07; Year 391: 1.0378e-07; Year 396: 7.3993e-08; Year 401: 5.2756e-08; Year 406: 3.7614e-08; Year 411: 2.6819e-08; Year 416: 1.9121e-08; Year 421: 1.3633e-08; Year 426: 9.7203e-09; Year 431: 6.9304e-09; Year 436: 4.9413e-09; Year 441: 3.5231e-09; Year 446: 2.5119e-09; Year 451: 1.791e-09; Year 456: 1.2769e-09; Year 461: 9.1043e-10; Year 466: 6.4912e-10; Year 471: 4.6282e-10; Year 476: 3.2998e-10; Year 481: 2.3527e-10; Year 486: 1.6775e-10; Year 491: 1.196e-10
| Project Management | 196331.9139 | Year 2: 39213.0317; Year 3: 36647.6932; Year 4: 34250.1805; Year 5: 32009.5145; Year 6: 14957.7171; Year 7: 13979.1748; Year 8: 13064.6494; Year 9: 12209.9527; Year 41: 2801.9675; Year 46: 1997.7641; Year 51: 1424.3782; Year 56: 1015.562; Year 61: 724.0816; Year 66: 516.2602; Year 71: 368.0864; Year 76: 262.4405; Year 81: 187.1165; Year 86: 133.4114; Year 91: 95.1205; Year 96: 67.8196; Year 101: 48.3544; Year 106: 34.4761; Year 111: 24.5809; Year 116: 17.5259; Year 121: 12.4957; Year 126: 8.9093; Year 131: 6.3522; Year 136: 4.529; Year 141: 3.2291; Year 146: 2.3023; Year 151: 1.6415; Year 156: 1.1704; Year 161: 0.83447; Year 166: 0.59496; Year 171: 0.4242; Year 176: 0.30245; Year 181: 0.21564; Year 186: 0.15375; Year 191: 0.10962; Year 196: 0.078159; Year 201: 0.055726; Year 206: 0.039732; Year 211: 0.028328; Year 216: 0.020198; Year 221: 0.014401; Year 226: 0.010267; Year 231: 0.0073206; Year 236: 0.0052195; Year 241: 0.0037214; Year 246: 0.0026533; Year 251: 0.0018918; Year 256: 0.0013488; Year 261: 0.00096168; Year 266: 0.00068567; Year 271: 0.00048887; Year 276: 0.00034856; Year 281: 0.00024852; Year 286: 0.00017719; Year 291: 0.00012633; Year 296: 9.0074e-05; Year 301: 6.4222e-05; Year 306: 4.5789e-05; Year 311: 3.2647e-05; Year 316: 2.3277e-05; Year 321: 1.6596e-05; Year 326: 1.1833e-05; Year 331: 8.4366e-06; Year 336: 6.0152e-06; Year 341: 4.2887e-06; Year 346: 3.0578e-06; Year 351: 2.1802e-06; Year 356: 1.5544e-06; Year 361: 1.1083e-06; Year 366: 7.902e-07; Year 371: 5.634e-07; Year 376: 4.017e-07; Year 381: 2.864e-07; Year 386: 2.042e-07; Year 391: 1.4559e-07; Year 396: 1.0381e-07; Year 401: 7.4012e-08; Year 406: 5.277e-08; Year 411: 3.7624e-08; Year 416: 2.6825e-08; Year 421: 1.9126e-08; Year 426: 1.3637e-08; Year 431: 9.7228e-09; Year 436: 6.9322e-09; Year 441: 4.9426e-09; Year 446: 3.524e-09; Year 451: 2.5125e-09; Year 456: 1.7914e-09; Year 461: 1.2773e-09; Year 466: 9.1066e-10; Year 471: 6.4929e-10; Year 476: 4.6293e-10; Year 481: 3.3007e-10; Year 486: 2.3533e-10; Year 491: 1.6779e-10
| Camp and General | 100356.8978 | Year 2: 20044.1087; Year 3: 18732.8118; Year 4: 17507.3008; Year 5: 16361.9633; Year 6: 7645.7773; Year 7: 7145.5862; Year 8: 6678.118; Year 9: 6241.2317; Year 41: 1432.2519; Year 46: 1021.1758; Year 51: 728.0843; Year 56: 519.114; Year 61: 370.1211; Year 66: 263.8912; Year 71: 188.1508; Year 76: 134.1489; Year 81: 95.6463; Year 86: 68.1945; Year 91: 48.6217; Year 96: 34.6666; Year 101: 24.7168; Year 106: 17.6228; Year 111: 12.5648; Year 116: 8.9585; Year 121: 6.3873; Year 126: 4.5541; Year 131: 3.247; Year 136: 2.3151; Year 141: 1.6506; Year 146: 1.1769; Year 151: 0.83908; Year 156: 0.59825; Year 161: 0.42655; Year 166: 0.30412; Year 171: 0.21683; Year 176: 0.1546; Year 181: 0.11023; Year 186: 0.078591; Year 191: 0.056034; Year 196: 0.039952; Year 201: 0.028485; Year 206: 0.020309; Year 211: 0.01448; Year 216: 0.010324; Year 221: 0.007361; Year 226: 0.0052483; Year 231: 0.003742; Year 236: 0.002668; Year 241: 0.0019022; Year 246: 0.0013563; Year 251: 0.000967; Year 256: 0.00068946; Year 261: 0.00049157; Year 266: 0.00035049; Year 271: 0.00024989; Year 276: 0.00017817; Year 281: 0.00012703; Year 286: 9.0572e-05; Year 291: 6.4577e-05; Year 296: 4.6042e-05; Year 301: 3.2827e-05; Year 306: 2.3406e-05; Year 311: 1.6688e-05; Year 316: 1.1898e-05; Year 321: 8.4832e-06; Year 326: 6.0484e-06; Year 331: 4.3124e-06; Year 336: 3.0747e-06; Year 341: 2.1922e-06; Year 346: 1.563e-06; Year 351: 1.1144e-06; Year 356: 7.9457e-07; Year 361: 5.6651e-07; Year 366: 4.0392e-07; Year 371: 2.8799e-07; Year 376: 2.0533e-07; Year 381: 1.464e-07; Year 386: 1.0438e-07; Year 391: 7.4421e-08; Year 396: 5.3061e-08; Year 401: 3.7832e-08; Year 406: 2.6974e-08; Year 411: 1.9232e-08; Year 416: 1.3712e-08; Year 421: 9.7765e-09; Year 426: 6.9705e-09; Year 431: 4.9699e-09; Year 436: 3.5435e-09; Year 441: 2.5264e-09; Year 446: 1.8013e-09; Year 451: 1.2843e-09; Year 456: 9.157e-10; Year 461: 6.5288e-10; Year 466: 4.6549e-10; Year 471: 3.3189e-10; Year 476: 2.3663e-10; Year 481: 1.6872e-10; Year 486: 1.2029e-10; Year 491: 8.5767e-11
Maintenance | 123116.8129
| Reclamation Maintenance | 45250.5131 | Year 2: 13037.8971; Year 3: 12184.9505; Year 4: 5693.9021; Year 5: 5321.4039; Year 6: 2486.6373; Year 7: 2323.9601; Year 8: 2171.9253; Year 9: 2029.8368; Year 41: 931.623; Year 46: 664.2343; Year 51: 473.5899; Year 56: 337.6631; Year 61: 240.7491; Year 66: 171.6508; Year 71: 122.3846; Year 76: 87.2586; Year 81: 62.2141; Year 86: 44.3578; Year 91: 31.6265; Year 96: 22.5493; Year 101: 16.0773; Year 106: 11.4629; Year 111: 8.1729; Year 116: 5.8272; Year 121: 4.1547; Year 126: 2.9622; Year 131: 2.112; Year 136: 1.5058; Year 141: 1.0736; Year 146: 0.7655; Year 151: 0.54579; Year 156: 0.38914; Year 161: 0.27745; Year 166: 0.19782; Year 171: 0.14104; Year 176: 0.10056; Year 181: 0.071699; Year 186: 0.05112; Year 191: 0.036448; Year 196: 0.025987; Year 201: 0.018528; Year 206: 0.01321; Year 211: 0.0094189; Year 216: 0.0067155; Year 221: 0.0047881; Year 226: 0.0034138; Year 231: 0.002434; Year 236: 0.0017354; Year 241: 0.0012373; Year 246: 0.0008822; Year 251: 0.00062899; Year 256: 0.00044846; Year 261: 0.00031975; Year 266: 0.00022798; Year 271: 0.00016254; Year 276: 0.00011589; Year 281: 8.2629e-05; Year 286: 5.8913e-05; Year 291: 4.2004e-05; Year 296: 2.9949e-05; Year 301: 2.1353e-05; Year 306: 1.5224e-05; Year 311: 1.0855e-05; Year 316: 7.7393e-06; Year 321: 5.518e-06; Year 326: 3.9343e-06; Year 331: 2.8051e-06; Year 336: 2e-06; Year 341: 1.426e-06; Year 346: 1.0167e-06; Year 351: 7.2489e-07; Year 356: 5.1683e-07; Year 361: 3.6849e-07; Year 366: 2.6273e-07; Year 371: 1.8732e-07; Year 376: 1.3356e-07; Year 381: 9.5226e-08; Year 386: 6.7895e-08; Year 391: 4.8408e-08; Year 396: 3.4514e-08; Year 401: 2.4608e-08; Year 406: 1.7545e-08; Year 411: 1.251e-08; Year 416: 8.9192e-09; Year 421: 6.3592e-09; Year 426: 4.534e-09; Year 431: 3.2327e-09; Year 436: 2.3049e-09; Year 441: 1.6433e-09; Year 446: 1.1717e-09; Year 451: 8.3539e-10; Year 456: 5.9562e-10; Year 461: 4.2467e-10; Year 466: 3.0279e-10; Year 471: 2.1588e-10; Year 476: 1.5392e-10; Year 481: 1.0974e-10; Year 486: 7.8245e-11; Year 491: 5.5788e-11
| Site Maintenance | 77866.2997 | Year 2: 15552.1006; Year 3: 14534.6735; Year 4: 13583.807; Year 5: 12695.1467; Year 6: 5932.3116; Year 7: 5544.2164; Year 8: 5181.5107; Year 9: 4842.5333; Year 41: 1111.2755; Year 46: 792.3241; Year 51: 564.9161; Year 56: 402.7774; Year 61: 287.1747; Year 66: 204.7516; Year 71: 145.9851; Year 76: 104.0853; Year 81: 74.2114; Year 86: 52.9117; Year 91: 37.7253; Year 96: 26.8976; Year 101: 19.1776; Year 106: 13.6734; Year 111: 9.7489; Year 116: 6.9509; Year 121: 4.9559; Year 126: 3.5335; Year 131: 2.5193; Year 136: 1.7962; Year 141: 1.2807; Year 146: 0.91311; Year 151: 0.65104; Year 156: 0.46418; Year 161: 0.33095; Year 166: 0.23597; Year 171: 0.16824; Year 176: 0.11995; Year 181: 0.085525; Year 186: 0.060978; Year 191: 0.043477; Year 196: 0.030998; Year 201: 0.022101; Year 206: 0.015758; Year 211: 0.011235; Year 216: 0.0080105; Year 221: 0.0057114; Year 226: 0.0040721; Year 231: 0.0029034; Year 236: 0.0020701; Year 241: 0.0014759; Year 246: 0.0010523; Year 251: 0.00075029; Year 256: 0.00053495; Year 261: 0.00038141; Year 266: 0.00027194; Year 271: 0.00019389; Year 276: 0.00013824; Year 281: 9.8563e-05; Year 286: 7.0274e-05; Year 291: 5.0105e-05; Year 296: 3.5724e-05; Year 301: 2.5471e-05; Year 306: 1.816e-05; Year 311: 1.2948e-05; Year 316: 9.2317e-06; Year 321: 6.5821e-06; Year 326: 4.6929e-06; Year 331: 3.346e-06; Year 336: 2.3857e-06; Year 341: 1.7009e-06; Year 346: 1.2127e-06; Year 351: 8.6467e-07; Year 356: 6.165e-07; Year 361: 4.3955e-07; Year 366: 3.134e-07; Year 371: 2.2345e-07; Year 376: 1.5931e-07; Year 381: 1.1359e-07; Year 386: 8.0988e-08; Year 391: 5.7743e-08; Year 396: 4.117e-08; Year 401: 2.9354e-08; Year 406: 2.0929e-08; Year 411: 1.4922e-08; Year 416: 1.0639e-08; Year 421: 7.5855e-09; Year 426: 5.4084e-09; Year 431: 3.8561e-09; Year 436: 2.7493e-09; Year 441: 1.9602e-09; Year 446: 1.3976e-09; Year 451: 9.9649e-10; Year 456: 7.1048e-10; Year 461: 5.0656e-10; Year 466: 3.6117e-10; Year 471: 2.5751e-10; Year 476: 1.836e-10; Year 481: 1.3091e-10; Year 486: 9.3334e-11; Year 491: 6.6546e-11
Transportation | 88329.2244
| Transportation Costs | 88329.2244 | Year 2: 25450.0393; Year 3: 23785.0835; Year 4: 11114.525; Year 5: 10387.4065; Year 6: 4853.9283; Year 7: 4536.3816; Year 8: 4239.6089; Year 9: 3962.2514; Year 41: 1818.5328; Year 46: 1296.5887; Year 51: 924.4498; Year 56: 659.12; Year 61: 469.9434; Year 66: 335.0632; Year 71: 238.8954; Year 76: 170.3291; Year 81: 121.4423; Year 86: 86.5867; Year 91: 61.7351; Year 96: 44.0163; Year 101: 31.383; Year 106: 22.3756; Year 111: 15.9535; Year 116: 11.3746; Year 121: 8.11; Year 126: 5.7823; Year 131: 4.1227; Year 136: 2.9394; Year 141: 2.0958; Year 146: 1.4943; Year 151: 1.0654; Year 156: 0.7596; Year 161: 0.54159; Year 166: 0.38614; Year 171: 0.27532; Year 176: 0.1963; Year 181: 0.13996; Year 186: 0.099787; Year 191: 0.071147; Year 196: 0.050727; Year 201: 0.036167; Year 206: 0.025787; Year 211: 0.018386; Year 216: 0.013109; Year 221: 0.0093463; Year 226: 0.0066638; Year 231: 0.0047512; Year 236: 0.0033875; Year 241: 0.0024153; Year 246: 0.0017221; Year 251: 0.0012278; Year 256: 0.0008754; Year 261: 0.00062415; Year 266: 0.00044501; Year 271: 0.00031729; Year 276: 0.00022622; Year 281: 0.00016129; Year 286: 0.000115; Year 291: 8.1993e-05; Year 296: 5.846e-05; Year 301: 4.1681e-05; Year 306: 2.9718e-05; Year 311: 2.1189e-05; Year 316: 1.5107e-05; Year 321: 1.0771e-05; Year 326: 7.6797e-06; Year 331: 5.4755e-06; Year 336: 3.904e-06; Year 341: 2.7835e-06; Year 346: 1.9846e-06; Year 351: 1.415e-06; Year 356: 1.0089e-06; Year 361: 7.193e-07; Year 366: 5.1285e-07; Year 371: 3.6566e-07; Year 376: 2.6071e-07; Year 381: 1.8588e-07; Year 386: 1.3253e-07; Year 391: 9.4493e-08; Year 396: 6.7372e-08; Year 401: 4.8035e-08; Year 406: 3.4249e-08; Year 411: 2.4419e-08; Year 416: 1.741e-08; Year 421: 1.2413e-08; Year 426: 8.8505e-09; Year 431: 6.3103e-09; Year 436: 4.4991e-09; Year 441: 3.2078e-09; Year 446: 2.2871e-09; Year 451: 1.6307e-09; Year 456: 1.1627e-09; Year 461: 8.2896e-10; Year 466: 5.9104e-10; Year 471: 4.214e-10; Year 476: 3.0045e-10; Year 481: 2.1422e-10; Year 486: 1.5274e-10; Year 491: 1.089e-10
Monitoring | 2992920.7491
| Water Quality Monitoring | 0 | Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Physical/Geotech Stability Monitoring | 0 | Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Surface Water Monitoring | 789950.7637 | Year 1: 225072.8972; Year 2: 210348.5021; Year 3: 98293.6925; Year 4: 91863.2641; Year 5: 57235.6785; Year 6: 26745.6442; Year 7: 24995.9291; Year 8: 23360.6814; Year 9: 21832.4126; Year 10: 10202.0619; Year 41: 1252.5378; Year 46: 893.0422; Year 51: 636.7267; Year 56: 453.9773; Year 61: 323.6796; Year 66: 230.7791; Year 71: 164.5423; Year 76: 117.3164; Year 81: 83.645; Year 86: 59.6377; Year 91: 42.5209; Year 96: 30.3168; Year 101: 21.6154; Year 106: 15.4115; Year 111: 10.9882; Year 116: 7.8344; Year 121: 5.5858; Year 126: 3.9826; Year 131: 2.8396; Year 136: 2.0246; Year 141: 1.4435; Year 146: 1.0292; Year 151: 0.7338; Year 156: 0.52319; Year 161: 0.37302; Year 166: 0.26596; Year 171: 0.18963; Year 176: 0.1352; Year 181: 0.096397; Year 186: 0.068729; Year 191: 0.049003; Year 196: 0.034939; Year 201: 0.024911; Year 206: 0.017761; Year 211: 0.012663; Year 216: 0.0090288; Year 221: 0.0064374; Year 226: 0.0045898; Year 231: 0.0032725; Year 236: 0.0023332; Year 241: 0.0016635; Year 246: 0.0011861; Year 251: 0.00084566; Year 256: 0.00060295; Year 261: 0.00042989; Year 266: 0.00030651; Year 271: 0.00021854; Year 276: 0.00015581; Year 281: 0.00011109; Year 286: 7.9207e-05; Year 291: 5.6474e-05; Year 296: 4.0265e-05; Year 301: 2.8708e-05; Year 306: 2.0469e-05; Year 311: 1.4594e-05; Year 316: 1.0405e-05; Year 321: 7.4188e-06; Year 326: 5.2895e-06; Year 331: 3.7713e-06; Year 336: 2.6889e-06; Year 341: 1.9172e-06; Year 346: 1.3669e-06; Year 351: 9.7459e-07; Year 356: 6.9487e-07; Year 361: 4.9543e-07; Year 366: 3.5323e-07; Year 371: 2.5185e-07; Year 376: 1.7957e-07; Year 381: 1.2803e-07; Year 386: 9.1283e-08; Year 391: 6.5083e-08; Year 396: 4.6403e-08; Year 401: 3.3085e-08; Year 406: 2.3589e-08; Year 411: 1.6819e-08; Year 416: 1.1992e-08; Year 421: 8.5498e-09; Year 426: 6.0959e-09; Year 431: 4.3463e-09; Year 436: 3.0988e-09; Year 441: 2.2094e-09; Year 446: 1.5753e-09; Year 451: 1.1232e-09; Year 456: 8.008e-10; Year 461: 5.7096e-10; Year 466: 4.0709e-10; Year 471: 2.9025e-10; Year 476: 2.0694e-10; Year 481: 1.4755e-10; Year 486: 1.052e-10; Year 491: 7.5005e-11
| Groundwater Monitoring | 809053.7227 | Year 1: 205192.5234; Year 2: 191768.7134; Year 3: 89611.5483; Year 4: 83749.1106; Year 5: 78270.1968; Year 6: 36574.8583; Year 7: 34182.1106; Year 8: 31945.8977; Year 9: 29855.9792; Year 10: 27902.7843; Year 41: 3425.7087; Year 46: 2442.483; Year 51: 1741.4566; Year 56: 1241.6345; Year 61: 885.2682; Year 66: 631.184; Year 71: 450.0255; Year 76: 320.8619; Year 81: 228.7701; Year 86: 163.1099; Year 91: 116.2951; Year 96: 82.9168; Year 101: 59.1185; Year 106: 42.1507; Year 111: 30.0529; Year 116: 21.4273; Year 121: 15.2774; Year 126: 10.8925; Year 131: 7.7662; Year 136: 5.5372; Year 141: 3.948; Year 146: 2.8148; Year 151: 2.0069; Year 156: 1.4309; Year 161: 1.0202; Year 166: 0.72741; Year 171: 0.51863; Year 176: 0.36978; Year 181: 0.26365; Year 186: 0.18798; Year 191: 0.13402; Year 196: 0.095558; Year 201: 0.068131; Year 206: 0.048577; Year 211: 0.034634; Year 216: 0.024694; Year 221: 0.017606; Year 226: 0.012553; Year 231: 0.0089502; Year 236: 0.0063814; Year 241: 0.0045498; Year 246: 0.003244; Year 251: 0.0023129; Year 256: 0.0016491; Year 261: 0.0011758; Year 266: 0.0008383; Year 271: 0.0005977; Year 276: 0.00042615; Year 281: 0.00030384; Year 286: 0.00021663; Year 291: 0.00015446; Year 296: 0.00011013; Year 301: 7.8518e-05; Year 306: 5.5982e-05; Year 311: 3.9914e-05; Year 316: 2.8458e-05; Year 321: 2.029e-05; Year 326: 1.4467e-05; Year 331: 1.0315e-05; Year 336: 7.3542e-06; Year 341: 5.2434e-06; Year 346: 3.7385e-06; Year 351: 2.6655e-06; Year 356: 1.9005e-06; Year 361: 1.355e-06; Year 366: 9.661e-07; Year 371: 6.8882e-07; Year 376: 4.9112e-07; Year 381: 3.5016e-07; Year 386: 2.4966e-07; Year 391: 1.78e-07; Year 396: 1.2691e-07; Year 401: 9.0488e-08; Year 406: 6.4517e-08; Year 411: 4.5999e-08; Year 416: 3.2797e-08; Year 421: 2.3384e-08; Year 426: 1.6672e-08; Year 431: 1.1887e-08; Year 436: 8.4754e-09; Year 441: 6.0428e-09; Year 446: 4.3084e-09; Year 451: 3.0719e-09; Year 456: 2.1902e-09; Year 461: 1.5616e-09; Year 466: 1.1134e-09; Year 471: 7.9383e-10; Year 476: 5.6599e-10; Year 481: 4.0354e-10; Year 486: 2.8772e-10; Year 491: 2.0514e-10
| Revegetation Success | 387245.0582 | Year 1: 80993.4579; Year 2: 75694.8205; Year 3: 70742.8229; Year 5: 61789.5213; Year 7: 53969.3609; Year 10: 44055.0747; Year 41: 5408.774; Year 46: 3856.3811; Year 51: 2749.5464; Year 56: 1960.3886; Year 61: 1397.73; Year 66: 996.5622; Year 71: 710.535; Year 76: 506.6017; Year 81: 361.2; Year 86: 257.5306; Year 91: 183.6158; Year 96: 130.9155; Year 101: 93.3409; Year 106: 66.5508; Year 111: 47.4498; Year 116: 33.8311; Year 121: 24.1211; Year 126: 17.198; Year 131: 12.2619; Year 136: 8.7426; Year 141: 6.2333; Year 146: 4.4443; Year 151: 3.1687; Year 156: 2.2593; Year 161: 1.6108; Year 166: 1.1485; Year 171: 0.81886; Year 176: 0.58383; Year 181: 0.41627; Year 186: 0.29679; Year 191: 0.21161; Year 196: 0.15087; Year 201: 0.10757; Year 206: 0.076696; Year 211: 0.054684; Year 216: 0.038989; Year 221: 0.027798; Year 226: 0.01982; Year 231: 0.014131; Year 236: 0.010075; Year 241: 0.0071836; Year 246: 0.0051218; Year 251: 0.0036518; Year 256: 0.0026037; Year 261: 0.0018564; Year 266: 0.0013236; Year 271: 0.00094369; Year 276: 0.00067284; Year 281: 0.00047972; Year 286: 0.00034204; Year 291: 0.00024387; Year 296: 0.00017387; Year 301: 0.00012397; Year 306: 8.8389e-05; Year 311: 6.302e-05; Year 316: 4.4932e-05; Year 321: 3.2036e-05; Year 326: 2.2841e-05; Year 331: 1.6286e-05; Year 336: 1.1611e-05; Year 341: 8.2788e-06; Year 346: 5.9026e-06; Year 351: 4.2085e-06; Year 356: 3.0006e-06; Year 361: 2.1394e-06; Year 366: 1.5254e-06; Year 371: 1.0876e-06; Year 376: 7.7541e-07; Year 381: 5.5286e-07; Year 386: 3.9418e-07; Year 391: 2.8105e-07; Year 396: 2.0038e-07; Year 401: 1.4287e-07; Year 406: 1.0186e-07; Year 411: 7.2627e-08; Year 416: 5.1782e-08; Year 421: 3.692e-08; Year 426: 2.6324e-08; Year 431: 1.8768e-08; Year 436: 1.3382e-08; Year 441: 9.5409e-09; Year 446: 6.8025e-09; Year 451: 4.8501e-09; Year 456: 3.458e-09; Year 461: 2.4655e-09; Year 466: 1.7579e-09; Year 471: 1.2534e-09; Year 476: 8.9363e-10; Year 481: 6.3714e-10; Year 486: 4.5427e-10; Year 491: 3.2389e-10
| Soil and Vegetation Chemistry | 445404.1839 | Year 1: 147164.486; Year 4: 120130.0575; Year 7: 98061.9109; Year 10: 80047.7296; Year 41: 9827.7004; Year 46: 7007.0146; Year 51: 4995.9046; Year 56: 3562.0109; Year 61: 2539.6645; Year 66: 1810.7457; Year 71: 1291.0367; Year 76: 920.4913; Year 81: 656.2976; Year 86: 467.9311; Year 91: 333.6284; Year 96: 237.8724; Year 101: 169.5998; Year 106: 120.9223; Year 111: 86.2159; Year 116: 61.4708; Year 121: 43.8278; Year 126: 31.2486; Year 131: 22.2798; Year 136: 15.8852; Year 141: 11.3259; Year 146: 8.0752; Year 151: 5.7575; Year 156: 4.105; Year 161: 2.9268; Year 166: 2.0868; Year 171: 1.4879; Year 176: 1.0608; Year 181: 0.75635; Year 186: 0.53927; Year 191: 0.38449; Year 196: 0.27414; Year 201: 0.19546; Year 206: 0.13936; Year 211: 0.09936; Year 216: 0.070842; Year 221: 0.050509; Year 226: 0.036012; Year 231: 0.025676; Year 236: 0.018307; Year 241: 0.013053; Year 246: 0.0093063; Year 251: 0.0066353; Year 256: 0.0047309; Year 261: 0.003373; Year 266: 0.0024049; Year 271: 0.0017147; Year 276: 0.0012225; Year 281: 0.00087166; Year 286: 0.00062148; Year 291: 0.00044311; Year 296: 0.00031593; Year 301: 0.00022525; Year 306: 0.0001606; Year 311: 0.00011451; Year 316: 8.1642e-05; Year 321: 5.821e-05; Year 326: 4.1503e-05; Year 331: 2.9591e-05; Year 336: 2.1098e-05; Year 341: 1.5042e-05; Year 346: 1.0725e-05; Year 351: 7.6468e-06; Year 356: 5.4521e-06; Year 361: 3.8873e-06; Year 366: 2.7716e-06; Year 371: 1.9761e-06; Year 376: 1.4089e-06; Year 381: 1.0045e-06; Year 386: 7.1622e-07; Year 391: 5.1066e-07; Year 396: 3.6409e-07; Year 401: 2.5959e-07; Year 406: 1.8509e-07; Year 411: 1.3196e-07; Year 416: 9.4088e-08; Year 421: 6.7084e-08; Year 426: 4.783e-08; Year 431: 3.4102e-08; Year 436: 2.4314e-08; Year 441: 1.7336e-08; Year 446: 1.236e-08; Year 451: 8.8126e-09; Year 456: 6.2832e-09; Year 461: 4.4799e-09; Year 466: 3.1941e-09; Year 471: 2.2773e-09; Year 476: 1.6237e-09; Year 481: 1.1577e-09; Year 486: 8.2541e-10; Year 491: 5.8851e-10
| Wildlife Aerial Surveys | 293673.8343 | Year 1: 97031.7757; Year 4: 79206.8325; Year 7: 64656.3692; Year 10: 52778.8569; Year 41: 6479.819; Year 46: 4620.0214; Year 51: 3294.0114; Year 56: 2348.5846; Year 61: 1674.5084; Year 66: 1193.9013; Year 71: 851.2351; Year 76: 606.9189; Year 81: 432.7248; Year 86: 308.5268; Year 91: 219.9753; Year 96: 156.8394; Year 101: 111.8243; Year 106: 79.7292; Year 111: 56.8458; Year 116: 40.5303; Year 121: 28.8975; Year 126: 20.6035; Year 131: 14.69; Year 136: 10.4738; Year 141: 7.4677; Year 146: 5.3243; Year 151: 3.7962; Year 156: 2.7066; Year 161: 1.9298; Year 166: 1.3759; Year 171: 0.98101; Year 176: 0.69944; Year 181: 0.49869; Year 186: 0.35556; Year 191: 0.25351; Year 196: 0.18075; Year 201: 0.12887; Year 206: 0.091884; Year 211: 0.065512; Year 216: 0.046709; Year 221: 0.033303; Year 226: 0.023745; Year 231: 0.01693; Year 236: 0.012071; Year 241: 0.0086061; Year 246: 0.006136; Year 251: 0.0043749; Year 256: 0.0031193; Year 261: 0.002224; Year 266: 0.0015857; Year 271: 0.0011306; Year 276: 0.00080607; Year 281: 0.00057472; Year 286: 0.00040977; Year 291: 0.00029216; Year 296: 0.0002083; Year 301: 0.00014852; Year 306: 0.00010589; Year 311: 7.5499e-05; Year 316: 5.383e-05; Year 321: 3.838e-05; Year 326: 2.7364e-05; Year 331: 1.951e-05; Year 336: 1.3911e-05; Year 341: 9.9181e-06; Year 346: 7.0715e-06; Year 351: 5.0419e-06; Year 356: 3.5948e-06; Year 361: 2.563e-06; Year 366: 1.8274e-06; Year 371: 1.3029e-06; Year 376: 9.2896e-07; Year 381: 6.6234e-07; Year 386: 4.7224e-07; Year 391: 3.367e-07; Year 396: 2.4006e-07; Year 401: 1.7116e-07; Year 406: 1.2203e-07; Year 411: 8.7009e-08; Year 416: 6.2036e-08; Year 421: 4.4231e-08; Year 426: 3.1536e-08; Year 431: 2.2485e-08; Year 436: 1.6031e-08; Year 441: 1.143e-08; Year 446: 8.1495e-09; Year 451: 5.8105e-09; Year 456: 4.1428e-09; Year 461: 2.9538e-09; Year 466: 2.106e-09; Year 471: 1.5015e-09; Year 476: 1.0706e-09; Year 481: 7.6331e-10; Year 486: 5.4423e-10; Year 491: 3.8803e-10
| Aquatics | 60687.0484 | Year 1: 20051.4019; Year 4: 16367.9168; Year 7: 13361.0957; Year 10: 10906.6341; Year 41: 1339.0403; Year 46: 954.7172; Year 51: 680.7002; Year 56: 485.3298; Year 61: 346.0334; Year 66: 246.7171; Year 71: 175.9059; Year 76: 125.4184; Year 81: 89.4216; Year 86: 63.7564; Year 91: 45.4574; Year 96: 32.4105; Year 101: 23.1082; Year 106: 16.4759; Year 111: 11.7471; Year 116: 8.3755; Year 121: 5.9716; Year 126: 4.2577; Year 131: 3.0357; Year 136: 2.1644; Year 141: 1.5432; Year 146: 1.1003; Year 151: 0.78447; Year 156: 0.55932; Year 161: 0.39879; Year 166: 0.28433; Year 171: 0.20272; Year 176: 0.14454; Year 181: 0.10305; Year 186: 0.073476; Year 191: 0.052387; Year 196: 0.037352; Year 201: 0.026631; Year 206: 0.018988; Year 211: 0.013538; Year 216: 0.0096523; Year 221: 0.006882; Year 226: 0.0049068; Year 231: 0.0034985; Year 236: 0.0024943; Year 241: 0.0017784; Year 246: 0.001268; Year 251: 0.00090407; Year 256: 0.00064459; Year 261: 0.00045958; Year 266: 0.00032768; Year 271: 0.00023363; Year 276: 0.00016657; Year 281: 0.00011876; Year 286: 8.4678e-05; Year 291: 6.0374e-05; Year 296: 4.3046e-05; Year 301: 3.0691e-05; Year 306: 2.1882e-05; Year 311: 1.5602e-05; Year 316: 1.1124e-05; Year 321: 7.9311e-06; Year 326: 5.6548e-06; Year 331: 4.0318e-06; Year 336: 2.8746e-06; Year 341: 2.0496e-06; Year 346: 1.4613e-06; Year 351: 1.0419e-06; Year 356: 7.4285e-07; Year 361: 5.2964e-07; Year 366: 3.7763e-07; Year 371: 2.6924e-07; Year 376: 1.9197e-07; Year 381: 1.3687e-07; Year 386: 9.7587e-08; Year 391: 6.9578e-08; Year 396: 4.9608e-08; Year 401: 3.537e-08; Year 406: 2.5218e-08; Year 411: 1.798e-08; Year 416: 1.282e-08; Year 421: 9.1403e-09; Year 426: 6.5169e-09; Year 431: 4.6464e-09; Year 436: 3.3128e-09; Year 441: 2.362e-09; Year 446: 1.6841e-09; Year 451: 1.2007e-09; Year 456: 8.561e-10; Year 461: 6.1039e-10; Year 466: 4.352e-10; Year 471: 3.1029e-10; Year 476: 2.2123e-10; Year 481: 1.5774e-10; Year 486: 1.1246e-10; Year 491: 8.0185e-11
| Effluent | 0 | Year 1: 0; Year 4: 0; Year 7: 0; Year 10: 0; Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Instrumentation Maintenance/Replacement | 140471.6308 | Year 1: 18691.5888; Year 2: 17468.7746; Year 3: 16325.9575; Year 4: 15257.9042; Year 5: 14259.7236; Year 6: 13326.8445; Year 7: 12454.9948; Year 8: 11640.1821; Year 9: 10878.6749; Year 10: 10166.9858; Year 41: 1248.2314; Year 46: 889.9718; Year 51: 634.5376; Year 56: 452.4165; Year 61: 322.5667; Year 66: 229.9856; Year 71: 163.9766; Year 76: 116.913; Year 81: 83.3574; Year 86: 59.4327; Year 91: 42.3747; Year 96: 30.2125; Year 101: 21.5411; Year 106: 15.3585; Year 111: 10.9504; Year 116: 7.8075; Year 121: 5.5666; Year 126: 3.9689; Year 131: 2.8298; Year 136: 2.0176; Year 141: 1.4385; Year 146: 1.0256; Year 151: 0.73127; Year 156: 0.52139; Year 161: 0.37174; Year 166: 0.26505; Year 171: 0.18897; Year 176: 0.13474; Year 181: 0.096065; Year 186: 0.068493; Year 191: 0.048835; Year 196: 0.034818; Year 201: 0.024825; Year 206: 0.0177; Year 211: 0.01262; Year 216: 0.0089978; Year 221: 0.0064153; Year 226: 0.004574; Year 231: 0.0032612; Year 236: 0.0023252; Year 241: 0.0016578; Year 246: 0.001182; Year 251: 0.00084276; Year 256: 0.00060087; Year 261: 0.00042841; Year 266: 0.00030545; Year 271: 0.00021778; Year 276: 0.00015528; Year 281: 0.00011071; Year 286: 7.8935e-05; Year 291: 5.628e-05; Year 296: 4.0127e-05; Year 301: 2.861e-05; Year 306: 2.0398e-05; Year 311: 1.4544e-05; Year 316: 1.0369e-05; Year 321: 7.3933e-06; Year 326: 5.2713e-06; Year 331: 3.7584e-06; Year 336: 2.6797e-06; Year 341: 1.9106e-06; Year 346: 1.3622e-06; Year 351: 9.7123e-07; Year 356: 6.9248e-07; Year 361: 4.9373e-07; Year 366: 3.5202e-07; Year 371: 2.5099e-07; Year 376: 1.7895e-07; Year 381: 1.2759e-07; Year 386: 9.0969e-08; Year 391: 6.4859e-08; Year 396: 4.6244e-08; Year 401: 3.2971e-08; Year 406: 2.3508e-08; Year 411: 1.6761e-08; Year 416: 1.195e-08; Year 421: 8.5204e-09; Year 426: 6.0749e-09; Year 431: 4.3313e-09; Year 436: 3.0882e-09; Year 441: 2.2018e-09; Year 446: 1.5699e-09; Year 451: 1.1193e-09; Year 456: 7.9804e-10; Year 461: 5.69e-10; Year 466: 4.0569e-10; Year 471: 2.8925e-10; Year 476: 2.0623e-10; Year 481: 1.4704e-10; Year 486: 1.0484e-10; Year 491: 7.4747e-11
| Road Closure and Reclamation | 66434.5071 | Year 1: 20200.9296; Year 5: 46233.5775; Year 41: 5396.1031; Year 46: 3847.3469; Year 51: 2743.1052; Year 56: 1955.7961; Year 61: 1394.4556; Year 66: 994.2276; Year 71: 708.8705; Year 76: 505.4149; Year 81: 360.3538; Year 86: 256.9273; Year 91: 183.1856; Year 96: 130.6088; Year 101: 93.1223; Year 106: 66.3949; Year 111: 47.3386; Year 116: 33.7518; Year 121: 24.0646; Year 126: 17.1577; Year 131: 12.2332; Year 136: 8.7221; Year 141: 6.2187; Year 146: 4.4339; Year 151: 3.1613; Year 156: 2.254; Year 161: 1.607; Year 166: 1.1458; Year 171: 0.81694; Year 176: 0.58247; Year 181: 0.41529; Year 186: 0.2961; Year 191: 0.21111; Year 196: 0.15052; Year 201: 0.10732; Year 206: 0.076517; Year 211: 0.054555; Year 216: 0.038897; Year 221: 0.027733; Year 226: 0.019773; Year 231: 0.014098; Year 236: 0.010052; Year 241: 0.0071668; Year 246: 0.0051098; Year 251: 0.0036432; Year 256: 0.0025976; Year 261: 0.001852; Year 266: 0.0013205; Year 271: 0.00094148; Year 276: 0.00067126; Year 281: 0.0004786; Year 286: 0.00034124; Year 291: 0.0002433; Year 296: 0.00017347; Year 301: 0.00012368; Year 306: 8.8182e-05; Year 311: 6.2872e-05; Year 316: 4.4827e-05; Year 321: 3.1961e-05; Year 326: 2.2788e-05; Year 331: 1.6247e-05; Year 336: 1.1584e-05; Year 341: 8.2594e-06; Year 346: 5.8888e-06; Year 351: 4.1986e-06; Year 356: 2.9936e-06; Year 361: 2.1344e-06; Year 366: 1.5218e-06; Year 371: 1.085e-06; Year 376: 7.736e-07; Year 381: 5.5156e-07; Year 386: 3.9326e-07; Year 391: 2.8039e-07; Year 396: 1.9991e-07; Year 401: 1.4253e-07; Year 406: 1.0163e-07; Year 411: 7.2457e-08; Year 416: 5.1661e-08; Year 421: 3.6834e-08; Year 426: 2.6262e-08; Year 431: 1.8724e-08; Year 436: 1.335e-08; Year 441: 9.5185e-09; Year 446: 6.7866e-09; Year 451: 4.8387e-09; Year 456: 3.4499e-09; Year 461: 2.4598e-09; Year 466: 1.7538e-09; Year 471: 1.2504e-09; Year 476: 8.9153e-10; Year 481: 6.3565e-10; Year 486: 4.5321e-10; Year 491: 3.2313e-10
| Total | 3641001.9441 | 814399.0605 | 636529.2282 | 406981.8883 | 513138.4968 | 357380.6708 | 123185.6521 | 345175.5144 | 107595.1194 | 100556.1863 | 236060.1274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44470.8215 | 0 | 0 | 0 | 0 | 31707.0811 | 0 | 0 | 0 | 0 | 22606.7106 | 0 | 0 | 0 | 0 | 16118.2722 | 0 | 0 | 0 | 0 | 11492.1053 | 0 | 0 | 0 | 0 | 8193.7123 | 0 | 0 | 0 | 0 | 5842.0036 | 0 | 0 | 0 | 0 | 4165.2678 | 0 | 0 | 0 | 0 | 2969.7784 | 0 | 0 | 0 | 0 | 2117.411 | 0 | 0 | 0 | 0 | 1509.6847 | 0 | 0 | 0 | 0 | 1076.3844 | 0 | 0 | 0 | 0 | 767.4472 | 0 | 0 | 0 | 0 | 547.1792 | 0 | 0 | 0 | 0 | 390.1312 | 0 | 0 | 0 | 0 | 278.1582 | 0 | 0 | 0 | 0 | 198.3229 | 0 | 0 | 0 | 0 | 141.4015 | 0 | 0 | 0 | 0 | 100.8173 | 0 | 0 | 0 | 0 | 71.8814 | 0 | 0 | 0 | 0 | 51.2504 | 0 | 0 | 0 | 0 | 36.5408 | 0 | 0 | 0 | 0 | 26.0531 | 0 | 0 | 0 | 0 | 18.5755 | 0 | 0 | 0 | 0 | 13.2441 | 0 | 0 | 0 | 0 | 9.4428 | 0 | 0 | 0 | 0 | 6.7326 | 0 | 0 | 0 | 0 | 4.8003 | 0 | 0 | 0 | 0 | 3.4225 | 0 | 0 | 0 | 0 | 2.4402 | 0 | 0 | 0 | 0 | 1.7398 | 0 | 0 | 0 | 0 | 1.2405 | 0 | 0 | 0 | 0 | 0.88444 | 0 | 0 | 0 | 0 | 0.6306 | 0 | 0 | 0 | 0 | 0.44961 | 0 | 0 | 0 | 0 | 0.32056 | 0 | 0 | 0 | 0 | 0.22856 | 0 | 0 | 0 | 0 | 0.16296 | 0 | 0 | 0 | 0 | 0.11619 | 0 | 0 | 0 | 0 | 0.08284 | 0 | 0 | 0 | 0 | 0.059064 | 0 | 0 | 0 | 0 | 0.042112 | 0 | 0 | 0 | 0 | 0.030025 | 0 | 0 | 0 | 0 | 0.021407 | 0 | 0 | 0 | 0 | 0.015263 | 0 | 0 | 0 | 0 | 0.010882 | 0 | 0 | 0 | 0 | 0.007759 | 0 | 0 | 0 | 0 | 0.0055321 | 0 | 0 | 0 | 0 | 0.0039443 | 0 | 0 | 0 | 0 | 0.0028122 | 0 | 0 | 0 | 0 | 0.0020051 | 0 | 0 | 0 | 0 | 0.0014296 | 0 | 0 | 0 | 0 | 0.0010193 | 0 | 0 | 0 | 0 | 0.00072673 | 0 | 0 | 0 | 0 | 0.00051815 | 0 | 0 | 0 | 0 | 0.00036943 | 0 | 0 | 0 | 0 | 0.0002634 | 0 | 0 | 0 | 0 | 0.0001878 | 0 | 0 | 0 | 0 | 0.0001339 | 0 | 0 | 0 | 0 | 9.5469e-05 | 0 | 0 | 0 | 0 | 6.8068e-05 | 0 | 0 | 0 | 0 | 4.8531e-05 | 0 | 0 | 0 | 0 | 3.4602e-05 | 0 | 0 | 0 | 0 | 2.4671e-05 | 0 | 0 | 0 | 0 | 1.759e-05 | 0 | 0 | 0 | 0 | 1.2541e-05 | 0 | 0 | 0 | 0 | 8.9419e-06 | 0 | 0 | 0 | 0 | 6.3754e-06 | 0 | 0 | 0 | 0 | 4.5456e-06 | 0 | 0 | 0 | 0 | 3.2409e-06 | 0 | 0 | 0 | 0 | 2.3108e-06 | 0 | 0 | 0 | 0 | 1.6475e-06 | 0 | 0 | 0 | 0 | 1.1747e-06 | 0 | 0 | 0 | 0 | 8.3752e-07 | 0 | 0 | 0 | 0 | 5.9714e-07 | 0 | 0 | 0 | 0 | 4.2575e-07 | 0 | 0 | 0 | 0 | 3.0356e-07 | 0 | 0 | 0 | 0 | 2.1643e-07 | 0 | 0 | 0 | 0 | 1.5431e-07 | 0 | 0 | 0 | 0 | 1.1002e-07 | 0 | 0 | 0 | 0 | 7.8445e-08 | 0 | 0 | 0 | 0 | 5.593e-08 | 0 | 0 | 0 | 0 | 3.9877e-08 | 0 | 0 | 0 | 0 | 2.8432e-08 | 0 | 0 | 0 | 0 | 2.0272e-08 | 0 | 0 | 0 | 0 | 1.4453e-08 | 0 | 0 | 0 | 0 | 1.0305e-08 | 0 | 0 | 0 | 0 | 7.3474e-09 | 0 | 0 | 0 | 0 | 5.2386e-09 | 0 | 0 | 0 | 0 | 3.735e-09 | 0 | 0 | 0 | 0 | 2.663e-09 | 0

## T19-NPV-YR5
Table 19
NPV-Post Closure Care, Maintenance, and Monitoring
| Full Annual Cost/Cost Rate |  |  | Discount Rate |  |  | 7%
| Task | Cost | Units | Number of PC years to include |  |  | 10 |  | *Enter the number of years AFTER transitional closure is complete
| Active Treatment System | 0 | an
| Passive Treatment System | 10525.95 | an
| Field Support Staff & Vehicles | 32001.375 | an
| Project Management | 105120 | an
| Camp and General | 26229 | an
| Reclamation Maintenance | 60887.2098 | an
| Site Maintenance | 17805.6 | an
| Transportation Costs | 64307.5 | an
| Water Quality Monitoring | 0 | ea
| Physical/Geotech Stability Monitoring | 0 | ea
| Surface Water Monitoring | 20069 | ea
| Groundwater Monitoring | 54889 | ea
| Revegetation Success | 86663 | ea
| Soil and Vegetation Chemistry | 157466 | ea
| Wildlife Aerial Surveys | 103824 | ea
| Aquatics | 21455 | ea
| Effluent | 0 | ea
| Instrumentation Maintenance/Replacement | 20000 | an
| Road Closure and Reclamation | 85949.825 | an
| Implementation Schedule |  | Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Active Treatment System
| Passive Treatment System |  | Year 11: 1; Year 12: 1; Year 13: 1; Year 14: 1; Year 15: 0.5; Year 16: 0.5; Year 17: 0.25; Year 18: 0.25; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Field Support Staff & Vehicles |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 1; Year 7: 1; Year 8: 1; Year 9: 0.5; Year 10: 0.5; Year 11: 0.5; Year 12: 0.5; Year 13: 0.5; Year 14: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Project Management |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 1; Year 7: 1; Year 8: 1; Year 9: 0.5; Year 10: 0.5; Year 11: 0.5; Year 12: 0.5; Year 13: 0.5; Year 14: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Camp and General |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 1; Year 7: 1; Year 8: 1; Year 9: 0.5; Year 10: 0.5; Year 11: 0.5; Year 12: 0.5; Year 13: 0.5; Year 14: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Reclamation Maintenance |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.25; Year 10: 0.25; Year 11: 0.25; Year 12: 0.25; Year 13: 0.25; Year 14: 0.25; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Site Maintenance |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 1; Year 7: 1; Year 8: 1; Year 9: 0.5; Year 10: 0.5; Year 11: 0.5; Year 12: 0.5; Year 13: 0.5; Year 14: 0.5; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Transportation Costs |  | Year 3: 1; Year 4: 1; Year 5: 1; Year 6: 0.5; Year 7: 0.5; Year 8: 0.5; Year 9: 0.25; Year 10: 0.25; Year 11: 0.25; Year 12: 0.25; Year 13: 0.25; Year 14: 0.25; Year 15: 0; Year 16: 0; Year 17: 0; Year 18: 0; Year 19: 0; Year 20: 0; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
Water Quality Monitoring | bar: Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Physical/Geotech Stability Monitoring | bar: Year 2 to Year 6; Year 8; Year 10; Year 13; Year 17; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
| Surface Water Monitoring |  | Year 1: 12; Year 2: 12; Year 3: 12; Year 4: 12; Year 5: 6; Year 6: 6; Year 7: 6; Year 8: 6; Year 9: 4; Year 10: 4; Year 11: 2; Year 12: 2; Year 13: 2; Year 14: 2; Year 15: 1; Year 16: 1; Year 17: 1; Year 18: 1; Year 19: 1; Year 20: 1; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Groundwater Monitoring |  | Year 1: 4; Year 2: 4; Year 3: 4; Year 4: 4; Year 5: 2; Year 6: 2; Year 7: 2; Year 8: 2; Year 9: 2; Year 10: 2; Year 11: 1; Year 12: 1; Year 13: 1; Year 14: 1; Year 15: 1; Year 16: 1; Year 17: 1; Year 18: 1; Year 19: 1; Year 20: 1; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
Revegetation Success | bar: Year 1 to Year 5; Year 8; Year 11; Year 15; Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Soil and Vegetation Chemistry | bar: Year 2; Year 5; Year 8; Year 11; Year 15; Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Wildlife Aerial Surveys | bar: Year 1 to Year 2; Year 5; Year 8; Year 11; Year 15; Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Aquatics | bar: Year 1 to Year 2; Year 5; Year 8; Year 11; Year 15; Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Effluent | bar: Year 1 to Year 2; Year 5; Year 8; Year 11; Year 15; Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
Instrumentation Maintenance/Replacement | bar: Year 1 to Year 20; Year 41; Year 46; Year 51; Year 56; Year 61; Year 66; Year 71; Year 76; Year 81; Year 86; Year 91; Year 96; Year 101; Year 106; Year 111; Year 116; Year 121; Year 126; Year 131; Year 136; Year 141; Year 146; Year 151; Year 156; Year 161; Year 166; Year 171; Year 176; Year 181; Year 186; Year 191; Year 196; Year 201; Year 206; Year 211; Year 216; Year 221; Year 226; Year 231; Year 236; Year 241; Year 246; Year 251; Year 256; Year 261; Year 266; Year 271; Year 276; Year 281; Year 286; Year 291; Year 296; Year 301; Year 306; Year 311; Year 316; Year 321; Year 326; Year 331; Year 336; Year 341; Year 346; Year 351; Year 356; Year 361; Year 366; Year 371; Year 376; Year 381; Year 386; Year 391; Year 396; Year 401; Year 406; Year 411; Year 416; Year 421; Year 426; Year 431; Year 436; Year 441; Year 446; Year 451; Year 456; Year 461; Year 466; Year 471; Year 476; Year 481; Year 486; Year 491
| Road Closure and Reclamation |  | Year 2: 0.25; Year 10: 0.75; Year 41: 1; Year 46: 1; Year 51: 1; Year 56: 1; Year 61: 1; Year 66: 1; Year 71: 1; Year 76: 1; Year 81: 1; Year 86: 1; Year 91: 1; Year 96: 1; Year 101: 1; Year 106: 1; Year 111: 1; Year 116: 1; Year 121: 1; Year 126: 1; Year 131: 1; Year 136: 1; Year 141: 1; Year 146: 1; Year 151: 1; Year 156: 1; Year 161: 1; Year 166: 1; Year 171: 1; Year 176: 1; Year 181: 1; Year 186: 1; Year 191: 1; Year 196: 1; Year 201: 1; Year 206: 1; Year 211: 1; Year 216: 1; Year 221: 1; Year 226: 1; Year 231: 1; Year 236: 1; Year 241: 1; Year 246: 1; Year 251: 1; Year 256: 1; Year 261: 1; Year 266: 1; Year 271: 1; Year 276: 1; Year 281: 1; Year 286: 1; Year 291: 1; Year 296: 1; Year 301: 1; Year 306: 1; Year 311: 1; Year 316: 1; Year 321: 1; Year 326: 1; Year 331: 1; Year 336: 1; Year 341: 1; Year 346: 1; Year 351: 1; Year 356: 1; Year 361: 1; Year 366: 1; Year 371: 1; Year 376: 1; Year 381: 1; Year 386: 1; Year 391: 1; Year 396: 1; Year 401: 1; Year 406: 1; Year 411: 1; Year 416: 1; Year 421: 1; Year 426: 1; Year 431: 1; Year 436: 1; Year 441: 1; Year 446: 1; Year 451: 1; Year 456: 1; Year 461: 1; Year 466: 1; Year 471: 1; Year 476: 1; Year 481: 1; Year 486: 1; Year 491: 1
| Undiscounted Cost |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 57892.725
| Active Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Passive Treatment System | 57892.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525.95 | 10525.95 | 10525.95 | 10525.95 | 5262.975 | 5262.975 | 2631.4875 | 2631.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0
Staff/Equipment | 1470153.375
| Field Support Staff & Vehicles | 288012.375 | 0 | 0 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0
| Project Management | 946080 | 0 | 0 | 105120 | 105120 | 105120 | 105120 | 105120 | 105120 | 52560 | 52560 | 52560 | 52560 | 52560 | 52560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0
| Camp and General | 236061 | 0 | 0 | 26229 | 26229 | 26229 | 26229 | 26229 | 26229 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0
Maintenance | 525573.6588
| Reclamation Maintenance | 365323.2588 | 0 | 0 | 60887.2098 | 60887.2098 | 60887.2098 | 30443.6049 | 30443.6049 | 30443.6049 | 15221.8025 | 15221.8025 | 15221.8025 | 15221.8025 | 15221.8025 | 15221.8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0 | 0 | 0 | 0 | 60887.2098 | 0
| Site Maintenance | 160250.4 | 0 | 0 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0
Transportation | 385845
| Transportation Costs | 385845 | 0 | 0 | 64307.5 | 64307.5 | 64307.5 | 32153.75 | 32153.75 | 32153.75 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0
Monitoring | 7059933.825
| Water Quality Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Physical/Geotech Stability Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surface Water Monitoring | 1886486 | 240828 | 240828 | 240828 | 240828 | 120414 | 120414 | 120414 | 120414 | 80276 | 80276 | 40138 | 40138 | 40138 | 40138 | 20069 | 20069 | 20069 | 20069 | 20069 | 20069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0
| Groundwater Monitoring | 2085782 | 219556 | 219556 | 219556 | 219556 | 109778 | 109778 | 109778 | 109778 | 109778 | 109778 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0
| Revegetation Success | 779967 | 86663 | 86663 | 86663 | 86663 | 86663 | 0 | 0 | 86663 | 0 | 0 | 86663 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0
| Soil and Vegetation Chemistry | 944796 | 0 | 157466 | 0 | 0 | 157466 | 0 | 0 | 157466 | 0 | 0 | 157466 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0
| Wildlife Aerial Surveys | 726768 | 103824 | 103824 | 0 | 0 | 103824 | 0 | 0 | 103824 | 0 | 0 | 103824 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0
| Aquatics | 150185 | 21455 | 21455 | 0 | 0 | 21455 | 0 | 0 | 21455 | 0 | 0 | 21455 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0
| Effluent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instrumentation Maintenance/Replacement | 400000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0
| Road Closure and Reclamation | 85949.825 | 0 | 21487.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64462.3687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0 | 0 | 0 | 0 | 85949.825 | 0
| Total | 9499398.5838 | 692326 | 871279.4563 | 873397.6848 | 873397.6848 | 925950.6848 | 493945.3299 | 493945.3299 | 863353.3299 | 331930.665 | 396393.0337 | 616837.615 | 247429.615 | 247429.615 | 247429.615 | 469628.975 | 100220.975 | 97589.4875 | 97589.4875 | 94958 | 464366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0 | 0 | 0 | 0 | 867192.4598 | 0
| NPV |  | Year 1: Year
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 23426.4104
| Active Treatment System | 0
| Passive Treatment System | 23426.4104 | Year 11: 5000.803; Year 12: 4673.6477; Year 13: 4367.895; Year 14: 4082.1449; Year 15: 1907.5443; Year 16: 1782.7517; Year 17: 833.0616; Year 18: 778.5622; Year 41: 656.9411; Year 46: 468.3899; Year 51: 333.9555; Year 56: 238.1057; Year 61: 169.7661; Year 66: 121.0409; Year 71: 86.3005; Year 76: 61.531; Year 81: 43.8708; Year 86: 31.2793; Year 91: 22.3017; Year 96: 15.9008; Year 101: 11.337; Year 106: 8.0832; Year 111: 5.7632; Year 116: 4.1091; Year 121: 2.9297; Year 126: 2.0888; Year 131: 1.4893; Year 136: 1.0619; Year 141: 0.75709; Year 146: 0.5398; Year 151: 0.38487; Year 156: 0.2744; Year 161: 0.19565; Year 166: 0.13949; Year 171: 0.099457; Year 176: 0.070911; Year 181: 0.050559; Year 186: 0.036048; Year 191: 0.025702; Year 196: 0.018325; Year 201: 0.013065; Year 206: 0.0093154; Year 211: 0.0066418; Year 216: 0.0047355; Year 221: 0.0033763; Year 226: 0.0024073; Year 231: 0.0017164; Year 236: 0.0012237; Year 241: 0.00087251; Year 246: 0.00062209; Year 251: 0.00044354; Year 256: 0.00031624; Year 261: 0.00022547; Year 266: 0.00016076; Year 271: 0.00011462; Year 276: 8.1722e-05; Year 281: 5.8267e-05; Year 286: 4.1543e-05; Year 291: 2.962e-05; Year 296: 2.1119e-05; Year 301: 1.5057e-05; Year 306: 1.0736e-05; Year 311: 7.6543e-06; Year 316: 5.4574e-06; Year 321: 3.8911e-06; Year 326: 2.7743e-06; Year 331: 1.978e-06; Year 336: 1.4103e-06; Year 341: 1.0055e-06; Year 346: 7.1693e-07; Year 351: 5.1116e-07; Year 356: 3.6445e-07; Year 361: 2.5985e-07; Year 366: 1.8527e-07; Year 371: 1.3209e-07; Year 376: 9.418e-08; Year 381: 6.7149e-08; Year 386: 4.7877e-08; Year 391: 3.4135e-08; Year 396: 2.4338e-08; Year 401: 1.7353e-08; Year 406: 1.2372e-08; Year 411: 8.8212e-09; Year 416: 6.2894e-09; Year 421: 4.4843e-09; Year 426: 3.1972e-09; Year 431: 2.2796e-09; Year 436: 1.6253e-09; Year 441: 1.1588e-09; Year 446: 8.2622e-10; Year 451: 5.8908e-10; Year 456: 4.2001e-10; Year 461: 2.9946e-10; Year 466: 2.1351e-10; Year 471: 1.5223e-10; Year 476: 1.0854e-10; Year 481: 7.7386e-11; Year 486: 5.5175e-11; Year 491: 3.9339e-11
Staff/Equipment | 906654.2169
| Field Support Staff & Vehicles | 177619.3143 | Year 3: 26122.6545; Year 4: 24413.6958; Year 5: 22816.5381; Year 6: 21323.8674; Year 7: 19928.848; Year 8: 18625.0916; Year 9: 8703.3138; Year 10: 8133.9382; Year 11: 7601.8114; Year 12: 7104.4966; Year 13: 6639.7165; Year 14: 6205.3425; Year 41: 1997.2561; Year 46: 1424.016; Year 51: 1015.3037; Year 56: 723.8975; Year 61: 516.1289; Year 66: 367.9928; Year 71: 262.3738; Year 76: 187.0689; Year 81: 133.3775; Year 86: 95.0963; Year 91: 67.8024; Year 96: 48.3422; Year 101: 34.4673; Year 106: 24.5747; Year 111: 17.5214; Year 116: 12.4925; Year 121: 8.907; Year 126: 6.3506; Year 131: 4.5279; Year 136: 3.2283; Year 141: 2.3017; Year 146: 1.6411; Year 151: 1.1701; Year 156: 0.83426; Year 161: 0.59481; Year 166: 0.42409; Year 171: 0.30237; Year 176: 0.21559; Year 181: 0.15371; Year 186: 0.10959; Year 191: 0.078139; Year 196: 0.055712; Year 201: 0.039722; Year 206: 0.028321; Year 211: 0.020193; Year 216: 0.014397; Year 221: 0.010265; Year 226: 0.0073187; Year 231: 0.0052181; Year 236: 0.0037205; Year 241: 0.0026526; Year 246: 0.0018913; Year 251: 0.0013485; Year 256: 0.00096144; Year 261: 0.00068549; Year 266: 0.00048875; Year 271: 0.00034847; Year 276: 0.00024845; Year 281: 0.00017714; Year 286: 0.0001263; Year 291: 9.0051e-05; Year 296: 6.4205e-05; Year 301: 4.5777e-05; Year 306: 3.2639e-05; Year 311: 2.3271e-05; Year 316: 1.6592e-05; Year 321: 1.183e-05; Year 326: 8.4345e-06; Year 331: 6.0137e-06; Year 336: 4.2877e-06; Year 341: 3.057e-06; Year 346: 2.1796e-06; Year 351: 1.554e-06; Year 356: 1.108e-06; Year 361: 7.9e-07; Year 366: 5.6326e-07; Year 371: 4.0159e-07; Year 376: 2.8633e-07; Year 381: 2.0415e-07; Year 386: 1.4556e-07; Year 391: 1.0378e-07; Year 396: 7.3993e-08; Year 401: 5.2756e-08; Year 406: 3.7614e-08; Year 411: 2.6819e-08; Year 416: 1.9121e-08; Year 421: 1.3633e-08; Year 426: 9.7203e-09; Year 431: 6.9304e-09; Year 436: 4.9413e-09; Year 441: 3.5231e-09; Year 446: 2.5119e-09; Year 451: 1.791e-09; Year 456: 1.2769e-09; Year 461: 9.1043e-10; Year 466: 6.4912e-10; Year 471: 4.6282e-10; Year 476: 3.2998e-10; Year 481: 2.3527e-10; Year 486: 1.6775e-10; Year 491: 1.196e-10
| Project Management | 583454.377 | Year 3: 85809.2328; Year 4: 80195.5447; Year 5: 74949.1072; Year 6: 70045.8946; Year 7: 65463.4529; Year 8: 61180.7971; Year 9: 28589.1575; Year 10: 26718.8388; Year 11: 24970.8774; Year 12: 23337.2686; Year 13: 21810.5314; Year 14: 20383.6742; Year 41: 6560.7043; Year 46: 4677.6915; Year 51: 3335.1294; Year 56: 2377.9012; Year 61: 1695.4107; Year 66: 1208.8044; Year 71: 861.8608; Year 76: 614.4949; Year 81: 438.1263; Year 86: 312.378; Year 91: 222.7212; Year 96: 158.7971; Year 101: 113.2202; Year 106: 80.7244; Year 111: 57.5554; Year 116: 41.0362; Year 121: 29.2582; Year 126: 20.8607; Year 131: 14.8734; Year 136: 10.6045; Year 141: 7.5609; Year 146: 5.3908; Year 151: 3.8436; Year 156: 2.7404; Year 161: 1.9539; Year 166: 1.3931; Year 171: 0.99325; Year 176: 0.70817; Year 181: 0.50492; Year 186: 0.36; Year 191: 0.25668; Year 196: 0.18301; Year 201: 0.13048; Year 206: 0.093031; Year 211: 0.06633; Year 216: 0.047292; Year 221: 0.033719; Year 226: 0.024041; Year 231: 0.017141; Year 236: 0.012221; Year 241: 0.0087135; Year 246: 0.0062126; Year 251: 0.0044295; Year 256: 0.0031582; Year 261: 0.0022517; Year 266: 0.0016055; Year 271: 0.0011447; Year 276: 0.00081614; Year 281: 0.00058189; Year 286: 0.00041488; Year 291: 0.00029581; Year 296: 0.00021091; Year 301: 0.00015037; Year 306: 0.00010721; Year 311: 7.6442e-05; Year 316: 5.4502e-05; Year 321: 3.8859e-05; Year 326: 2.7706e-05; Year 331: 1.9754e-05; Year 336: 1.4084e-05; Year 341: 1.0042e-05; Year 346: 7.1598e-06; Year 351: 5.1048e-06; Year 356: 3.6397e-06; Year 361: 2.595e-06; Year 366: 1.8502e-06; Year 371: 1.3192e-06; Year 376: 9.4056e-07; Year 381: 6.706e-07; Year 386: 4.7813e-07; Year 391: 3.409e-07; Year 396: 2.4306e-07; Year 401: 1.733e-07; Year 406: 1.2356e-07; Year 411: 8.8095e-08; Year 416: 6.2811e-08; Year 421: 4.4783e-08; Year 426: 3.193e-08; Year 431: 2.2765e-08; Year 436: 1.6231e-08; Year 441: 1.1573e-08; Year 446: 8.2513e-09; Year 451: 5.883e-09; Year 456: 4.1945e-09; Year 461: 2.9906e-09; Year 466: 2.1323e-09; Year 471: 1.5203e-09; Year 476: 1.0839e-09; Year 481: 7.7284e-10; Year 486: 5.5102e-10; Year 491: 3.9287e-10
| Camp and General | 145580.5256 | Year 3: 21410.677; Year 4: 20009.9785; Year 5: 18700.9145; Year 6: 17477.4902; Year 7: 16334.103; Year 8: 15265.5168; Year 9: 7133.4191; Year 10: 6666.7468; Year 11: 6230.6045; Year 12: 5822.9948; Year 13: 5442.0513; Year 14: 5086.0292; Year 41: 1636.9931; Year 46: 1167.1535; Year 51: 832.1643; Year 56: 593.3216; Year 61: 423.0301; Year 66: 301.6146; Year 71: 215.0471; Year 76: 153.3256; Year 81: 109.319; Year 86: 77.943; Year 91: 55.5722; Year 96: 39.6222; Year 101: 28.2501; Year 106: 20.1419; Year 111: 14.3609; Year 116: 10.2391; Year 121: 7.3004; Year 126: 5.2051; Year 131: 3.7111; Year 136: 2.646; Year 141: 1.8866; Year 146: 1.3451; Year 151: 0.95903; Year 156: 0.68377; Year 161: 0.48752; Year 166: 0.3476; Year 171: 0.24783; Year 176: 0.1767; Year 181: 0.12598; Year 186: 0.089825; Year 191: 0.064044; Year 196: 0.045663; Year 201: 0.032557; Year 206: 0.023213; Year 211: 0.01655; Year 216: 0.0118; Year 221: 0.0084133; Year 226: 0.0059986; Year 231: 0.0042769; Year 236: 0.0030494; Year 241: 0.0021742; Year 246: 0.0015501; Year 251: 0.0011052; Year 256: 0.00078802; Year 261: 0.00056184; Year 266: 0.00040059; Year 271: 0.00028561; Year 276: 0.00020364; Year 281: 0.00014519; Year 286: 0.00010352; Year 291: 7.3808e-05; Year 296: 5.2624e-05; Year 301: 3.752e-05; Year 306: 2.6751e-05; Year 311: 1.9073e-05; Year 316: 1.3599e-05; Year 321: 9.6959e-06; Year 326: 6.9131e-06; Year 331: 4.9289e-06; Year 336: 3.5142e-06; Year 341: 2.5056e-06; Year 346: 1.7865e-06; Year 351: 1.2737e-06; Year 356: 9.0815e-07; Year 361: 6.475e-07; Year 366: 4.6166e-07; Year 371: 3.2915e-07; Year 376: 2.3468e-07; Year 381: 1.6733e-07; Year 386: 1.193e-07; Year 391: 8.506e-08; Year 396: 6.0647e-08; Year 401: 4.324e-08; Year 406: 3.083e-08; Year 411: 2.1981e-08; Year 416: 1.5672e-08; Year 421: 1.1174e-08; Year 426: 7.967e-09; Year 431: 5.6803e-09; Year 436: 4.05e-09; Year 441: 2.8876e-09; Year 446: 2.0588e-09; Year 451: 1.4679e-09; Year 456: 1.0466e-09; Year 461: 7.4621e-10; Year 466: 5.3204e-10; Year 471: 3.7933e-10; Year 476: 2.7046e-10; Year 481: 1.9283e-10; Year 486: 1.3749e-10; Year 491: 9.8027e-11
Maintenance | 337582.902
| Reclamation Maintenance | 238755.3215 | Year 3: 49702.1001; Year 4: 46450.5608; Year 5: 43411.7391; Year 6: 20285.8594; Year 7: 18958.7471; Year 8: 17718.4552; Year 9: 8279.652; Year 10: 7737.9925; Year 11: 7231.7687; Year 12: 6758.6623; Year 13: 6316.5069; Year 14: 5903.2774; Year 41: 3800.0664; Year 46: 2709.3948; Year 51: 1931.7611; Year 56: 1377.3189; Year 61: 982.0094; Year 66: 700.1591; Year 71: 499.2038; Year 76: 355.9254; Year 81: 253.7699; Year 86: 180.9344; Year 91: 129.0037; Year 96: 91.9779; Year 101: 65.579; Year 106: 46.7569; Year 111: 33.337; Year 116: 23.7688; Year 121: 16.9468; Year 126: 12.0829; Year 131: 8.6149; Year 136: 6.1423; Year 141: 4.3794; Year 146: 3.1224; Year 151: 2.2263; Year 156: 1.5873; Year 161: 1.1317; Year 166: 0.8069; Year 171: 0.57531; Year 176: 0.41019; Year 181: 0.29246; Year 186: 0.20852; Year 191: 0.14867; Year 196: 0.106; Year 201: 0.075576; Year 206: 0.053885; Year 211: 0.038419; Year 216: 0.027392; Year 221: 0.01953; Year 226: 0.013925; Year 231: 0.0099283; Year 236: 0.0070787; Year 241: 0.005047; Year 246: 0.0035985; Year 251: 0.0025657; Year 256: 0.0018293; Year 261: 0.0013042; Year 266: 0.00092991; Year 271: 0.00066301; Year 276: 0.00047272; Year 281: 0.00033704; Year 286: 0.00024031; Year 291: 0.00017134; Year 296: 0.00012216; Year 301: 8.7098e-05; Year 306: 6.21e-05; Year 311: 4.4276e-05; Year 316: 3.1568e-05; Year 321: 2.2508e-05; Year 326: 1.6048e-05; Year 331: 1.1442e-05; Year 336: 8.1579e-06; Year 341: 5.8164e-06; Year 346: 4.147e-06; Year 351: 2.9568e-06; Year 356: 2.1081e-06; Year 361: 1.5031e-06; Year 366: 1.0717e-06; Year 371: 7.6409e-07; Year 376: 5.4479e-07; Year 381: 3.8842e-07; Year 386: 2.7694e-07; Year 391: 1.9746e-07; Year 396: 1.4078e-07; Year 401: 1.0038e-07; Year 406: 7.1567e-08; Year 411: 5.1026e-08; Year 416: 3.6381e-08; Year 421: 2.5939e-08; Year 426: 1.8494e-08; Year 431: 1.3186e-08; Year 436: 9.4015e-09; Year 441: 6.7032e-09; Year 446: 4.7793e-09; Year 451: 3.4076e-09; Year 456: 2.4295e-09; Year 461: 1.7322e-09; Year 466: 1.2351e-09; Year 471: 8.8058e-10; Year 476: 6.2784e-10; Year 481: 4.4764e-10; Year 486: 3.1916e-10; Year 491: 2.2756e-10
| Site Maintenance | 98827.5804 | Year 3: 14534.6735; Year 4: 13583.807; Year 5: 12695.1467; Year 6: 11864.6231; Year 7: 11088.4328; Year 8: 10363.0213; Year 9: 4842.5333; Year 10: 4525.7321; Year 11: 4229.6561; Year 12: 3952.9497; Year 13: 3694.3455; Year 14: 3452.6593; Year 41: 1111.2755; Year 46: 792.3241; Year 51: 564.9161; Year 56: 402.7774; Year 61: 287.1747; Year 66: 204.7516; Year 71: 145.9851; Year 76: 104.0853; Year 81: 74.2114; Year 86: 52.9117; Year 91: 37.7253; Year 96: 26.8976; Year 101: 19.1776; Year 106: 13.6734; Year 111: 9.7489; Year 116: 6.9509; Year 121: 4.9559; Year 126: 3.5335; Year 131: 2.5193; Year 136: 1.7962; Year 141: 1.2807; Year 146: 0.91311; Year 151: 0.65104; Year 156: 0.46418; Year 161: 0.33095; Year 166: 0.23597; Year 171: 0.16824; Year 176: 0.11995; Year 181: 0.085525; Year 186: 0.060978; Year 191: 0.043477; Year 196: 0.030998; Year 201: 0.022101; Year 206: 0.015758; Year 211: 0.011235; Year 216: 0.0080105; Year 221: 0.0057114; Year 226: 0.0040721; Year 231: 0.0029034; Year 236: 0.0020701; Year 241: 0.0014759; Year 246: 0.0010523; Year 251: 0.00075029; Year 256: 0.00053495; Year 261: 0.00038141; Year 266: 0.00027194; Year 271: 0.00019389; Year 276: 0.00013824; Year 281: 9.8563e-05; Year 286: 7.0274e-05; Year 291: 5.0105e-05; Year 296: 3.5724e-05; Year 301: 2.5471e-05; Year 306: 1.816e-05; Year 311: 1.2948e-05; Year 316: 9.2317e-06; Year 321: 6.5821e-06; Year 326: 4.6929e-06; Year 331: 3.346e-06; Year 336: 2.3857e-06; Year 341: 1.7009e-06; Year 346: 1.2127e-06; Year 351: 8.6467e-07; Year 356: 6.165e-07; Year 361: 4.3955e-07; Year 366: 3.134e-07; Year 371: 2.2345e-07; Year 376: 1.5931e-07; Year 381: 1.1359e-07; Year 386: 8.0988e-08; Year 391: 5.7743e-08; Year 396: 4.117e-08; Year 401: 2.9354e-08; Year 406: 2.0929e-08; Year 411: 1.4922e-08; Year 416: 1.0639e-08; Year 421: 7.5855e-09; Year 426: 5.4084e-09; Year 431: 3.8561e-09; Year 436: 2.7493e-09; Year 441: 1.9602e-09; Year 446: 1.3976e-09; Year 451: 9.9649e-10; Year 456: 7.1048e-10; Year 461: 5.0656e-10; Year 466: 3.6117e-10; Year 471: 2.5751e-10; Year 476: 1.836e-10; Year 481: 1.3091e-10; Year 486: 9.3334e-11; Year 491: 6.6546e-11
Transportation | 252167.2103
| Transportation Costs | 252167.2103 | Year 3: 52494.0757; Year 4: 49059.8838; Year 5: 45850.3587; Year 6: 21425.4013; Year 7: 20023.7395; Year 8: 18713.7752; Year 9: 8744.7548; Year 10: 8172.668; Year 11: 7638.0075; Year 12: 7138.3248; Year 13: 6671.3316; Year 14: 6234.8893; Year 15: 0; Year 16: 0; Year 17: 0; Year 18: 0; Year 19: 0; Year 20: 0; Year 41: 4013.5321; Year 46: 2861.5929; Year 51: 2040.2762; Year 56: 1454.6887; Year 61: 1037.173; Year 66: 739.49; Year 71: 527.2461; Year 76: 375.9192; Year 81: 268.0252; Year 86: 191.0983; Year 91: 136.2504; Year 96: 97.1447; Year 101: 69.2628; Year 106: 49.3834; Year 111: 35.2097; Year 116: 25.104; Year 121: 17.8988; Year 126: 12.7616; Year 131: 9.0989; Year 136: 6.4874; Year 141: 4.6254; Year 146: 3.2978; Year 151: 2.3513; Year 156: 1.6765; Year 161: 1.1953; Year 166: 0.85223; Year 171: 0.60763; Year 176: 0.43323; Year 181: 0.30889; Year 186: 0.22023; Year 191: 0.15702; Year 196: 0.11195; Year 201: 0.079822; Year 206: 0.056912; Year 211: 0.040577; Year 216: 0.028931; Year 221: 0.020628; Year 226: 0.014707; Year 231: 0.010486; Year 236: 0.0074764; Year 241: 0.0053305; Year 246: 0.0038006; Year 251: 0.0027098; Year 256: 0.001932; Year 261: 0.0013775; Year 266: 0.00098215; Year 271: 0.00070026; Year 276: 0.00049927; Year 281: 0.00035598; Year 286: 0.00025381; Year 291: 0.00018096; Year 296: 0.00012902; Year 301: 9.1991e-05; Year 306: 6.5588e-05; Year 311: 4.6763e-05; Year 316: 3.3342e-05; Year 321: 2.3772e-05; Year 326: 1.6949e-05; Year 331: 1.2085e-05; Year 336: 8.6161e-06; Year 341: 6.1432e-06; Year 346: 4.38e-06; Year 351: 3.1229e-06; Year 356: 2.2266e-06; Year 361: 1.5875e-06; Year 366: 1.1319e-06; Year 371: 8.0701e-07; Year 376: 5.7539e-07; Year 381: 4.1024e-07; Year 386: 2.925e-07; Year 391: 2.0855e-07; Year 396: 1.4869e-07; Year 401: 1.0601e-07; Year 406: 7.5587e-08; Year 411: 5.3893e-08; Year 416: 3.8425e-08; Year 421: 2.7396e-08; Year 426: 1.9533e-08; Year 431: 1.3927e-08; Year 436: 9.9297e-09; Year 441: 7.0797e-09; Year 446: 5.0477e-09; Year 451: 3.599e-09; Year 456: 2.566e-09; Year 461: 1.8295e-09; Year 466: 1.3044e-09; Year 471: 9.3004e-10; Year 476: 6.6311e-10; Year 481: 4.7279e-10; Year 486: 3.3709e-10; Year 491: 2.4034e-10
Monitoring | 4460678.0775
| Water Quality Monitoring | 0 | Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Physical/Geotech Stability Monitoring | 0 | Year 2: 0; Year 3: 0; Year 4: 0; Year 5: 0; Year 6: 0; Year 8: 0; Year 10: 0; Year 13: 0; Year 17: 0; Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Surface Water Monitoring | 1317580.2205 | Year 1: 225072.8972; Year 2: 210348.5021; Year 3: 196587.3851; Year 4: 183726.5281; Year 5: 85853.5178; Year 6: 80236.9325; Year 7: 74987.7874; Year 8: 70082.0443; Year 9: 43664.8251; Year 10: 40808.2478; Year 11: 19069.2747; Year 12: 17821.752; Year 13: 16655.843; Year 14: 15566.2084; Year 15: 7273.9292; Year 16: 6798.0646; Year 17: 6353.3314; Year 18: 5937.6929; Year 19: 5549.2457; Year 20: 5186.211; Year 41: 1252.5378; Year 46: 893.0422; Year 51: 636.7267; Year 56: 453.9773; Year 61: 323.6796; Year 66: 230.7791; Year 71: 164.5423; Year 76: 117.3164; Year 81: 83.645; Year 86: 59.6377; Year 91: 42.5209; Year 96: 30.3168; Year 101: 21.6154; Year 106: 15.4115; Year 111: 10.9882; Year 116: 7.8344; Year 121: 5.5858; Year 126: 3.9826; Year 131: 2.8396; Year 136: 2.0246; Year 141: 1.4435; Year 146: 1.0292; Year 151: 0.7338; Year 156: 0.52319; Year 161: 0.37302; Year 166: 0.26596; Year 171: 0.18963; Year 176: 0.1352; Year 181: 0.096397; Year 186: 0.068729; Year 191: 0.049003; Year 196: 0.034939; Year 201: 0.024911; Year 206: 0.017761; Year 211: 0.012663; Year 216: 0.0090288; Year 221: 0.0064374; Year 226: 0.0045898; Year 231: 0.0032725; Year 236: 0.0023332; Year 241: 0.0016635; Year 246: 0.0011861; Year 251: 0.00084566; Year 256: 0.00060295; Year 261: 0.00042989; Year 266: 0.00030651; Year 271: 0.00021854; Year 276: 0.00015581; Year 281: 0.00011109; Year 286: 7.9207e-05; Year 291: 5.6474e-05; Year 296: 4.0265e-05; Year 301: 2.8708e-05; Year 306: 2.0469e-05; Year 311: 1.4594e-05; Year 316: 1.0405e-05; Year 321: 7.4188e-06; Year 326: 5.2895e-06; Year 331: 3.7713e-06; Year 336: 2.6889e-06; Year 341: 1.9172e-06; Year 346: 1.3669e-06; Year 351: 9.7459e-07; Year 356: 6.9487e-07; Year 361: 4.9543e-07; Year 366: 3.5323e-07; Year 371: 2.5185e-07; Year 376: 1.7957e-07; Year 381: 1.2803e-07; Year 386: 9.1283e-08; Year 391: 6.5083e-08; Year 396: 4.6403e-08; Year 401: 3.3085e-08; Year 406: 2.3589e-08; Year 411: 1.6819e-08; Year 416: 1.1992e-08; Year 421: 8.5498e-09; Year 426: 6.0959e-09; Year 431: 4.3463e-09; Year 436: 3.0988e-09; Year 441: 2.2094e-09; Year 446: 1.5753e-09; Year 451: 1.1232e-09; Year 456: 8.008e-10; Year 461: 5.7096e-10; Year 466: 4.0709e-10; Year 471: 2.9025e-10; Year 476: 2.0694e-10; Year 481: 1.4755e-10; Year 486: 1.052e-10; Year 491: 7.5005e-11
| Groundwater Monitoring | 1338853.4924 | Year 1: 205192.5234; Year 2: 191768.7134; Year 3: 179223.0967; Year 4: 167498.2212; Year 5: 78270.1968; Year 6: 73149.7166; Year 7: 68364.2212; Year 8: 63891.7955; Year 9: 59711.9584; Year 10: 55805.5686; Year 11: 26077.3685; Year 12: 24371.3724; Year 13: 22776.9836; Year 14: 21286.9005; Year 15: 19894.2996; Year 16: 18592.8033; Year 17: 17376.4517; Year 18: 16239.6745; Year 19: 15177.2659; Year 20: 14184.3606; Year 41: 3425.7087; Year 46: 2442.483; Year 51: 1741.4566; Year 56: 1241.6345; Year 61: 885.2682; Year 66: 631.184; Year 71: 450.0255; Year 76: 320.8619; Year 81: 228.7701; Year 86: 163.1099; Year 91: 116.2951; Year 96: 82.9168; Year 101: 59.1185; Year 106: 42.1507; Year 111: 30.0529; Year 116: 21.4273; Year 121: 15.2774; Year 126: 10.8925; Year 131: 7.7662; Year 136: 5.5372; Year 141: 3.948; Year 146: 2.8148; Year 151: 2.0069; Year 156: 1.4309; Year 161: 1.0202; Year 166: 0.72741; Year 171: 0.51863; Year 176: 0.36978; Year 181: 0.26365; Year 186: 0.18798; Year 191: 0.13402; Year 196: 0.095558; Year 201: 0.068131; Year 206: 0.048577; Year 211: 0.034634; Year 216: 0.024694; Year 221: 0.017606; Year 226: 0.012553; Year 231: 0.0089502; Year 236: 0.0063814; Year 241: 0.0045498; Year 246: 0.003244; Year 251: 0.0023129; Year 256: 0.0016491; Year 261: 0.0011758; Year 266: 0.0008383; Year 271: 0.0005977; Year 276: 0.00042615; Year 281: 0.00030384; Year 286: 0.00021663; Year 291: 0.00015446; Year 296: 0.00011013; Year 301: 7.8518e-05; Year 306: 5.5982e-05; Year 311: 3.9914e-05; Year 316: 2.8458e-05; Year 321: 2.029e-05; Year 326: 1.4467e-05; Year 331: 1.0315e-05; Year 336: 7.3542e-06; Year 341: 5.2434e-06; Year 346: 3.7385e-06; Year 351: 2.6655e-06; Year 356: 1.9005e-06; Year 361: 1.355e-06; Year 366: 9.661e-07; Year 371: 6.8882e-07; Year 376: 4.9112e-07; Year 381: 3.5016e-07; Year 386: 2.4966e-07; Year 391: 1.78e-07; Year 396: 1.2691e-07; Year 401: 9.0488e-08; Year 406: 6.4517e-08; Year 411: 4.5999e-08; Year 416: 3.2797e-08; Year 421: 2.3384e-08; Year 426: 1.6672e-08; Year 431: 1.1887e-08; Year 436: 8.4754e-09; Year 441: 6.0428e-09; Year 446: 4.3084e-09; Year 451: 3.0719e-09; Year 456: 2.1902e-09; Year 461: 1.5616e-09; Year 466: 1.1134e-09; Year 471: 7.9383e-10; Year 476: 5.6599e-10; Year 481: 4.0354e-10; Year 486: 2.8772e-10; Year 491: 2.0514e-10
| Revegetation Success | 500753.0579 | Year 1: 80993.4579; Year 2: 75694.8205; Year 3: 70742.8229; Year 4: 66114.7878; Year 5: 61789.5213; Year 8: 50438.655; Year 11: 41172.967; Year 15: 31410.6594; Year 20: 22395.366; Year 41: 5408.774; Year 46: 3856.3811; Year 51: 2749.5464; Year 56: 1960.3886; Year 61: 1397.73; Year 66: 996.5622; Year 71: 710.535; Year 76: 506.6017; Year 81: 361.2; Year 86: 257.5306; Year 91: 183.6158; Year 96: 130.9155; Year 101: 93.3409; Year 106: 66.5508; Year 111: 47.4498; Year 116: 33.8311; Year 121: 24.1211; Year 126: 17.198; Year 131: 12.2619; Year 136: 8.7426; Year 141: 6.2333; Year 146: 4.4443; Year 151: 3.1687; Year 156: 2.2593; Year 161: 1.6108; Year 166: 1.1485; Year 171: 0.81886; Year 176: 0.58383; Year 181: 0.41627; Year 186: 0.29679; Year 191: 0.21161; Year 196: 0.15087; Year 201: 0.10757; Year 206: 0.076696; Year 211: 0.054684; Year 216: 0.038989; Year 221: 0.027798; Year 226: 0.01982; Year 231: 0.014131; Year 236: 0.010075; Year 241: 0.0071836; Year 246: 0.0051218; Year 251: 0.0036518; Year 256: 0.0026037; Year 261: 0.0018564; Year 266: 0.0013236; Year 271: 0.00094369; Year 276: 0.00067284; Year 281: 0.00047972; Year 286: 0.00034204; Year 291: 0.00024387; Year 296: 0.00017387; Year 301: 0.00012397; Year 306: 8.8389e-05; Year 311: 6.302e-05; Year 316: 4.4932e-05; Year 321: 3.2036e-05; Year 326: 2.2841e-05; Year 331: 1.6286e-05; Year 336: 1.1611e-05; Year 341: 8.2788e-06; Year 346: 5.9026e-06; Year 351: 4.2085e-06; Year 356: 3.0006e-06; Year 361: 2.1394e-06; Year 366: 1.5254e-06; Year 371: 1.0876e-06; Year 376: 7.7541e-07; Year 381: 5.5286e-07; Year 386: 3.9418e-07; Year 391: 2.8105e-07; Year 396: 2.0038e-07; Year 401: 1.4287e-07; Year 406: 1.0186e-07; Year 411: 7.2627e-08; Year 416: 5.1782e-08; Year 421: 3.692e-08; Year 426: 2.6324e-08; Year 431: 1.8768e-08; Year 436: 1.3382e-08; Year 441: 9.5409e-09; Year 446: 6.8025e-09; Year 451: 4.8501e-09; Year 456: 3.458e-09; Year 461: 2.4655e-09; Year 466: 1.7579e-09; Year 471: 1.2534e-09; Year 476: 8.9363e-10; Year 481: 6.3714e-10; Year 486: 4.5427e-10; Year 491: 3.2389e-10
| Soil and Vegetation Chemistry | 514030.7241 | Year 2: 137536.9028; Year 5: 112271.0817; Year 8: 91646.6457; Year 11: 74810.9623; Year 15: 57072.9249; Year 20: 40692.2067; Year 41: 9827.7004; Year 46: 7007.0146; Year 51: 4995.9046; Year 56: 3562.0109; Year 61: 2539.6645; Year 66: 1810.7457; Year 71: 1291.0367; Year 76: 920.4913; Year 81: 656.2976; Year 86: 467.9311; Year 91: 333.6284; Year 96: 237.8724; Year 101: 169.5998; Year 106: 120.9223; Year 111: 86.2159; Year 116: 61.4708; Year 121: 43.8278; Year 126: 31.2486; Year 131: 22.2798; Year 136: 15.8852; Year 141: 11.3259; Year 146: 8.0752; Year 151: 5.7575; Year 156: 4.105; Year 161: 2.9268; Year 166: 2.0868; Year 171: 1.4879; Year 176: 1.0608; Year 181: 0.75635; Year 186: 0.53927; Year 191: 0.38449; Year 196: 0.27414; Year 201: 0.19546; Year 206: 0.13936; Year 211: 0.09936; Year 216: 0.070842; Year 221: 0.050509; Year 226: 0.036012; Year 231: 0.025676; Year 236: 0.018307; Year 241: 0.013053; Year 246: 0.0093063; Year 251: 0.0066353; Year 256: 0.0047309; Year 261: 0.003373; Year 266: 0.0024049; Year 271: 0.0017147; Year 276: 0.0012225; Year 281: 0.00087166; Year 286: 0.00062148; Year 291: 0.00044311; Year 296: 0.00031593; Year 301: 0.00022525; Year 306: 0.0001606; Year 311: 0.00011451; Year 316: 8.1642e-05; Year 321: 5.821e-05; Year 326: 4.1503e-05; Year 331: 2.9591e-05; Year 336: 2.1098e-05; Year 341: 1.5042e-05; Year 346: 1.0725e-05; Year 351: 7.6468e-06; Year 356: 5.4521e-06; Year 361: 3.8873e-06; Year 366: 2.7716e-06; Year 371: 1.9761e-06; Year 376: 1.4089e-06; Year 381: 1.0045e-06; Year 386: 7.1622e-07; Year 391: 5.1066e-07; Year 396: 3.6409e-07; Year 401: 2.5959e-07; Year 406: 1.8509e-07; Year 411: 1.3196e-07; Year 416: 9.4088e-08; Year 421: 6.7084e-08; Year 426: 4.783e-08; Year 431: 3.4102e-08; Year 436: 2.4314e-08; Year 441: 1.7336e-08; Year 446: 1.236e-08; Year 451: 8.8126e-09; Year 456: 6.2832e-09; Year 461: 4.4799e-09; Year 466: 3.1941e-09; Year 471: 2.2773e-09; Year 476: 1.6237e-09; Year 481: 1.1577e-09; Year 486: 8.2541e-10; Year 491: 5.8851e-10
| Wildlife Aerial Surveys | 435953.9932 | Year 1: 97031.7757; Year 2: 90683.9025; Year 5: 74025.0771; Year 8: 60426.5133; Year 11: 49326.0345; Year 15: 37630.5955; Year 20: 26830.0945; Year 41: 6479.819; Year 46: 4620.0214; Year 51: 3294.0114; Year 56: 2348.5846; Year 61: 1674.5084; Year 66: 1193.9013; Year 71: 851.2351; Year 76: 606.9189; Year 81: 432.7248; Year 86: 308.5268; Year 91: 219.9753; Year 96: 156.8394; Year 101: 111.8243; Year 106: 79.7292; Year 111: 56.8458; Year 116: 40.5303; Year 121: 28.8975; Year 126: 20.6035; Year 131: 14.69; Year 136: 10.4738; Year 141: 7.4677; Year 146: 5.3243; Year 151: 3.7962; Year 156: 2.7066; Year 161: 1.9298; Year 166: 1.3759; Year 171: 0.98101; Year 176: 0.69944; Year 181: 0.49869; Year 186: 0.35556; Year 191: 0.25351; Year 196: 0.18075; Year 201: 0.12887; Year 206: 0.091884; Year 211: 0.065512; Year 216: 0.046709; Year 221: 0.033303; Year 226: 0.023745; Year 231: 0.01693; Year 236: 0.012071; Year 241: 0.0086061; Year 246: 0.006136; Year 251: 0.0043749; Year 256: 0.0031193; Year 261: 0.002224; Year 266: 0.0015857; Year 271: 0.0011306; Year 276: 0.00080607; Year 281: 0.00057472; Year 286: 0.00040977; Year 291: 0.00029216; Year 296: 0.0002083; Year 301: 0.00014852; Year 306: 0.00010589; Year 311: 7.5499e-05; Year 316: 5.383e-05; Year 321: 3.838e-05; Year 326: 2.7364e-05; Year 331: 1.951e-05; Year 336: 1.3911e-05; Year 341: 9.9181e-06; Year 346: 7.0715e-06; Year 351: 5.0419e-06; Year 356: 3.5948e-06; Year 361: 2.563e-06; Year 366: 1.8274e-06; Year 371: 1.3029e-06; Year 376: 9.2896e-07; Year 381: 6.6234e-07; Year 386: 4.7224e-07; Year 391: 3.367e-07; Year 396: 2.4006e-07; Year 401: 1.7116e-07; Year 406: 1.2203e-07; Year 411: 8.7009e-08; Year 416: 6.2036e-08; Year 421: 4.4231e-08; Year 426: 3.1536e-08; Year 431: 2.2485e-08; Year 436: 1.6031e-08; Year 441: 1.143e-08; Year 446: 8.1495e-09; Year 451: 5.8105e-09; Year 456: 4.1428e-09; Year 461: 2.9538e-09; Year 466: 2.106e-09; Year 471: 1.5015e-09; Year 476: 1.0706e-09; Year 481: 7.6331e-10; Year 486: 5.4423e-10; Year 491: 3.8803e-10
| Aquatics | 90088.9286 | Year 1: 20051.4019; Year 2: 18739.6279; Year 5: 15297.1185; Year 8: 12487.0053; Year 11: 10193.1159; Year 15: 7776.2794; Year 20: 5544.3797; Year 41: 1339.0403; Year 46: 954.7172; Year 51: 680.7002; Year 56: 485.3298; Year 61: 346.0334; Year 66: 246.7171; Year 71: 175.9059; Year 76: 125.4184; Year 81: 89.4216; Year 86: 63.7564; Year 91: 45.4574; Year 96: 32.4105; Year 101: 23.1082; Year 106: 16.4759; Year 111: 11.7471; Year 116: 8.3755; Year 121: 5.9716; Year 126: 4.2577; Year 131: 3.0357; Year 136: 2.1644; Year 141: 1.5432; Year 146: 1.1003; Year 151: 0.78447; Year 156: 0.55932; Year 161: 0.39879; Year 166: 0.28433; Year 171: 0.20272; Year 176: 0.14454; Year 181: 0.10305; Year 186: 0.073476; Year 191: 0.052387; Year 196: 0.037352; Year 201: 0.026631; Year 206: 0.018988; Year 211: 0.013538; Year 216: 0.0096523; Year 221: 0.006882; Year 226: 0.0049068; Year 231: 0.0034985; Year 236: 0.0024943; Year 241: 0.0017784; Year 246: 0.001268; Year 251: 0.00090407; Year 256: 0.00064459; Year 261: 0.00045958; Year 266: 0.00032768; Year 271: 0.00023363; Year 276: 0.00016657; Year 281: 0.00011876; Year 286: 8.4678e-05; Year 291: 6.0374e-05; Year 296: 4.3046e-05; Year 301: 3.0691e-05; Year 306: 2.1882e-05; Year 311: 1.5602e-05; Year 316: 1.1124e-05; Year 321: 7.9311e-06; Year 326: 5.6548e-06; Year 331: 4.0318e-06; Year 336: 2.8746e-06; Year 341: 2.0496e-06; Year 346: 1.4613e-06; Year 351: 1.0419e-06; Year 356: 7.4285e-07; Year 361: 5.2964e-07; Year 366: 3.7763e-07; Year 371: 2.6924e-07; Year 376: 1.9197e-07; Year 381: 1.3687e-07; Year 386: 9.7587e-08; Year 391: 6.9578e-08; Year 396: 4.9608e-08; Year 401: 3.537e-08; Year 406: 2.5218e-08; Year 411: 1.798e-08; Year 416: 1.282e-08; Year 421: 9.1403e-09; Year 426: 6.5169e-09; Year 431: 4.6464e-09; Year 436: 3.3128e-09; Year 441: 2.362e-09; Year 446: 1.6841e-09; Year 451: 1.2007e-09; Year 456: 8.561e-10; Year 461: 6.1039e-10; Year 466: 4.352e-10; Year 471: 3.1029e-10; Year 476: 2.2123e-10; Year 481: 1.5774e-10; Year 486: 1.1246e-10; Year 491: 8.0185e-11
| Effluent | 0 | Year 1: 0; Year 2: 0; Year 5: 0; Year 8: 0; Year 11: 0; Year 15: 0; Year 20: 0; Year 41: 0; Year 46: 0; Year 51: 0; Year 56: 0; Year 61: 0; Year 66: 0; Year 71: 0; Year 76: 0; Year 81: 0; Year 86: 0; Year 91: 0; Year 96: 0; Year 101: 0; Year 106: 0; Year 111: 0; Year 116: 0; Year 121: 0; Year 126: 0; Year 131: 0; Year 136: 0; Year 141: 0; Year 146: 0; Year 151: 0; Year 156: 0; Year 161: 0; Year 166: 0; Year 171: 0; Year 176: 0; Year 181: 0; Year 186: 0; Year 191: 0; Year 196: 0; Year 201: 0; Year 206: 0; Year 211: 0; Year 216: 0; Year 221: 0; Year 226: 0; Year 231: 0; Year 236: 0; Year 241: 0; Year 246: 0; Year 251: 0; Year 256: 0; Year 261: 0; Year 266: 0; Year 271: 0; Year 276: 0; Year 281: 0; Year 286: 0; Year 291: 0; Year 296: 0; Year 301: 0; Year 306: 0; Year 311: 0; Year 316: 0; Year 321: 0; Year 326: 0; Year 331: 0; Year 336: 0; Year 341: 0; Year 346: 0; Year 351: 0; Year 356: 0; Year 361: 0; Year 366: 0; Year 371: 0; Year 376: 0; Year 381: 0; Year 386: 0; Year 391: 0; Year 396: 0; Year 401: 0; Year 406: 0; Year 411: 0; Year 416: 0; Year 421: 0; Year 426: 0; Year 431: 0; Year 436: 0; Year 441: 0; Year 446: 0; Year 451: 0; Year 456: 0; Year 461: 0; Year 466: 0; Year 471: 0; Year 476: 0; Year 481: 0; Year 486: 0; Year 491: 0
| Instrumentation Maintenance/Replacement | 211880.2849 | Year 1: 18691.5888; Year 2: 17468.7746; Year 3: 16325.9575; Year 4: 15257.9042; Year 5: 14259.7236; Year 6: 13326.8445; Year 7: 12454.9948; Year 8: 11640.1821; Year 9: 10878.6749; Year 10: 10166.9858; Year 11: 9501.8559; Year 12: 8880.2392; Year 13: 8299.289; Year 14: 7756.3448; Year 15: 7248.9204; Year 16: 6774.692; Year 17: 6331.4878; Year 18: 5917.2783; Year 19: 5530.1667; Year 20: 5168.3801; Year 41: 1248.2314; Year 46: 889.9718; Year 51: 634.5376; Year 56: 452.4165; Year 61: 322.5667; Year 66: 229.9856; Year 71: 163.9766; Year 76: 116.913; Year 81: 83.3574; Year 86: 59.4327; Year 91: 42.3747; Year 96: 30.2125; Year 101: 21.5411; Year 106: 15.3585; Year 111: 10.9504; Year 116: 7.8075; Year 121: 5.5666; Year 126: 3.9689; Year 131: 2.8298; Year 136: 2.0176; Year 141: 1.4385; Year 146: 1.0256; Year 151: 0.73127; Year 156: 0.52139; Year 161: 0.37174; Year 166: 0.26505; Year 171: 0.18897; Year 176: 0.13474; Year 181: 0.096065; Year 186: 0.068493; Year 191: 0.048835; Year 196: 0.034818; Year 201: 0.024825; Year 206: 0.0177; Year 211: 0.01262; Year 216: 0.0089978; Year 221: 0.0064153; Year 226: 0.004574; Year 231: 0.0032612; Year 236: 0.0023252; Year 241: 0.0016578; Year 246: 0.001182; Year 251: 0.00084276; Year 256: 0.00060087; Year 261: 0.00042841; Year 266: 0.00030545; Year 271: 0.00021778; Year 276: 0.00015528; Year 281: 0.00011071; Year 286: 7.8935e-05; Year 291: 5.628e-05; Year 296: 4.0127e-05; Year 301: 2.861e-05; Year 306: 2.0398e-05; Year 311: 1.4544e-05; Year 316: 1.0369e-05; Year 321: 7.3933e-06; Year 326: 5.2713e-06; Year 331: 3.7584e-06; Year 336: 2.6797e-06; Year 341: 1.9106e-06; Year 346: 1.3622e-06; Year 351: 9.7123e-07; Year 356: 6.9248e-07; Year 361: 4.9373e-07; Year 366: 3.5202e-07; Year 371: 2.5099e-07; Year 376: 1.7895e-07; Year 381: 1.2759e-07; Year 386: 9.0969e-08; Year 391: 6.4859e-08; Year 396: 4.6244e-08; Year 401: 3.2971e-08; Year 406: 2.3508e-08; Year 411: 1.6761e-08; Year 416: 1.195e-08; Year 421: 8.5204e-09; Year 426: 6.0749e-09; Year 431: 4.3313e-09; Year 436: 3.0882e-09; Year 441: 2.2018e-09; Year 446: 1.5699e-09; Year 451: 1.1193e-09; Year 456: 7.9804e-10; Year 461: 5.69e-10; Year 466: 4.0569e-10; Year 471: 2.8925e-10; Year 476: 2.0623e-10; Year 481: 1.4704e-10; Year 486: 1.0484e-10; Year 491: 7.4747e-11
| Road Closure and Reclamation | 51537.376 | Year 2: 18767.9765; Year 10: 32769.3995; Year 41: 5364.2636; Year 46: 3824.6458; Year 51: 2726.9196; Year 56: 1944.256; Year 61: 1386.2277; Year 66: 988.3612; Year 71: 704.6878; Year 76: 502.4327; Year 81: 358.2276; Year 86: 255.4113; Year 91: 182.1047; Year 96: 129.8382; Year 101: 92.5728; Year 106: 66.0031; Year 111: 47.0593; Year 116: 33.5526; Year 121: 23.9226; Year 126: 17.0565; Year 131: 12.161; Year 136: 8.6706; Year 141: 6.182; Year 146: 4.4077; Year 151: 3.1426; Year 156: 2.2407; Year 161: 1.5976; Year 166: 1.139; Year 171: 0.81212; Year 176: 0.57903; Year 181: 0.41284; Year 186: 0.29435; Year 191: 0.20987; Year 196: 0.14963; Year 201: 0.10669; Year 206: 0.076065; Year 211: 0.054234; Year 216: 0.038668; Year 221: 0.02757; Year 226: 0.019657; Year 231: 0.014015; Year 236: 0.0099925; Year 241: 0.0071245; Year 246: 0.0050797; Year 251: 0.0036217; Year 256: 0.0025822; Year 261: 0.0018411; Year 266: 0.0013127; Year 271: 0.00093593; Year 276: 0.0006673; Year 281: 0.00047578; Year 286: 0.00033922; Year 291: 0.00024186; Year 296: 0.00017244; Year 301: 0.00012295; Year 306: 8.7662e-05; Year 311: 6.2501e-05; Year 316: 4.4563e-05; Year 321: 3.1773e-05; Year 326: 2.2653e-05; Year 331: 1.6152e-05; Year 336: 1.1516e-05; Year 341: 8.2106e-06; Year 346: 5.8541e-06; Year 351: 4.1739e-06; Year 356: 2.9759e-06; Year 361: 2.1218e-06; Year 366: 1.5128e-06; Year 371: 1.0786e-06; Year 376: 7.6903e-07; Year 381: 5.4831e-07; Year 386: 3.9094e-07; Year 391: 2.7873e-07; Year 396: 1.9873e-07; Year 401: 1.4169e-07; Year 406: 1.0103e-07; Year 411: 7.203e-08; Year 416: 5.1356e-08; Year 421: 3.6616e-08; Year 426: 2.6107e-08; Year 431: 1.8614e-08; Year 436: 1.3271e-08; Year 441: 9.4624e-09; Year 446: 6.7465e-09; Year 451: 4.8102e-09; Year 456: 3.4296e-09; Year 461: 2.4453e-09; Year 466: 1.7434e-09; Year 471: 1.243e-09; Year 476: 8.8627e-10; Year 481: 6.319e-10; Year 486: 4.5054e-10; Year 491: 3.2123e-10
| Total | 5980508.8171 | 647033.6449 | 761009.2202 | 712952.6758 | 666310.912 | 660190.0411 | 329136.6296 | 307604.3267 | 502479.4985 | 180548.2889 | 201506.1181 | 293055.1074 | 109861.7081 | 102674.4936 | 95957.4706 | 170215.1527 | 33948.3117 | 30894.3325 | 28873.208 | 26256.6783 | 120000.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54122.8438 | 0 | 0 | 0 | 0 | 38588.8396 | 0 | 0 | 0 | 0 | 27513.3093 | 0 | 0 | 0 | 0 | 19616.6093 | 0 | 0 | 0 | 0 | 13986.3713 | 0 | 0 | 0 | 0 | 9972.0895 | 0 | 0 | 0 | 0 | 7109.962 | 0 | 0 | 0 | 0 | 5069.3046 | 0 | 0 | 0 | 0 | 3614.3441 | 0 | 0 | 0 | 0 | 2576.9774 | 0 | 0 | 0 | 0 | 1837.3493 | 0 | 0 | 0 | 0 | 1310.0046 | 0 | 0 | 0 | 0 | 934.0152 | 0 | 0 | 0 | 0 | 665.9399 | 0 | 0 | 0 | 0 | 474.806 | 0 | 0 | 0 | 0 | 338.5301 | 0 | 0 | 0 | 0 | 241.3673 | 0 | 0 | 0 | 0 | 172.0915 | 0 | 0 | 0 | 0 | 122.6989 | 0 | 0 | 0 | 0 | 87.4826 | 0 | 0 | 0 | 0 | 62.3739 | 0 | 0 | 0 | 0 | 44.4717 | 0 | 0 | 0 | 0 | 31.7077 | 0 | 0 | 0 | 0 | 22.6072 | 0 | 0 | 0 | 0 | 16.1186 | 0 | 0 | 0 | 0 | 11.4923 | 0 | 0 | 0 | 0 | 8.1939 | 0 | 0 | 0 | 0 | 5.8421 | 0 | 0 | 0 | 0 | 4.1654 | 0 | 0 | 0 | 0 | 2.9698 | 0 | 0 | 0 | 0 | 2.1175 | 0 | 0 | 0 | 0 | 1.5097 | 0 | 0 | 0 | 0 | 1.0764 | 0 | 0 | 0 | 0 | 0.76746 | 0 | 0 | 0 | 0 | 0.54719 | 0 | 0 | 0 | 0 | 0.39014 | 0 | 0 | 0 | 0 | 0.27816 | 0 | 0 | 0 | 0 | 0.19833 | 0 | 0 | 0 | 0 | 0.1414 | 0 | 0 | 0 | 0 | 0.10082 | 0 | 0 | 0 | 0 | 0.071883 | 0 | 0 | 0 | 0 | 0.051251 | 0 | 0 | 0 | 0 | 0.036542 | 0 | 0 | 0 | 0 | 0.026054 | 0 | 0 | 0 | 0 | 0.018576 | 0 | 0 | 0 | 0 | 0.013244 | 0 | 0 | 0 | 0 | 0.009443 | 0 | 0 | 0 | 0 | 0.0067328 | 0 | 0 | 0 | 0 | 0.0048004 | 0 | 0 | 0 | 0 | 0.0034226 | 0 | 0 | 0 | 0 | 0.0024403 | 0 | 0 | 0 | 0 | 0.0017399 | 0 | 0 | 0 | 0 | 0.0012405 | 0 | 0 | 0 | 0 | 0.00088446 | 0 | 0 | 0 | 0 | 0.00063061 | 0 | 0 | 0 | 0 | 0.00044962 | 0 | 0 | 0 | 0 | 0.00032057 | 0 | 0 | 0 | 0 | 0.00022856 | 0 | 0 | 0 | 0 | 0.00016296 | 0 | 0 | 0 | 0 | 0.00011619 | 0 | 0 | 0 | 0 | 8.2841e-05 | 0 | 0 | 0 | 0 | 5.9065e-05 | 0 | 0 | 0 | 0 | 4.2112e-05 | 0 | 0 | 0 | 0 | 3.0026e-05 | 0 | 0 | 0 | 0 | 2.1408e-05 | 0 | 0 | 0 | 0 | 1.5263e-05 | 0 | 0 | 0 | 0 | 1.0883e-05 | 0 | 0 | 0 | 0 | 7.7592e-06 | 0 | 0 | 0 | 0 | 5.5322e-06 | 0 | 0 | 0 | 0 | 3.9444e-06 | 0 | 0 | 0 | 0 | 2.8123e-06 | 0 | 0 | 0 | 0 | 2.0051e-06 | 0 | 0 | 0 | 0 | 1.4296e-06 | 0 | 0 | 0 | 0 | 1.0193e-06 | 0 | 0 | 0 | 0 | 7.2675e-07 | 0 | 0 | 0 | 0 | 5.1816e-07 | 0 | 0 | 0 | 0 | 3.6944e-07 | 0 | 0 | 0 | 0 | 2.6341e-07 | 0 | 0 | 0 | 0 | 1.8781e-07 | 0 | 0 | 0 | 0 | 1.339e-07 | 0 | 0 | 0 | 0 | 9.5471e-08 | 0 | 0 | 0 | 0 | 6.8069e-08 | 0 | 0 | 0 | 0 | 4.8532e-08 | 0 | 0 | 0 | 0 | 3.4603e-08 | 0 | 0 | 0 | 0 | 2.4671e-08 | 0 | 0 | 0 | 0 | 1.759e-08 | 0 | 0 | 0 | 0 | 1.2542e-08 | 0 | 0 | 0 | 0 | 8.9421e-09 | 0 | 0 | 0 | 0 | 6.3756e-09 | 0 | 0 | 0 | 0 | 4.5457e-09 | 0 | 0 | 0 | 0 | 3.241e-09 | 0

## T20-NPV-EOM
Table 20
NPV-Post Closure Care, Maintenance, and Monitoring
| Full Annual Cost/Cost Rate |  |  | Discount Rate |  |  | 7%
| Task | Cost | Units | Number of PC years to include |  |  | 10 |  | *Enter the number of years AFTER transitional closure is complete
| Active Treatment System | 0 | an
| Passive Treatment System | 10525.95 | an
| Field Support Staff & Vehicles | 32001.375 | an
| Project Management | 105120 | an
| Camp and General | 26229 | an
| Reclamation Maintenance | 112845.6085 | an
| Site Maintenance | 17805.6 | an
| Transportation Costs | 64307.5 | an
| Water Quality Monitoring | 0 | ea
| Physical/Geotech Stability Monitoring | 20069 | ea
| Surface Water Monitoring | 17008 | ea
| Groundwater Monitoring | 78761 | ea
| Revegetation Success | 54889 | ea
| Soil and Vegetation Chemistry | 86663 | ea
| Wildlife Aerial Surveys | 157466 | ea
| Aquatics | 103824 | ea
| Effluent | 21455 | ea
| Instrumentation Maintenance/Replacement | 20000 | an
| Road Closure and Reclamation | 113054.5182 | an
| Implementation Schedule |  | Year of Closure
| Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Active Treatment System
| Passive Treatment System |  | Year of Closure 16: 1; Year of Closure 17: 1; Year of Closure 18: 1; Year of Closure 19: 1; Year of Closure 20: 0.5; Year of Closure 21: 0.5; Year of Closure 22: 0.25; Year of Closure 23: 0.25; Year of Closure 30: 1; Year of Closure 35: 1
| Field Support Staff & Vehicles |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 1; Year of Closure 8: 1; Year of Closure 9: 1; Year of Closure 10: 1; Year of Closure 11: 1; Year of Closure 12: 1; Year of Closure 13: 0.5; Year of Closure 14: 0.5; Year of Closure 15: 0.5; Year of Closure 16: 0.5; Year of Closure 17: 0.5; Year of Closure 18: 0.5; Year of Closure 19: 0.5; Year of Closure 30: 1; Year of Closure 35: 1
| Project Management |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 1; Year of Closure 8: 1; Year of Closure 9: 1; Year of Closure 10: 1; Year of Closure 11: 1; Year of Closure 12: 1; Year of Closure 13: 0.5; Year of Closure 14: 0.5; Year of Closure 15: 0.5; Year of Closure 16: 0.5; Year of Closure 17: 0.5; Year of Closure 18: 0.5; Year of Closure 19: 0.5; Year of Closure 30: 1; Year of Closure 35: 1
| Camp and General |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 1; Year of Closure 8: 1; Year of Closure 9: 1; Year of Closure 10: 1; Year of Closure 11: 1; Year of Closure 12: 1; Year of Closure 13: 0.5; Year of Closure 14: 0.5; Year of Closure 15: 0.5; Year of Closure 16: 0.5; Year of Closure 17: 0.5; Year of Closure 18: 0.5; Year of Closure 19: 0.5; Year of Closure 30: 1; Year of Closure 35: 1
| Reclamation Maintenance |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 0.5; Year of Closure 8: 0.5; Year of Closure 9: 0.5; Year of Closure 10: 0.5; Year of Closure 11: 0.5; Year of Closure 12: 0.5; Year of Closure 13: 0.5; Year of Closure 14: 0.25; Year of Closure 15: 0.25; Year of Closure 16: 0.25; Year of Closure 17: 0.25; Year of Closure 18: 0.25; Year of Closure 19: 0.25; Year of Closure 30: 1; Year of Closure 35: 1
| Site Maintenance |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 1; Year of Closure 8: 1; Year of Closure 9: 1; Year of Closure 10: 1; Year of Closure 11: 1; Year of Closure 12: 1; Year of Closure 13: 0.5; Year of Closure 14: 0.5; Year of Closure 15: 0.5; Year of Closure 16: 0.5; Year of Closure 17: 0.5; Year of Closure 18: 0.5; Year of Closure 19: 0.5; Year of Closure 30: 1; Year of Closure 35: 1
| Transportation Costs |  | Year of Closure 4: 1; Year of Closure 5: 1; Year of Closure 6: 1; Year of Closure 7: 0.5; Year of Closure 8: 0.5; Year of Closure 9: 0.5; Year of Closure 10: 0.5; Year of Closure 11: 0.5; Year of Closure 12: 0.5; Year of Closure 13: 0.5; Year of Closure 14: 0.25; Year of Closure 15: 0.25; Year of Closure 16: 0.25; Year of Closure 17: 0.25; Year of Closure 18: 0.25; Year of Closure 19: 0.25; Year of Closure 20: 0; Year of Closure 21: 0; Year of Closure 22: 0; Year of Closure 23: 0; Year of Closure 24: 0; Year of Closure 25: 0; Year of Closure 30: 1; Year of Closure 35: 1
Water Quality Monitoring
Physical/Geotech Stability Monitoring | bar: Year of Closure 2 to Year of Closure 8; Year of Closure 10; Year of Closure 12; Year of Closure 15; Year of Closure 18; Year of Closure 22; Year of Closure 26; Year of Closure 30; Year of Closure 35
| Surface Water Monitoring |  | Year of Closure 1: 12; Year of Closure 2: 12; Year of Closure 3: 12; Year of Closure 4: 12; Year of Closure 5: 12; Year of Closure 6: 12; Year of Closure 7: 6; Year of Closure 8: 6; Year of Closure 9: 6; Year of Closure 10: 6; Year of Closure 11: 4; Year of Closure 12: 4; Year of Closure 13: 4; Year of Closure 14: 4; Year of Closure 15: 4; Year of Closure 16: 2; Year of Closure 17: 2; Year of Closure 18: 2; Year of Closure 19: 2; Year of Closure 20: 1; Year of Closure 21: 1; Year of Closure 22: 1; Year of Closure 23: 1; Year of Closure 24: 1; Year of Closure 25: 1; Year of Closure 26: 1; Year of Closure 30: 1; Year of Closure 35: 1
| Groundwater Monitoring |  | Year of Closure 1: 4; Year of Closure 2: 4; Year of Closure 3: 4; Year of Closure 4: 4; Year of Closure 5: 4; Year of Closure 6: 4; Year of Closure 7: 2; Year of Closure 8: 2; Year of Closure 9: 2; Year of Closure 10: 2; Year of Closure 11: 2; Year of Closure 12: 2; Year of Closure 13: 2; Year of Closure 14: 2; Year of Closure 15: 2; Year of Closure 16: 1; Year of Closure 17: 1; Year of Closure 18: 1; Year of Closure 19: 1; Year of Closure 20: 1; Year of Closure 21: 1; Year of Closure 22: 1; Year of Closure 23: 1; Year of Closure 24: 1; Year of Closure 25: 1; Year of Closure 26: 1; Year of Closure 30: 1; Year of Closure 35: 1
Revegetation Success | bar: Year of Closure 1 to Year of Closure 6; Year of Closure 8; Year of Closure 11; Year of Closure 15; Year of Closure 20; Year of Closure 25; Year of Closure 30; Year of Closure 35
Soil and Vegetation Chemistry | bar: Year of Closure 3; Year of Closure 6; Year of Closure 10; Year of Closure 15; Year of Closure 20; Year of Closure 25; Year of Closure 30; Year of Closure 35
Wildlife Aerial Surveys | bar: Year of Closure 1 to Year of Closure 3; Year of Closure 6; Year of Closure 10; Year of Closure 15; Year of Closure 20; Year of Closure 25
Aquatics | bar: Year of Closure 1 to Year of Closure 3; Year of Closure 6; Year of Closure 10; Year of Closure 15; Year of Closure 20; Year of Closure 25; Year of Closure 30; Year of Closure 35
Effluent | bar: Year of Closure 1 to Year of Closure 3; Year of Closure 6; Year of Closure 10; Year of Closure 15; Year of Closure 20; Year of Closure 25; Year of Closure 30; Year of Closure 35
Instrumentation Maintenance/Replacement | bar: Year of Closure 1 to Year of Closure 25; Year of Closure 30; Year of Closure 35
| Road Closure and Reclamation |  | Year of Closure 3: 0.25; Year of Closure 15: 0.75
| Undiscounted Cost |  | Year of Closure 1: Year of Closure
| Task | SUM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 57892.725
| Active Treatment System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Passive Treatment System | 57892.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10525.95 | 10525.95 | 10525.95 | 10525.95 | 5262.975 | 5262.975 | 2631.4875 | 2631.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 10525.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff/Equipment | 2041879.6875
| Field Support Staff & Vehicles | 400017.1875 | 0 | 0 | 0 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 32001.375 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 16000.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 32001.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Management | 1314000 | 0 | 0 | 0 | 105120 | 105120 | 105120 | 105120 | 105120 | 105120 | 105120 | 105120 | 105120 | 52560 | 52560 | 52560 | 52560 | 52560 | 52560 | 52560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 105120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Camp and General | 327862.5 | 0 | 0 | 0 | 26229 | 26229 | 26229 | 26229 | 26229 | 26229 | 26229 | 26229 | 26229 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 13114.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 26229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance | 1125334.8682
| Reclamation Maintenance | 902764.8682 | 0 | 0 | 0 | 112845.6085 | 112845.6085 | 112845.6085 | 56422.8043 | 56422.8043 | 56422.8043 | 56422.8043 | 56422.8043 | 56422.8043 | 56422.8043 | 28211.4021 | 28211.4021 | 28211.4021 | 28211.4021 | 28211.4021 | 28211.4021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112845.6085 | 0 | 0 | 0 | 0 | 112845.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Site Maintenance | 222570 | 0 | 0 | 0 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 17805.6 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 8902.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 17805.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 514460
| Transportation Costs | 514460 | 0 | 0 | 0 | 64307.5 | 64307.5 | 64307.5 | 32153.75 | 32153.75 | 32153.75 | 32153.75 | 32153.75 | 32153.75 | 32153.75 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 16076.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 64307.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monitoring | 10546211.5182
| Water Quality Monitoring | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Physical/Geotech Stability Monitoring | 240828 | 0 | 20069 | 20069 | 20069 | 20069 | 20069 | 20069 | 20069 | 0 | 20069 | 0 | 20069 | 0 | 0 | 20069 | 0 | 0 | 20069 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 20069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Surface Water Monitoring | 2211040 | 204096 | 204096 | 204096 | 204096 | 204096 | 204096 | 102048 | 102048 | 102048 | 102048 | 68032 | 68032 | 68032 | 68032 | 68032 | 34016 | 34016 | 34016 | 34016 | 17008 | 17008 | 17008 | 17008 | 17008 | 17008 | 17008 | 0 | 0 | 0 | 17008 | 0 | 0 | 0 | 0 | 17008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Groundwater Monitoring | 4095572 | 315044 | 315044 | 315044 | 315044 | 315044 | 315044 | 157522 | 157522 | 157522 | 157522 | 157522 | 157522 | 157522 | 157522 | 157522 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 78761 | 0 | 0 | 0 | 78761 | 0 | 0 | 0 | 0 | 78761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Revegetation Success | 603779 | 54889 | 54889 | 54889 | 54889 | 54889 | 54889 | 0 | 54889 | 0 | 0 | 54889 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 54889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Soil and Vegetation Chemistry | 519978 | 0 | 0 | 86663 | 0 | 0 | 86663 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 86663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wildlife Aerial Surveys | 1259728 | 157466 | 157466 | 157466 | 0 | 0 | 157466 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 157466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aquatics | 830592 | 103824 | 103824 | 103824 | 0 | 0 | 103824 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 103824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effluent | 171640 | 21455 | 21455 | 21455 | 0 | 0 | 21455 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 21455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instrumentation Maintenance/Replacement | 500000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Road Closure and Reclamation | 113054.5182 | 0 | 0 | 28263.6296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84790.8887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 14285778.7989 | 876774 | 896843 | 1011769.6295 | 972407.0835 | 972407.0835 | 1341815.0835 | 569371.5293 | 624260.5293 | 549302.5293 | 938779.5293 | 570175.5293 | 535355.5293 | 424708.5418 | 380420.2646 | 909577.1533 | 278169.2146 | 278169.2146 | 298238.2146 | 278169.2146 | 545328.975 | 121031.975 | 138469.4875 | 118400.4875 | 115769 | 540066 | 115838 | 0 | 0 | 0 | 771504.0335 | 0 | 0 | 0 | 0 | 771504.0335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| NPV |  | Year of Closure 1: Year
| Task | SUM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426 | 427 | 428 | 429 | 430 | 431 | 432 | 433 | 434 | 435 | 436 | 437 | 438 | 439 | 440 | 441 | 442 | 443 | 444 | 445 | 446 | 447 | 448 | 449 | 450 | 451 | 452 | 453 | 454 | 455 | 456 | 457 | 458 | 459 | 460 | 461 | 462 | 463 | 464 | 465 | 466 | 467 | 468 | 469 | 470 | 471 | 472 | 473 | 474 | 475 | 476 | 477 | 478 | 479 | 480 | 481 | 482 | 483 | 484 | 485 | 486 | 487 | 488 | 489 | 490 | 491 | 492
Water Treatment | 16702.7069
| Active Treatment System | 0
| Passive Treatment System | 16702.7069 | Year of Closure 16: 3565.5034; Year of Closure 17: 3332.2462; Year of Closure 18: 3114.2488; Year of Closure 19: 2910.5129; Year of Closure 20: 1360.0528; Year of Closure 21: 1271.0773; Year of Closure 22: 593.9614; Year of Closure 23: 555.1041; Year of Closure 30: 1382.7637; Year of Closure 35: 985.8914
Staff/Equipment | 1064199.0619
| Field Support Staff & Vehicles | 208483.3491 | Year of Closure 4: 24413.6958; Year of Closure 5: 22816.5381; Year of Closure 6: 21323.8674; Year of Closure 7: 19928.848; Year of Closure 8: 18625.0916; Year of Closure 9: 17406.6277; Year of Closure 10: 16267.8763; Year of Closure 11: 15203.6227; Year of Closure 12: 14208.9932; Year of Closure 13: 6639.7165; Year of Closure 14: 6205.3425; Year of Closure 15: 5799.3855; Year of Closure 16: 5419.9864; Year of Closure 17: 5065.4079; Year of Closure 18: 4734.0261; Year of Closure 19: 4424.3234; Year of Closure 30: 4203.9284; Year of Closure 35: 2997.3428
| Project Management | 684838.3751 | Year of Closure 4: 80195.5447; Year of Closure 5: 74949.1072; Year of Closure 6: 70045.8946; Year of Closure 7: 65463.4529; Year of Closure 8: 61180.7971; Year of Closure 9: 57178.315; Year of Closure 10: 53437.6776; Year of Closure 11: 49941.7548; Year of Closure 12: 46674.5372; Year of Closure 13: 21810.5314; Year of Closure 14: 20383.6742; Year of Closure 15: 19050.1628; Year of Closure 16: 17803.8905; Year of Closure 17: 16639.15; Year of Closure 18: 15550.6074; Year of Closure 19: 14533.278; Year of Closure 30: 13809.3114; Year of Closure 35: 9845.8481
| Camp and General | 170877.3377 | Year of Closure 4: 20009.9785; Year of Closure 5: 18700.9145; Year of Closure 6: 17477.4902; Year of Closure 7: 16334.103; Year of Closure 8: 15265.5168; Year of Closure 9: 14266.8381; Year of Closure 10: 13333.4936; Year of Closure 11: 12461.209; Year of Closure 12: 11645.9897; Year of Closure 13: 5442.0513; Year of Closure 14: 5086.0292; Year of Closure 15: 4753.2983; Year of Closure 16: 4442.3349; Year of Closure 17: 4151.7148; Year of Closure 18: 3880.1073; Year of Closure 19: 3626.2685; Year of Closure 30: 3445.6281; Year of Closure 35: 2456.6852
Maintenance | 616162.0361
| Reclamation Maintenance | 500161.6729 | Year of Closure 4: 86089.3744; Year of Closure 5: 80457.3593; Year of Closure 6: 75193.7937; Year of Closure 7: 35137.2868; Year of Closure 8: 32838.5858; Year of Closure 9: 30690.2671; Year of Closure 10: 28682.4926; Year of Closure 11: 26806.0679; Year of Closure 12: 25052.3999; Year of Closure 13: 23413.4578; Year of Closure 14: 10940.8681; Year of Closure 15: 10225.1104; Year of Closure 16: 9556.178; Year of Closure 17: 8931.0074; Year of Closure 18: 8346.7359; Year of Closure 19: 7800.6878; Year of Closure 30: 14824.2023; Year of Closure 35: 10569.4513
| Site Maintenance | 116000.3631 | Year of Closure 4: 13583.807; Year of Closure 5: 12695.1467; Year of Closure 6: 11864.6231; Year of Closure 7: 11088.4328; Year of Closure 8: 10363.0213; Year of Closure 9: 9685.0666; Year of Closure 10: 9051.4642; Year of Closure 11: 8459.3123; Year of Closure 12: 7905.8993; Year of Closure 13: 3694.3455; Year of Closure 14: 3452.6593; Year of Closure 15: 3226.7844; Year of Closure 16: 3015.6864; Year of Closure 17: 2818.3985; Year of Closure 18: 2634.0173; Year of Closure 19: 2461.6984; Year of Closure 30: 2339.0703; Year of Closure 35: 1667.7248
Transportation | 285027.8996
| Transportation Costs | 285027.8996 | Year of Closure 4: 49059.8838; Year of Closure 5: 45850.3587; Year of Closure 6: 42850.8026; Year of Closure 7: 20023.7395; Year of Closure 8: 18713.7752; Year of Closure 9: 17489.5096; Year of Closure 10: 16345.3361; Year of Closure 11: 15276.015; Year of Closure 12: 14276.6495; Year of Closure 13: 13342.6631; Year of Closure 14: 6234.8893; Year of Closure 15: 5826.9994; Year of Closure 16: 5445.7938; Year of Closure 17: 5089.5269; Year of Closure 18: 4756.5672; Year of Closure 19: 4445.3899; Year of Closure 20: 0; Year of Closure 21: 0; Year of Closure 22: 0; Year of Closure 23: 0; Year of Closure 24: 0; Year of Closure 25: 0; Year of Closure 30: 8447.8909; Year of Closure 35: 6023.2294
Monitoring | 6127936.4229
| Water Quality Monitoring | 0
| Physical/Geotech Stability Monitoring | 137936.3125 | Year of Closure 2: 17529.0418; Year of Closure 3: 16382.2821; Year of Closure 4: 15310.544; Year of Closure 5: 14308.9196; Year of Closure 6: 13372.8221; Year of Closure 7: 12497.9646; Year of Closure 8: 11680.3407; Year of Closure 10: 10202.0619; Year of Closure 12: 8910.876; Year of Closure 15: 7273.9292; Year of Closure 18: 5937.6929; Year of Closure 22: 4529.8375; Year of Closure 26: 3455.7913; Year of Closure 30: 2636.4067; Year of Closure 35: 1879.7215
| Surface Water Monitoring | 1409136.7383 | Year of Closure 1: 190743.9252; Year of Closure 2: 178265.3507; Year of Closure 3: 166603.1315; Year of Closure 4: 155703.8612; Year of Closure 5: 145517.6273; Year of Closure 6: 135997.7825; Year of Closure 7: 63550.3657; Year of Closure 8: 59392.8651; Year of Closure 9: 55507.3506; Year of Closure 10: 51876.0286; Year of Closure 11: 32321.5131; Year of Closure 12: 30207.0216; Year of Closure 13: 28230.8613; Year of Closure 14: 26383.9825; Year of Closure 15: 24657.9276; Year of Closure 16: 11522.3961; Year of Closure 17: 10768.5945; Year of Closure 18: 10064.107; Year of Closure 19: 9405.7075; Year of Closure 20: 4395.1904; Year of Closure 21: 4107.6546; Year of Closure 22: 3838.9295; Year of Closure 23: 3587.7846; Year of Closure 24: 3353.0697; Year of Closure 25: 3133.71; Year of Closure 26: 2928.7009; Year of Closure 30: 2234.2919; Year of Closure 35: 1593.0193
| Groundwater Monitoring | 2386031.1399 | Year of Closure 1: 294433.6449; Year of Closure 2: 275171.6307; Year of Closure 3: 257169.7483; Year of Closure 4: 240345.5592; Year of Closure 5: 224622.0179; Year of Closure 6: 209927.1196; Year of Closure 7: 98096.7848; Year of Closure 8: 91679.2382; Year of Closure 9: 85681.531; Year of Closure 10: 80076.1972; Year of Closure 11: 74837.5675; Year of Closure 12: 69941.6518; Year of Closure 13: 65366.0298; Year of Closure 14: 61089.7474; Year of Closure 15: 57093.2219; Year of Closure 16: 26679.0757; Year of Closure 17: 24933.7156; Year of Closure 18: 23302.5379; Year of Closure 19: 21778.0728; Year of Closure 20: 20353.3391; Year of Closure 21: 19021.8122; Year of Closure 22: 17777.3946; Year of Closure 23: 16614.3875; Year of Closure 24: 15527.4649; Year of Closure 25: 14511.6495; Year of Closure 26: 13562.2892; Year of Closure 30: 10346.6055; Year of Closure 35: 7376.9867
| Revegetation Success | 363845.7749 | Year of Closure 1: 51298.1308; Year of Closure 2: 47942.1784; Year of Closure 3: 44805.7742; Year of Closure 4: 41874.5553; Year of Closure 5: 39135.0984; Year of Closure 6: 36574.8583; Year of Closure 8: 31945.8977; Year of Closure 11: 26077.3685; Year of Closure 15: 19894.2996; Year of Closure 20: 14184.3606; Year of Closure 25: 10113.2531; Year of Closure 30: 7210.6097; Year of Closure 35: 5141.0651
| Soil and Vegetation Chemistry | 242318.7257 | Year of Closure 3: 70742.8229; Year of Closure 6: 57747.2161; Year of Closure 10: 44055.0747; Year of Closure 15: 31410.6594; Year of Closure 20: 22395.366; Year of Closure 25: 15967.5865; Year of Closure 30: 11384.6685; Year of Closure 35: 8117.1113
| Wildlife Aerial Surveys | 724992.6371 | Year of Closure 1: 147164.486; Year of Closure 2: 137536.9028; Year of Closure 3: 128539.1615; Year of Closure 6: 104926.2446; Year of Closure 10: 80047.7296; Year of Closure 15: 57072.9249; Year of Closure 20: 40692.2067; Year of Closure 25: 29012.981
| Aquatics | 478018.3376 | Year of Closure 1: 97031.7757; Year of Closure 2: 90683.9025; Year of Closure 3: 84751.3108; Year of Closure 6: 69182.315; Year of Closure 10: 52778.8569; Year of Closure 15: 37630.5955; Year of Closure 20: 26830.0945; Year of Closure 25: 19129.4866; Year of Closure 30: 13639.0596; Year of Closure 35: 9724.461
| Effluent | 98781.4324 | Year of Closure 1: 20051.4019; Year of Closure 2: 18739.6279; Year of Closure 3: 17513.6709; Year of Closure 6: 14296.3724; Year of Closure 10: 10906.6341; Year of Closure 15: 7776.2794; Year of Closure 20: 5544.3797; Year of Closure 25: 3953.0661; Year of Closure 30: 2818.4815; Year of Closure 35: 2009.5384
| Instrumentation Maintenance/Replacement | 233071.6636 | Year of Closure 1: 18691.5888; Year of Closure 2: 17468.7746; Year of Closure 3: 16325.9575; Year of Closure 4: 15257.9042; Year of Closure 5: 14259.7236; Year of Closure 6: 13326.8445; Year of Closure 7: 12454.9948; Year of Closure 8: 11640.1821; Year of Closure 9: 10878.6749; Year of Closure 10: 10166.9858; Year of Closure 11: 9501.8559; Year of Closure 12: 8880.2392; Year of Closure 13: 8299.289; Year of Closure 14: 7756.3448; Year of Closure 15: 7248.9204; Year of Closure 16: 6774.692; Year of Closure 17: 6331.4878; Year of Closure 18: 5917.2783; Year of Closure 19: 5530.1667; Year of Closure 20: 5168.3801; Year of Closure 21: 4830.2617; Year of Closure 22: 4514.2633; Year of Closure 23: 4218.9377; Year of Closure 24: 3942.9324; Year of Closure 25: 3684.9836; Year of Closure 30: 2627.3423; Year of Closure 35: 1873.2588
| Road Closure and Reclamation | 53803.6609 | Year of Closure 3: 23071.5408; Year of Closure 15: 30732.1201
| Total | 8110028.1274 | 819414.9533 | 783337.4094 | 825905.4005 | 741844.7082 | 693312.8114 | 894108.0467 | 354575.9729 | 363325.3117 | 298784.1806 | 477227.9092 | 270886.2866 | 237704.2574 | 176238.9455 | 147533.5375 | 329672.6188 | 94225.537 | 88061.2496 | 88237.9262 | 76916.1058 | 140923.3699 | 29230.8059 | 31254.3863 | 24976.2138 | 22823.467 | 99506.7163 | 19946.7815 | 0 | 0 | 0 | 101350.2608 | 0 | 0 | 0 | 0 | 72261.3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Lists
5
YG Hire | Blaster
BC Blue Book | General Labourer
Owner | Trades Labourer
Camp Labourer
Site Caretaker
Mechanic
6 | Environmental Monitor
Total LOM | Site Supervisor
EOM | Design Engineer
Environmental Scientist
Passive Treatment Specialist
Project Manager
1
YG
Mining
2
Low
Medium
High

## Erosion
Table 21
Sediment & Erosion Control
[7 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | EOM
Item No. | Work Item Description | Equipment/Labour | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total
Diversion Ditch Construction (Operational ditches to be used)
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Sediment Pond Construction
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Equipment
Labour
Load, Haul, Dump
Misc
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total Estimated Cost for Sediment & Erosion Control | [10 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0

## Tailings
Table 15
Tailings Facilities
[7 empty] | Current |  |  |  |  | Year 2 |  |  |  |  | EOM
Item No. | Work Item Description | Equipment/Labour | Productivity | Units | Unit Rate | Units | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total | Quantity | Units | Rate Quantity | Units | Total
Included in the reclamation of Class A Storage Facility
Equipment
Labour
Materials
| Sub-Total | [9 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Total Estimated Cost in Reclaiming Tailings Facilities | [10 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0